## co.p (hidden)
Date: 22.03.2011
PROGRESS REPORT OF 271 SUB-CENTERS

## Abs (hidden)
ABSTRACT Construction of CEMONC Centres, Birth Waiting Homes & Sub-centers
S.No | Year | Total sanctioned (No.) | Started (No.) | Completed (No.) | Handed over (No.) | To be completed | Works not taken up | Financial out lay (Rs. In lakhs) | Amount Released (Rs. In lakhs) | Expenditure (Rs. In lakhs) | Balance Amount (Rs. In lakhs) | Remarks | Page No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 13
A) | CEMONC CENTERS
| 2007-08 | 151 | 121 | 111 | 111 | 10 | 30 | 6535.8 | 6535.8 | 6489.6891 | 0 |  | 1 - 13
B) | BIRTH WAITING HOMES
| 2006-07 | 38 | 37 | 37 | 37 | 0 | 1 | 384.8 | 384.8 | 377.6137 | 0 |  | 14 - 18
B) | OTHER WORKS:
|  | 3 | 3 | 1 | 1 | 1 |  | 602.5 | 548.5 | #REF! | 54 |  | 14
(sub center funds utilized for Niloufer Hospital)
C) | CENTRES OF EXCELLENCE FOR MATERNAL AND CHILDREN'S HEALTH
| 2010-11 | 5 | 5 |  |  | 5 |  | #REF! | 600 | #REF! | #REF! |  | 39
D) | SUBCENTERS
| 2009-10 (NRHM) | 271 | 260 | 186 | 186 | 74 | 11 | 2439 | 2080 | #REF! | 359 |  | 17 - 38
D) | INCOMPLETE PHCs
|  | 5 | 5 | 5 | 5 | 0 | 0 | 45.63 | 45.63 | 45.63 | 0 |  | 44
| TOTAL | [6 empty] | #REF! | 9764.3 | #REF! | #REF!

## CEMONC (hidden)
SCHEME : RCH-II (CEMONC CENTERS)
Sl. No. | Name of the work | Date of sanction by CFW | Date of Starting work | Report submitted by the EE during Previous Review | Progress (Stage) of work | Date of handing over to user department | Report furnished as on 21-09-2010 | Month by which likely to be completed | Financial Out lay | Re-revised Sanction (Rs.in lakhs) | Expenditure | Balance
DISTRICT : SRIKAKULAM
1 | Palakonda | 17.12.2007 | 20.06.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 52 |  | 122.71 | 15.79
2 | Narasannapeta | 17.12.2007 |  | Work completed and handed over | Work completed and handed over |  |  | Completed | 58
3 | Srikakulam | 17.12.2007 |  | Work completed and handed over | Work completed and handed over |  |  | Completed | 28.5
4 | Palasa | 17.12.2007 | 01.04.2008 | Work completed and handed over | Work completed and handed over |  |  | Completed | 34 |  | 16.89 | 17.11
5 | Ichapuram | 17.12.2007 | 25.02.2008 | Work completed and handed over | Work completed and handed over |  |  | Completed | 53.2 |  | 60.7 | -7.5
| TOTAL | [7 empty] | 225.7 |  | 200.3 | 25.4
DISTRICT : VIZIANAGARAM
6 | Saloor | 17.12.2007 | 16.07.2007 | Work completed | Work completed |  |  | Completed | 48 | 57.5 | 41.22 | 6.78
7 | Parvathipuram | 17.12.2007 |  | Paintings work under progress. | Work completed |  |  | Completed | 37.8 |  | 19.87 | 17.93
8 | S. Kota | 17.12.2007 | 06.02.2008 | Work completed and handed over | Work completed and handed over |  |  | Completed | 48.75 | 62 | 48.79 | -0.04
9 | Cheepurapalli | 17.12.2007 | 28.08.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 50 | 65.6 | 51.04 | -1.04
10 | Gajapathinagaram | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 54 |  | 0 | 54
11 | Bobbilli | 17.12.2007 | 25.10.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 39.1 |  | 41.03 | -1.93
12 | MCH Vizianagaram CEOMENC Unit. | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 76 |  | 0 | 76
13 | UFWC Vizianagaram | 17.12.2007 | 29.10.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 47.75 |  | 49.92 | -2.17
| TOTAL | [7 empty] | 401.4 | 185.1 | 251.87 | 149.53
DISTRICT : VISAKHAPATNAM
14 | Anakapalli | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 100.05 |  | 0 | 100.05
15 | Arakuvelly | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 80.04 |  | 0 | 80.04
16 | Chintapalli (Tribal) No specialist | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 58.7 |  | 0 | 58.7
17 | Narsipatnam | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 57.36 |  | 0 | 57.36
18 | Paderu | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 76.04 |  | 0 | 76.04
19 | Aganampudi | 17.12.2007 | 27.02.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 50.59 | 55.99 | 49.57 | 1.02
20 | Chodavaram | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 26.68 |  | 0 | 26.68
21 | KGH | 17.12.2007 | 17.03.2008 | Work completed and handed over | Work completed and handed over |  |  | Completed | 106.72 | 124.73 | 117.51 | 7.22
22 | Victoria | 17.12.2007 | 15.02.2008 | Work completed and handed over | Work completed and handed over |  |  | Completed | 126.73 | 147.29 | 136.32 | 10.97
| TOTAL | [7 empty] | 682.91 | 328.01 | 303.4 | 418.08
DISTRICT : EAST GODAVARI
23 | CHC Àmalapuram | 17.12.2007 | 07.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 48 |  | 96.79 | 42.21
24 | Kothapeta | 17.12.2007 | [5 empty] | Completed | 51
25 | Razole | 17.12.2007 | [5 empty] | Completed | 40
26 | Addateegala | 17.12.2007 | 28.05.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 45 | 49 | 36.06 | 8.94
27 | Pathipadu | 17.12.2007 | 22.05.2007 | Work completed to be inagurated | Work completed to be inagurated |  |  | Completed | 80 | 92 | 49.86 | 30.14
28 | Tuni | 17.12.2007 | 22.02.2008 | Work completed and handed over | Work completed and handed over |  |  |  | 101.38 | 124 | 94.22 | 7.16
29 | Peddapuram | 17.12.2007 | 22.05.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 50 |  | 45.46 | 4.54
30 | Dist Hosp. Rajahmundry | 17.12.2007 | 01.09.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 90 | 96 | 84.65 | 5.35
31 | PPU Kakinada | 17.12.2007 | 01.09.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 86 | 98 | 73.44 | 12.56
| TOTAL | [7 empty] | 591.38 | 459 | 480.48 | 110.9
DISTRICT : WEST GODAVARI
32 | Chintalapudi | 17.12.2007 |  | Deleted | Deleted |  |  |  | 55 |  | 0 | 55
33 | Jangareddygudem | 17.12.2007 | 07.03.2007 | Work Completed and handed over. | Work Completed and handed over. |  |  | Completed | 16.65 |  | 15.95 | 0.7
34 | Polavaram | 17.12.2007 | 07.03.2007 | Work completed to be inagurated | Work completed to be inagurated |  |  | Completed | 20 | 25 | 10.45 | 9.55
35 | T.P.Gudem | 17.12.2007 | 17.05.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 138 |  | 129.12 | 8.88
36 | Tanuku | 17.12.2007 |  | Work completed and handed over | Work completed and handed over |  |  | Completed
37 | Kovvuru | 17.12.2007 |  | Work completed and handed over | Work completed and handed over |  |  | Completed
38 | Bhimavaram | 17.12.2007 |  | Deleted | Deleted |  |  |  | 6.95 |  | 0 | 6.95
39 | Narasapur | 17.12.2007 | 26.02.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 20 |  | 18.36 | 1.64
40 | Palacole | 17.12.2007 | 17.05.2007 | Work completed handed over | Work completed handed over |  |  | Completed | 45 | 55 | 41.98 | 3.02
41 | District Hospital, Eluru | 17.12.2007 | 26.03.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 20 |  | 18.64 | 1.36
| TOTAL | [7 empty] | 321.6 | 80 | 234.5 | 87.1
DISTRICT : KRISHNA
42 | Vijayawada | 17.12.2007 |  | Deleted | Deleted |  |  |  | 71.37 |  | 0 | 71.37
43 | Avanigadda | 17.12.2007 | 31.08.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 65 |  | 59.86 | 5.14
44 | Tiruvuru | 17.12.2007 | 16.03.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 13 |  | 11.91 | 1.09
45 | Nuziveedu | 17.12.2007 | 28.05.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 54 |  | 61.5 | -7.5
46 | Gudivada | 17.12.2007 |  | Deleted | Deleted |  |  |  | 63.68 |  | 0.08 | 63.6
| TOTAL | [7 empty] | 267.05 |  | 133.35 | 133.7
DISTRICT : GUNTUR
Package-I
47 | GGH | 17.12.2007 | 23.04.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 215 | 264.85 | 55.55 | 16.34
48 | Narasaraopeta |  |  | Work completed and handed over | Work completed and handed over |  |  | Completed |  |  | 39.26
49 | Sattenapalli |  |  | Work completed and handed over | Work completed and handed over |  |  | Completed |  |  | 49.89
50 | Vinukonda |  |  | Work completed and handed over | Work completed and handed over |  |  | Completed |  |  | 53.96
Package-II
51 | Macherla | 17.12.2007 |  | Work completed and handed over | Work completed and handed over |  |  | Completed | 51.23 |  | 49.07 | 2.16
Package-III
52 | District Hospital (Tenali) | 17.12.2007 | 26.02.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 11.14 |  | 8.55 | 2.59
| TOTAL | [7 empty] | 277.37 | 264.85 | 256.28 | 21.09
DISTRICT : PRAKASAM
53 | Giddaluru | 17.12.2007 | 01.05.2007 | Roof slab laid for OP block and 20 bed ward completed upto basement level for 10 bed ward. Further work to be taken up. | Roof slab laid for OP block and 2 IP wards, one IP ward at roof level. |  |  | RAS required to take up balance work | 48.5 |  | 27.12 | 67.38
54 | Kanigiri | 17.12.2007 |  | Work completed to be inagurated | Work completed to be handed over. |  |  | Completed | 46 | 55 | 34.24
| TOTAL | [7 empty] | 94.5 | 55 | 61.36 | 67.38
DISTRICT : NELLORE
55 | Atmakur | 17.12.2007 | 19.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 58.5 |  | 51.04 | 7.46
56 | Guduru | 17.12.2007 | 28.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 70 | 84 | 65.36 | 4.64
57 | Kavali | 17.12.2007 | 10.05.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 42 | 61 | 43.66 | -1.66
58 | Sullurupet | 17.12.2007 | 01.05.2008 | Work cancelled and balance work entrusted to another agency | Work cancelled and balance work entrusted to another agency |  |  | Completed | 93.38 | 102.5 | 42.38 | 51
59 | Udayagiri | 17.12.2007 | 13.10.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 58.8 |  | 51.42 | 7.38
60 | Venkatagiri Ghosha Hospital | 17.12.2007 | 18.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 43 |  | 42.05 | 0.95
61 | Nellore MCH | 17.12.2007 | 05.03.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 13.5 | 14.3 | 12.33 | 1.17
| TOTAL | [7 empty] | 379.18 | 261.8 | 308.24 | 70.94
DISTRICT : CHITTOOR
62 | Bangarupalem | 17.12.2007 | 24.05.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 45.5 |  | 40.98 | 4.52
63 | Madanapalli | 17.12.2007 | 09.03.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 61 |  | 144.87 | 16.13
64 | Punganur | 17.12.2007 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 54.5
65 | Pileru | 17.12.2007 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 45.5
66 | SriKalahasthi | 17.12.2007 | 01.03.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 60 |  | 61.7 | -1.7
67 | Kuppam | 17.12.2007 | 04.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 52.5 |  | 53.05 | -0.55
68 | Puttur | 17.12.2007 | 08.03.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 52.5 |  | 45.55 | 6.95
69 | Satyaveedu | 17.12.2007 |  | Deleted | Deleted |  |  |  | 63.5 |  | 0 | 63.5
| TOTAL | [7 empty] | 435 |  | 346.15 | 88.85
DISTRICT : ANANTHAPUR
70 | GGH | 17.12.2007 | 22.01.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 71.37 | 86.37 | 64.14 | 7.23
71 | Kalyanadurgam | 17.12.2007 | 28.01.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 52.03 | 60.03 | 45.86 | 6.17
72 | Dharmavaram | 17.12.2007 | 02.08.2007 | Columns completed upto roof slab.(work determind | Columns completed upto roof slab.(work determind |  |  |  | 58 | 117.57 | 19.38 | 38.62
73 | Gooty | 17.12.2007 | 10.04.2007 | Deleted | Deleted |  |  |  | 42 |  | 0 | 87
74 | Tadipatri | 17.12.2007 |  | Deleted | Deleted |  |  |  | 45
75 | Madakasira | 17.12.2007 | 23.05.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 37 | 42.07 | 36.79 | 0.21
76 | Kadiri | 17.12.2007 | 14.06.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 60 | 114.8 | 35.75 | 24.25
77 | Penugonda | 17.12.2007 | 11.06.2007 | Finishings are in progress. | Work completed. |  |  | Completed | 50 | 90 | 25.88 | 24.12
78 | Hindupur | 17.12.2007 | 18.07.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 53 | 110 | 52.81 | 0.19
| TOTAL | [7 empty] | 468.4 | 620.84 | 280.61 | 187.79
DISTRICT : KADAPA
79 | Badvel | 17.12.2007 | 10.05.2007 | Work completed to the extent of sanction and handed over. | Work completed to the extent of sanction and handed over. |  |  | Completed | 81.36 | 126.11 | 133.07 | 13.83
80 | Proddatur | 17.12.2007 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 65.54
81 | Jammalamadugu | 17.12.2007 | 17.04.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 62.15 | 72.15 | 56.6 | 5.55
82 | Rajampet | 17.12.2007 | 23.04.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 51.98 | 71.98 | 70.53 | 33.43
83 | Rayachoty | 17.12.2007 |  | Work completed to be inagurated | Work completed to be inagurated |  |  | Completed | 51.98 | 71.98
| TOTAL | [7 empty] | 313.01 | 342.22 | 260.2 | 52.81
DISTRICT : KURNOOL
84 | KMC | 17.12.2007 |  | Deleted | Deleted |  |  |  | 103.75 |  | 0 | 103.75
85 | Dhone | 17.12.2007 | 23.04.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 54.52 |  | 49.97 | 4.55
86 | Koilakuntla | 17.12.2007 | 05.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 55 |  | 111.79 | 2.21
87 | DH. Nandyal | 17.12.2007 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 59 |  | 0
88 | Pattikonda | 17.12.2007 | 23.04.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 47 |  | 40.37 | 6.63
89 | Srisailam | 17.12.2007 | 16.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 59 |  | 100.78 | 5.22
90 | Nandikotkuru | 17.12.2007 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 47
91 | Adoni Area Hospital (MCH) | 17.12.2007 | 02.06.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 57.07 |  | 54.19 | 2.88
92 | Yemmiganur | 17.12.2007 |  | Deleted | Deleted |  |  |  | 17.8 |  | 0 | 17.8
| TOTAL | [7 empty] | 500.14 |  | 357.1 | 143.04
DISTRICT : MAHABOOBNAGAR
93 | Mahaboobnagar | 17.12.2007 | 18.10.2007 | Work completed and handed over. | Work completed and handed over. |  |  | completed | 64.41 | 73.2 | 51.51 | 12.9
94 | Shadnagar | 17.12.2007 | 02.07.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 53.36 |  | 42.32 | 11.04
95 | Atchampet | 17.12.2007 | 26.12.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 50.69 | 59.86 | 45.84 | 4.85
96 | Nagarkurnool | 17.12.2007 |  | Deleted | Deleted |  |  |  | 58.7 |  | 0 | 58.7
97 | Gadwal | 17.12.2007 |  | Work completed to be inagurated | Work completed |  |  | Completed | 80.04 | 96.04 | 77.96 | 2.08
98 | Wanaparthy | 17.12.2007 | 28.12.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 60.03 | 71.62 | 50.59 | 9.44
99 | Narayanpet | 17.12.2007 | 10.09.2007 | Work completed and handed over. | Work completed and handed over. |  |  | completed | 50.59 | 52.79 | 46.65 | 3.94
100 | Makthal | 17.12.2007 | 17.05.2008 | Work completed and handed over. | Work completed and handed over. |  |  | completed | 72.04 | 80.6 | 56.31 | 15.73
| TOTAL | [7 empty] | 489.86 | 434.11 | 371.18 | 118.68
DISTRICT : HYDERABAD
101 | Osmania (Niloufer) | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 620 |  | 369.6 | 250.4
102 | Sultan Bazar | 17.12.2007 | 20.12.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 162.75 | 195.75 | 127.54 | 35.21
| TOTAL | [7 empty] | 782.75 | 195.75 | 497.14 | 285.61
DISTRICT : RANGA REDDY
103 | Parigi | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 69.37 |  | 0 | 69.37
104 | Vikarabad | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 62.65 |  | 0 | 62.65
105 | Hayathnagar | 17.12.2007 | 21.04.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 109.35 | 150 | 103.54 | 5.81
106 | Kondapur | 17.12.2007 | --- | Deleted | Deleted |  |  |  | 80 |  | 0 | 80
| TOTAL | [7 empty] | 321.37 | 150 | 103.54 | 217.83
DISTRICT : NALGONDA
107 | Bhongir | 17.12.2007 | 22.05.2007 | Work completed handed over. | Work completed and handed over. |  |  | Completed | 56 | 61.5 | 52.08 | 3.92
108 | Devara Konda | 17.12.2007 | 19.07.2007 | Work completed handed over. | Work completed and handed over. |  |  | Completed | 52 | 54 | 47.99 | 4.01
109 | Miryalaguda | 17.12.2007 | --- | Deleted | Deleted |  |  | --- | 62.7 |  | 0.21 | 62.49
110 | Huzurnagar | 17.12.2007 |  | Deleted | Deleted |  |  |  | 44.02 |  | 0.21 | 43.81
| TOTAL | [7 empty] | 214.72 | 115.5 | 100.49 | 114.23
DISTRICT:MEDAK
111 | Medak | 17.12.2007 | 01.03.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 15 |  | 12.29 | 2.71
112 | Narayankhed | 17.12.2007 | 24.03.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 15 |  | 12.89 | 2.11
113 | Gazwel | 17.12.2007 | 24.03.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 15 |  | 13.15 | 1.85
114 | Siddipet | 17.12.2007 | 31.03.2007 | Revised sanction for Rs 80.00 lakhs is awaited from CFW. | Work completed and handed over |  |  | Completed | 65 | 70 | 60.55 | 4.45
115 | Zahirabad | 17.12.2007 |  | Deleted | Deleted |  |  |  | 81.37 |  | 0 | 81.37
116 | Sadasivpet | 17.12.2007 | 14.06.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 55 | 70 | 52.93 | 2.07
117 | Sanga Reddy | 17.12.2007 | 09.05.2007 | Work completed upto revised sanction for Rs.65.00 lakhs, additional Rs.14.70 lakhs requirement for left over items i.e. finishings. | Work completed upto revised sanction for Rs.65.00 lakes. |  |  | Completed | 65 | 84 | 59.55 | 5.45
| TOTAL | [7 empty] | 311.37 | 224 | 211.36 | 100.01
DISTRICT : NIZAMABAD
118 | Nzbd HQH | 17.12.2007 | 11.06.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 120 | 70.76 | 112.09 | 7.91
119 | Armoor Cemonc |  |  | Work completed and handed over | Work completed and handed over |  |  | Completed
120 | Baanswada | 17.12.2007 | 26.04.2007 | Deleted | Deleted |  |  |  | 52 |  | 0.17 | 51.83
121 | Kamareddy | 17.12.2007 | 19.12.2007 | Agreement terminated due to non availbility of site vide HO Memo No.2675, dt.25.07.08. | Agreement terminated due to non availbility of site vide HO Memo No.2675, dt.25.07.08. |  |  | Tenders will be recalled after finalization of site. | 96.98 |  | 0 | 96.98
122 | Bodhan | 17.12.2007 |  | Deleted | Deleted |  |  |  | 41 |  | 0.17 | 40.83
123 | Yellareddy | 17.12.2007 | 12.02.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 33.48 | 50.43 | 31.29 | 2.19
| TOTAL | 343.46 | [6 empty] | 343.46 | 121.19 | 143.72 | 199.74
DISTRICT : WARANGAL
124 | CKM | 17.12.2007 | 19.12.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 96.05 |  | 90.91 | 5.14
125 | MGM | 17.12.2007 | 19.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 114 |  | 106.67 | 7.33
126 | Jangaon | 17.12.2007 |  | Work Cancelled | Work Cancelled |  |  |  | 55 |  | 0 | 0
127 | Mahabubabad | 17.12.2007 | 23.04.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 32 |  | 57.55 | 15.05
128 | Narsampet | 17.12.2007 | [5 empty] | Completed | 40.6
129 | Mulugu | 17.12.2007 | 16.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 63 |  | 56.43 | 6.57
130 | Wardhannapet | 17.12.2007 | 16.07.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 87 |  | 78.47 | 8.53
131 | Parkal | 17.12.2007 | 16.07.2007 | Work completed handed over. | Work completed handed over. |  |  | Completed | 42 |  | 38.69 | 3.31
| TOTAL | [7 empty] | 529.65 |  | 428.72 | 45.93
DISTRICT : KHAMMAM
132 | Kothagudem | 17.12.2007 | 25.04.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 55.8 |  | 106.82 | 8.98
133 | Bhadrachalam | 17.12.2007 | 25.04.2007 | Work completed and handed over | Work completed and handed over |  |  | Completed | 60
134 | Sattupalli | 17.12.2007 |  | Work restricted to extent of administrative sanction. Finishings are in progress. CFW was requested for according revised administrative sanction for Rs.78.70 lakhs for completing the work in full shape. | Plastering work is completed and doors and windows fixing work is in progress. |  |  | 90 % completed for remaining RAS required | 63.37 | 78.37 | 53.36 | 10.01
135 | Aswaraopet | 17.12.2007 |  | Work restricted to extent of administrative sanction. Finishings are in progress. CFW was requested for according revised administrative sanction for Rs.65.00 lakhs for completing the work in full shape. | Plastering work is completed and doors and windows fixing work is in progress. |  |  | 95 % completed for remaining RAS required | 50.69 | 63.69 | 41.21 | 9.48
136 | Cherla | 17.12.2007 | 24.01.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 39.35 | 55.35 | 36.88 | 2.47
137 | Chintoor | 17.12.2007 |  | Deleted | Deleted |  |  |  | 38.69 |  | 0 | 38.69
| TOTAL | [7 empty] | 307.9 | 197.41 | 238.27 | 69.63
DISTRICT : KARIMNAGAR
138 | Karimnagar | 17.12.2007 | 17.05.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 50.5 |  | 48.4 | 2.1
139 | Jagtial | 17.12.2007 | 02.03.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 35 |  | 32.25 | 2.75
140 | Sircilla | 17.12.2007 | 13.02.2007 | Plastering completed. Flooring & painting to be completed. | Work completed. |  |  | Completed | 20 |  | 12.86 | 7.14
141 | Peddapalli | 17.12.2007 | 29.10.2007 | Roof slab laid and brick work completed. Plastering completed. The remaining work not done due to lack of administrative sanction. Hence the balance work estimate submitted amount to Rs.19.00 lakhs. | Roof slab laid and finishings are in progress. |  |  | Completed | 38 | 60.51 | 34.65 | 3.35
142 | Huzurabad | 17.12.2007 | 19.11.2007 | Work completed and Handed over | Work completed and Handed over |  |  | Completed | 47 | 51.29 | 45.05 | 1.95
143 | Mantheni | 17.12.2007 | 09.05.2007 | Work completed and Handed over | Work completed and Handed over |  |  | Completed | 31 |  | 29.19 | 1.81
144 | Mahadevapur | 17.12.2007 | 14.06.2007 | Work completed & handed over. | Work completed & handed over. |  |  | Completed | 44 | 45.29 | 39.64 | 4.36
| TOTAL | [7 empty] | 265.5 | 157.09 | 242.04 | 23.46
DISTRICT : ADILABAD
145 | Adilabad HQH | 17.12.2007 | 23.04.2007 | Work completed to the extent of sanction amount | Roof slab laid and finishings are in progress. |  |  | Completed | 71 | 117.24 | 65.35 | 5.65
146 | Mancherial | 17.12.2007 |  | Deleted | Deleted |  |  |  | 50 |  | 0 | 50
147 | Utnoor | 17.12.2007 | 30.04.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 50 |  | 46.68 | 3.32
148 | Khanapur | 17.12.2007 | 15.03.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 20 |  | 18.39 | 1.61
149 | Nirmal | 17.12.2007 | 11.06.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 53 |  | 48.09 | 4.91
150 | Luxettipet | 17.12.2007 | 02.06.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 28 |  | 26.26 | 1.74
151 | Kagaznagar Cemonc | 17.12.2007 | 02.06.2007 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 53 |  | 50.06 | 2.94
| TOTAL | [7 empty] | 325 | 117.24 | 254.83 | 70.17
[9 empty] | 8849.22 | 4309.11 | 6065.13 | 2801.9
| Add: 7% Establishment charges | [9 empty] | 424.5591
| Grand Total | [9 empty] | 6489.6891
Note on D192: Plande: As per LOA Lr.

## BWH (hidden)
BIRTH WAITING HOMES
Sl. No. | Name of the work | Date of sanction by CFW | Date of starting work | Report submitted by the EE during Previous Review | Progress (Stage) of work | Date of handing over to user department | Report furnished as on 21-09-2010 | Month by which likely to be completed. | Fianancial Outlay | Amount released | Expenditure | Balance
DISTRICT : SRIKAKULAM
1 | CHC, Pathapatnam | dt.02/01/07 | 05.02.2008 | Work completed. Handed over. | Work completed. Handed over. |  |  | Completed | 10.4 |  | 8.02 | 2.38
2 | Seethampet | dt.02/01/07 | 13.03.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 8.84 | 1.56
3 | CHC, Koturu | dt.02/01/07 | 13.03.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.59 | 0.81
4 | Palakonda Area Hospital, APVVP | dt.02/01/07 | 29.01.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 8.44 | 1.96
5 | CHC, Palasa (Muliputti) | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 10.69 | -0.29
| TOTAL | [7 empty] | 52 |  | 45.58 | 6.42
DISTRICT : VIZIANAGARAM
6 | CHC, Saluru | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 11.83 | -1.43
7 | AH, Parvathipuram | dt.02/01/07 |  | Work completed | Work completed |  |  | Completed | 10.4 |  | 10.64 | -0.24
8 | UPHC, Kurupam | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 11.41 | -1.01
9 | PHC, Vepada | dt.02/01/07 |  | Work completed to be inagurated | Work completed to be inagurated |  |  | Completed | 10.4 |  | 11.79 | -1.39
| TOTAL | [7 empty] | 41.6 |  | 45.67 | -4.07
DISTRICT : VISAKHAPATNAM
10 | CHC, Paderu | dt.02/01/07 | 09.02.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 8.76 | 1.64
11 | CHC, Araku | dt.02/01/07 | 09.02.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.08 | 1.32
12 | CHC, Chintapalli | dt.02/01/07 | 09.02.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 8.58 | 1.82
13 | UPHC, Hukumpet | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.17 | 1.23
| TOTAL | [7 empty] | 41.6 |  | 35.59 | 6.01
DISTRICT : EAST GODAVARI
14 | CHC, Rampachodavaram | dt.02/01/07 | 09.07.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.46 | 0.94
15 | AH, Rajahmundry | dt.02/01/07 | 20.02.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.01 | 1.39
16 | CHC, Addateegala | dt.02/01/07 | 09.07.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.48 | 0.92
17 | CHC, Rajuva Mangi | dt.02/01/07 | 09.07.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 10.12 | 0.28
| TOTAL | [7 empty] | 41.6 |  | 38.07 | 3.53
DISTRICT : WEST GODAVARI
18 | CHC, Koyalagudem | dt.02/01/07 | 10.03.2008 | Work completed to be inagurated | Work completed to be inagurated |  |  | Work completed | 10.4 |  | 9.74 | 0.66
19 | CHC, Polavaram | dt.02/01/07 | 10.03.2008 | Work completed to be inagurated | Work completed to be inagurated |  |  | Completed | 10.4 |  | 7.88 | 2.52
20 | PHC, P.R.Gudem | dt.02/01/07 | 24.03.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.9 | 0.5
21 | CHC, Jellugumilli | dt.02/01/07 | 27.02.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 10.12 | 0.28
| TOTAL | [7 empty] | 41.6 |  | 37.64 | 3.96
DISTRICT : PRAKASAM
22 | CHC, Y.Palem | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 8.93 | 1.47
23 | GH, Dornala | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 8.75 | 1.65
| TOTAL | [7 empty] | 20.8 |  | 17.68 | 3.12
DISTRICT : KURNOOL
24 | CHC, Athmakur | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.72 | 0.68
25 | Porject Hospital, Srisailam | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.71 | 0.69
| TOTAL | 20.8 | [6 empty] | 20.8 |  | 19.43 | 1.37
DISTRICT : MAHABOOBNAGAR
26 | CHC, Achampet | dt.02/01/07 | 05.03.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.49 | 0.91
27 | PHC, Siddapur | dt.02/01/07 | 15.05.2008 | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.19 | 1.21
| TOTAL | 20.8 | [6 empty] | 20.8 |  | 18.68 | 2.12
DISTRICT : KHAMMAM
28 | GH, Chintoor | dt.02/01/07 |  | Differed | Differed |  |  | Differed | 10.4 |  | 0 | 10.4
29 | CHC, Charla | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 10.4 | 0
30 | AH, Bhadrachalam | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.72 | 0.68
31 | CHC, Yellandu | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.56 | 0.84
| TOTAL | [7 empty] | 41.6 |  | 29.68 | 11.92
DISTRICT : WARANGAL
32 | CHC, Eturnagaram | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 10.11 | 0.29
33 | CHC, Mulugu | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 8.95 | 1.45
34 | AH, Mahabubabad | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.49 | 0.91
| TOTAL | [7 empty] | 31.2 |  | 28.55 | 2.65
DISTRICT : ADILABAD
35 | CHC, Utnoor | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.46 | 0.94
36 | CHC, Asifabad | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 8.73 | 1.67
37 | AH, Mancherial | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 8.69 | 1.71
38 | PHC, Jainoor | dt.02/01/07 |  | Work completed and handed over. | Work completed and handed over. |  |  | Completed | 10.4 |  | 9.46 | 0.94
| TOTAL | [7 empty] | 41.6 |  | 36.34 | 5.26
| GRAND TOTAL | [7 empty] | 395.2 |  | 352.91 | 42.29
| Add: 7% Establishment charges | [9 empty] | 24.7037
377.6137

## NRHM-incomplete PHCs (hidden)
NRHM - Complete of incomplete PHCs
Sl. No. | Name of the work | Date of sanction by CFW | Date of Starting work | Progress (Stage) of work | Date of handing over to user department | Month by which likely to be completed | Financial Out lay | Amount released | Expenditured | Balance
1 | Manuguru, Khammam Dist. | 29.07.08 |  | Work completed and handed over |  | completed | 9.63 | 9.63 | 9.63 | 0
2 | Mandapeta, East Godavari Dist. | 29.07.08 |  | Work completed and handed over |  | completed | 12 | 12 | 12 | 0
3 | Bhiminipalli, East Godavari Dist. | 29.07.08 |  | Work completed |  | completed | 4 | 4 | 4 | 0
4 | Gudlavalluru, Krishna | 29.07.08 |  | Work completed and handed over |  | completed | 10 | 10 | 10 | 0
5 | Thotalavalluru, Krishna Dist. | 29.07.08 |  | Work completed and handed over |  | completed | 10 | 10 | 10 | 0
| TOTAL | [5 empty] | 45.63 | 45.63 | 45.63 | 0
Note on B3: Procdg.No.426/RCH-II/2008, dt.29.07 08

## co.p (3)
Dt:19.01.2016
8.35
Construction of (271) Sub-Centre Building for the year 2009-10 under NRHM

## ABS 271 Sub. (2) (hidden)
STATUS OF 271 SUB-CENTERS UNDER NRHM
Sl. No. | Name of the District | Administrative sanction amount (Rs. in lakhs) | No. of works | Stage of work |  |  |  |  | Expenditure (Rs.in lakhs) | Remarks
|  |  |  | Site problem if any | Work not takenup | Tender stage | Works progress | Completed
1 | Srikakulam | 117 | 13 |  |  |  | 1 | 12 | #REF!
2 | Vizianagaram | 72 | 8 |  |  |  |  | 8 | #REF!
3 | Vishakhapatnam | 162 | 18 |  | 1 |  | 1 | 16 | #REF!
4 | East Godavari | 153 | 17 |  | 2 |  |  | 15 | #REF!
5 | West Godavari | 99 | 11 |  |  | 1 |  | 10 | #REF!
6 | Krishna | 99 | 11 |  |  |  | 1 | 10 | #REF!
7 | Guntur | 117 | 13 |  |  |  |  | 13 | #REF!
8 | Prakasam | 153 | 17 |  |  |  | 2 | 15 | #REF!
9 | Nellore | 81 | 9 |  |  |  |  | 9 | #REF!
10 | Chittoor | 90 | 10 |  |  |  | 1 | 9 | #REF!
11 | Kadapa | 108 | 12 |  |  |  |  | 12 | #REF!
12 | Ananthapur | 99 | 11 |  |  |  |  | 11 | #REF!
13 | Kurnool | 126 | 14 |  |  |  |  | 14 | #REF!
14 | Mahaboobnagar | 108 | 12 |  |  |  |  | 12 | #REF!
15 | Ranga Reddy | 90 | 10 |  |  |  | 2 | 8 | #REF!
16 | Medak | 90 | 10 |  |  |  |  | 10 | #REF!
17 | Nizamabad | 117 | 13 |  |  |  |  | 13 | #REF!
18 | Adilabad | 99 | 11 |  |  |  | 2 | 9 | #REF!
19 | Karimnagar | 126 | 14 |  | 2 |  | 1 | 11 | #REF! | The building is already constructed at Thimmapur. Hence, the work may be cancelled.
20 | Warangal | 135 | 15 |  |  |  |  | 15 | #REF!
21 | Khammam | 117 | 13 |  |  |  | 1 | 12 | #REF! | Work completed under LWE funds at Jaganadhapuram.
22 | Nalgonda | 81 | 9 | 0 |  |  |  | 9 | #REF!
| TOTAL | 2439 | 271 | 0 | 5 | 1 | 12 | 253 | #REF!

## abs monthwise
ABSTRACT
STATUS OF 271 SUB-CENTERS UNDER NRHM
Sl. No. | Name of the District | AS / RAS amount (Rs. in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up (6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other dept | Site problem | RAS awaited or etc | Total (7+8+9) |  | Completed | Work to be started | Works progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | SKLM | 123.5 | 106.86 |  | 13 |  |  |  |  | 13 | 13 |  |  | 13 | 0 | 13 | 0
2 | VZM | 72 | 71.51 |  | 8 |  | 0 | 0 |  | 8 | 8 |  |  | 8 | 0 | 8 | 0
3 | VSP | 164.5 | 141.62 |  | 18 | 1 | 0 | 0 | 1 | 17 | 17 |  |  | 17 | 0 | 17 | 0
4 | EG | 153 | 122.1 |  | 17 | 2 | 0 | 0 | 2 | 15 | 15 |  |  | 15 | 0 | 15
5 | WG | 99 | 86.82 |  | 11 |  |  |  |  | 11 | 11 |  |  | 11 | 0 | 11
6 | KRI | 106.5 | 97.66 |  | 11 |  |  |  |  | 11 | 11 |  |  | 11 | 0 | 11
7 | GNT | 117 | 105.86 |  | 13 |  |  |  |  | 13 | 13 |  |  | 13 |  | 13
8 | PKSM | 153 | 119.29 |  | 17 |  |  |  |  | 17 | 15 |  | 2 | 15 | 2 | 15 | 2
9 | NLR | 81 | 72.9384 |  | 9 |  |  |  |  | 9 | 9 |  |  | 9 | 0 | 9 | 0
10 | CTR | 90 | 86.31 |  | 10 |  |  |  |  | 10 | 10 |  |  | 10 |  | 10
11 | KDP | 108 | 94.18 |  | 12 |  |  |  |  | 12 | 12 |  |  | 12 |  | 12
12 | ATP | 99 | 80.86 |  | 11 |  |  |  |  | 11 | 11 |  |  | 11 |  | 11
13 | KNL | 126 | 117.38 |  | 14 |  |  |  |  | 14 | 14 |  |  | 14 | 0 | 14 | 0
| TOTAL | 1492.5 | 1303.3884 |  | 164 | 3 | 0 | 0 | 3 | 161 | 159 |  | 2 | 159 | 2 | 159 | 2
2499.9167
1465.5

## details
Construction of (271) Sub-Centres under NRHM
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
SRIKAKULAM
1 | SKLM | Meliaputti | Vasundara (Kosamala) | 19-9-2009 | 9.5 | 8.35 | Sri Y.Srinivas Rao | 26.11.12 | Work Completed & Final bill paid
2 | - do - | Jadupalli (V) Meliaputti (M) | Jadupalli |  | 9.5 | 8.35 | Sri M.Harikrishna | 14.10.2012 | Work Completed & Final bill paid
3 | - do - | Meliaputti | Heerapuram |  | 9.5 | 8.01 | Sri Y.Srinivas Rao | 5.3.2013 | Work Completed & Final bill paid
4 | - do - | Kothuru | Metturu |  | 9.5 | 8 | Sri P.Arjuna Rao | 13.3.2011 | Work Completed & Final bill paid
5 | - do - | L.N.Peta | Dabbapadu / Ravichandri |  | 9.5 | 8.12 | Sri R.Arjuna Rao | 22.10.12 | Work Completed & Final bill paid
6 | - do - | Pathapatnam | Rompavalasa |  | 9.5 | 7.84 | Sri M.Ramarao | 12.2.2012 | Work Completed & Final bill paid
7 | - do - | Mandasa | Mandasa |  | 9.5 | 8.41 | Sri V.Mohana Rao | 7.6.2010 | Work Completed & Final bill paid
8 | - do - | Pathapatnam | Koduru |  | 9.5 | 8.28 | Sri M.Ramarao | 3.1.2012 | Work Completed & Final bill paid
9 | - do - | Lavelru | Govindapuram |  | 9.5 | 8.99 | Sri M/s.A.Appalasuri | 28.10.2011 | Work Completed & Final bill paid
10 | - do - | Etcherla | Bhagiradhapuram |  | 9.5 | 8.39 | Sri P.Narisinga Rao | 17.11.2011 | Work Completed & Final bill paid
11 | - do - | Etcherla | Dharmavaram |  | 9.5 | 7.88 | Sri P.Narisinga Rao | 8.11.2011 | Work Completed & Final bill paid
12 | - do - | Etcherla | Penubarthi |  | 9.5 | 8.61 | M/s.Vijayalakshmi Constructions | 24.12.2011 | Work Completed & Final bill paid
13 | - do - | Ranastalam | P.V.Palem |  | 9.5 | 7.63 | Sri K.Kannam Naidu | 21.1.11 | Work Completed & Final bill paid
|  |  | TOTAL : |  | 123.5 | 106.86
VIZIANAGARAM
14 | VZM | Cheepurupalli | Pedanadipalli | 19-9-2009 | 9 | 8.89 | S.Srinivas Rao | 31.01.11 | Completed & Handed over
15 | - do - | Dathirajeru | Dathi |  | 9 | 8.82 | D.Bala krishna, | 31.03.12 | Completed & Handed over
16 | - do - | Bondapalli | Bondapalli |  | 9 | 8.96 | B.V.Prabhujee, | 31.08.11 | Completed & Handed over
17 | - do - | Gurla | Pedabantupalli |  | 9 | 8.92 | V.Suryanarayana, | 31.08.11 | Completed & Handed over
18 | - do - | Merakamudidham | Budarayavalasa |  | 9 | 8.98 | A.Chinnam Naidu, | 12.04.10 | Completed & Handed over
19 | - do - | Makkuva | Gaisala |  | 9 | 9 | J.B.Chowdary, | 25.12.10 | Completed & Handed over
20 | - do - | Pachipenta | Badnaikavalasa |  | 9 | 9 | N.Ravikumar, | 25.12.10 | Completed & Handed over
21 | - do - | Pachipenta | Viswanadhapuram |  | 9 | 8.94 | J.B.Chowdary, | 31.01.11 | Completed & Handed over
|  |  | TOTAL : |  | 72 | 71.51
VISHAKHAPATNAM
22 | VSP | Atchutapuram | Pudimadaka | 13.09.2008, | 9 | 8.32 | Sri K.Satyanaryana | 06.04.10 | Completed
23 | - do - | Munagapaka | Thotata |  | 9 | 7.22 | Sri P.Jagga Rao, | 27.04.11 | Completed
24 | - do - | Sabbavaram | Batajangala Palem |  | 9 | 8.38 | Sri P.Jagga Rao | 25.03.11 | Completed
25 | - do - | Devarapalli | Koligotla-II |  | 9 | 8.22 | Sri A.V.G.Jagannadha Rao, | 19.04.11 | Completed
26 | - do - | Butchaiahpeta | Dibbidi |  | 9 | 8.31 | Sri A.V.G.Jagannadha Rao | 20.04.11 | Completed
27 | - do - | Munagapaka | Vadarevupalli (Vadrapalli) |  | 9 | 8.26 | Sri Y.V.Mohan | 16.06.10 | Completed
28 | - do - | Munagapaka | Arubupalem |  | 9 | 8.32 | Sri K.Satyanaryana Murthy | 25.05.11 | Completed
29 | - do - | Parawada | Desupatrunipalem |  | 10.25 | 9.78 | Sri K.Satyanaryana Murthy | 10.04.10 | Completed
30 | - do - | G.Madugula | Kullupadu |  | 10.25 | 8.28 | Sri V.Mohan Rao | 29.05.11 | Completed
31 | - do - | Hukumpeta | Tadiput |  | 9 | 8.43 | Sri V.Mohan Rao | 10.05.11 | Completed
32 | - do - | Minimuluru | Kandamamidi |  | 9 | 8.35 | Sri V.Mohan Rao | 22.05.11 | Completed
33 | - do - | K.D.Peta | Nandimpalem | 13.09.2008, | 9 | 8.21 | Sri P.N.V.Ramana | 23.06.10 | Completed
34 | - do - | Lambasingi | Raju Pakalu |  | 9 | 8.31 | Sri Y.V.Mohan | 23.05.11 | Completed
35 | - do - | Rudakota | Kandrangivalasa |  | 9 | 0 | Sri P.Rambabu, | … | Transfer to Tribal Welfare Department
36 | - do - | Jerrila | Bailakinchangi | 13.09.2008 | 9 | 8.21 | Sri Y.V.Mohan | 18.05.11 | Completed
37 | - do - | Rudakota | Nimmala Paleru |  | 9 | 8.3 | Sri Y.V.Mohan | 16.05.11 | Completed
38 | - do - | Uppa | Pattam |  | 9 | 8.35 | Sri Y.V.Mohan | 26.03.11 | Completed
39 | - do - | Gannela | Lotheru-I (instead of Sunkarametta) |  | 9 | 8.37 | Sri P.Rambabu | 24.09.10 | Work Completed final bill to be paid
|  |  | TOTAL : |  | 164.5 | 141.62
EAST GODAVARI
40 | EG | Rajanagaram | Palacherla | 19-09-2009 | 9 | 8.3 | G. Appa Rao | 08.05.2010 | Final bill paid
41 | - do - | Rayavaram | Vedurupaka |  | 9 | 7.48 | D. Sriram | 27.6.2010 | Final bill paid
42 | - do - | Tallarevu | Injaram |  | 9 | 8.35 | R.S. Sanada Rao | 07.05.2010 | Final bill paid
43 | - do - | Amalapuram | Sakurru |  | 9 | 8.3 | K. Nageswara Rao | 27.5.2010 | Final bill paid
44 | - do - | Gangavaram | Pedagarlapudi |  | 9 | 8.18 | S. Srinivasa Rao | 17.6.2010 | Final bill paid
45 | - do - | Addateegala | Thimmapuram |  | 9 | 8.33 | N. Prasada Rao | 16.5.2010 | Final bill paid
46 | - do - | Addateegala | Gontavanipalem |  | 9 | 8.14 | G. Appa Rao | 04.06.2010 | Final bill paid
47 | - do - | Rajavommangi | Kindra |  | 9 | 8.35 | G. Ramana | 07.06.2010 | Final bill paid
48 | - do - | Rampachodavaram | Fokespeta |  | 9 | 8.24 | G. Appa Rao | 08.05.2010 | Final bill paid
49 | - do - | Devipatnam | Bhimpalli |  | 9 | 8.06 | G. Eswara Raju | 02.07.2010 | Final bill paid
50 | - do - | Rajavommangi | Ameenabada |  | 9 | 7.78 | G. Appa Rao | 09.05.2010 | Final bill paid
51 | - do - | Maredumilli | Maredumilli |  | 9 | 7.9 | S. Srinivasa Rao | 28.06.2010 | Final bill paid
52 | - do - | Prathipadu | U.Jagannadapuram |  | 9 | 8.26 | T.S.R. Swamy | 28.05.2010 | Final bill paid
53 | - do - | Anaparthy | Someswaram |  | 9 | 8.17 | M. Gangi Reddy | 20.05.2010 | Final bill paid
54 | - do - | Karapa | Nadakuduru | 19-09-2009 | 9 | 8.26 | R.V.Ch. Bapanna, | 05.10.2010 | Final bill paid
55 | - do - |  | Rajupalem |  | 9 |  |  |  | Not taken up, as there is a new building exists.
56 | - do - |  | Jaderu |  | 9 |  |  |  | Not taken up, as there is a new building exists.
|  |  | TOTAL : |  | 153 | 122.1
WEST GODAVARI
57 | WG | VR Gudem | Kommugudem | 19-09-2009 | 9 | 8.33 | N.Venkateswara Rao | 01.3.2010 | Completed & Handed over
58 | - do - | Devarapalli | Krishtampalem |  | 9 | 7.68 | S.Lakshmana Rao, | 15.08.2011 | Completed & Handed over
59 | - do - | Tadepalligudem | Marempalli |  | 9 | 7.82 | DV.Ramana, | 28.3.2011 | Completed & Handed over
60 | - do - | Penugonda | Ramannapalem |  | 9 | 8.3 | Raj Kumar | 14.3.2010 | Completed & Handed over
61 | - do - | Undi | Mahadevapatnam |  | 9 | 8.42 | Sri Sairam Ravindra, | 31.06.2011 | Completed & Handed over
62 | - do - | Bhimadollu | Pulla |  | 9 | 8.75 | M/s Srinidhi Constructions, | 28-03-11 | Completed & Handed over
63 | - do - | Bhimadollu | Kurellagudem |  | 9 | 8.8 | M/s Srinidhi Constructions | 28.03.2011 | Completed & Handed over
64 | - do - | Undrajavaram | Palangi |  | 9 | 8.3 | N.Venkateswara Rao, | 20.11-2011 | Completed & Handed over
65 | - do - | Veeravasaram | Rayakuduru |  | 9 | 8.3 | G.Venkatesewara Rao, | 15.03-2011 | Completed & Handed over
66 | - do - | Ganapavaram ( | Kasipadu |  | 9 | 3.95 | S.Ramakrishna | 15.08.2011 | Completed & Handed over
67 | - do - | Unguturu | Gollagudem |  | 9 | 8.17 | M/s.Shanmuka Consultency, | 15.05.2011 | Completed & Handed over
|  |  | TOTAL : |  | 99 | 86.82
KRISHNA
68 | KRI | Guduru | Lellagaruvu | 19-09-2009 | 9 | 8.36 | Sri N.Balakotaiah | 06-02-2011.
69 | - do - | Ghantasala | Kodali |  | 9 | 8.35 | Sri Vemuri Babji | 01-06-2010.
70 | - do - | Bantumilli | Chorampudi |  | 9 | 8.4 | Sri T.Srimannarayana | 05-02-2011.
71 | - do - | Thotlavalluru | Illuru |  | 9 | 8.27 | Sri S.V.Koteswara Rao | 23-04-2011.
72 | - do - | Pedana | Penumalli |  | 11.5 | 8.15 | Sri V.V.Nageswara Rao | 07-02-2011.
73 | - do - | Chevendrapalem | Chevendra |  | 11.5 | 10.46 | Sri N.Srinivasa Rao | 06-02-2011.
74 | - do - | Thotlavalluru | Inapuru |  | 9 | 10.43 | Sri S.V.Koteswara Rao | 31-08-2012.
75 | - do - | Kanchikacherla | Gottumukkala |  | 9 | 8.24 | Sri B.Bhaskara Rao | 25-10-2010.
76 | - do - | Nandigama | Navabpeta |  | 9 | 8.17 | Sri N.Srinivasa Rao | 25-10-2010.
77 | - do - | Mudinepalli | Dakaram |  | 9 | 8.33 | Sri N.Balakotaiah | 02-06-2011.
78 | - do - | Nagayalanka | Talagada Devi |  | 11.5 | 10.5 | Sri N.Balakotaiah | 31-08-2013.
|  |  | TOTAL : |  | 106.5 | 97.66
GUNTUR
79 | GNT | Bollapalli (M) | Remidicherla | 19-09-2009 | 9 | 8.41 | Sri K.Sankara Rao, | 27-10-2011 | Work completed & Handed over
80 | - do - | Amaravathi(M) | Lemalle |  | 9 | 8.41 | Sri V.Sambasiva Rao | 30-3-2011 | Work completed & Handed over
81 | - do - | Amarathaluru(M) | Yadavuru |  | 9 | 7.83 | Sri K.Gowri Sankar. | 26-4-2012 | Work completed & Handed over
82 | - do - | Amaravathi(M) | Malladi |  | 9 | 8.41 | Sri N.Venkata Appa Rao. | 31-3-2011 | Work completed & Handed over
83 | - do - | Mangalagiri(M) | Kaza-II |  | 9 | 8.37 | Sri A.Sambasiva Rao. | 2011-09-11 | Work completed & Handed over
84 | - do - | Nuzendla(M) | Chinthalacheruvu |  | 9 | 8.39 | Sri L.Govindru | 2011-08-04 | Work completed & Handed over
85 | - do - | Nadendla(M) | Sathuluru - II |  | 9 | 8.41 | Sri B.Srinivasa Rao | 28-10-11 | Work completed & Handed over
86 | - do - | Bollapalli (M) | Vellatur |  | 9 | 7.92 | Sri N.Bala Krishna Reddy | 30-4-2011 | Work completed & Handed over
87 | - do - | Macherla(M) | Nagulavaram |  | 9 | 8.39 | Sri S.Bhaskara Reddy, | 25-7-2012 | Work completed & Handed over
88 | - do - | Vemuru(M) | Peravali |  | 9 | 8.3 | Sri M.Rama Krishna. | 21-3-2011 | Work completed & Handed over
89 | - do - | Mangalagiri(M) | Kaja-I |  | 9 | 8.36 | Sri A.Sambasiva Rao. | 2011-09-11 | Work completed & Handed over
90 | - do - | Krosuru(M) | Balemarru |  | 9 | 7.26 | Sri K.Sankara Rao, | 2013-04-02 | Work completed & Handed over
91 | - do - | Atchempeta | Rudravaram |  | 9 | 7.4 | Sri K.Sankara Rao, | 17-11-12 | Work completed & Handed over
|  |  | TOTAL : |  | 117 | 105.86
PRAKASAM
92 | PKSM | N.G.Padu | Uppugundur | 19-09-2009 | 9 | 7.58 | Sri K.V.Subba Rao, | 31.7.2010
93 | - do - | Kothapatnam | Motumala |  | 9 | 8.31 | M/s SC Labour | 14.8.2010
94 | - do - | Inkollu | Pavuluru |  | 9 | 7.73 | Sri S.Ramamohan Rao, | 31.7.2010
95 | - do - | Korisapadu | Somavarappadu |  | 9 | 6.87 | Sri V.Sundaraiah | 31.7.2010
96 | - do - | Ongole | Karavadi |  | 9 | 7.29 | Sri Paleti Subba Rao | 31.7.2010
97 | - do - | Tangutur | Konijedu |  | 9 | 8.33 | Sri P.Malakondaiah, | 14.8.2010
98 | - do - | Hanumanthunipadu | Thurakapalli (Doddichinthala) |  | 9 | 8.41 | Sri S.Venugopal Reddy, | 4.8.2010
99 | - do - | Kurichedu | Potlapadu |  | 9 | 8.37 | Sri Ch.Srinivasulu, | 31.7.2010
100 | - do - | Talluru | East Gangavaram |  | 9 | 8.06 | Sri T.Tirupathaiah, | 31.7.2010
101 | - do - | Yerragondapalem | Ammanigudipadu | 19-09-2009 | 9 | 8.41 | Sri B.Venkateswara Reddy, | 9.9.2010
102 | - do - | Korisapadu | Thimmanapalem |  | 9 | 7.42 | Sri V.Sundaraiah, | 2.8.2010
103 | - do - | Addanki | Kotikalapudi |  | 9 | 7.42 | Sri Paleti Subba Rao, | 31.7.2010
104 | - do - | Korisapadu | Pamidipadu |  | 9 | 0.89 | Sri T.Chandra Sekhar Rao, | - | At basement level. Work cancelled. RE submitted for Rs.12.20 Lakhs RAS awaited
105 | - do - | Korisapadu | Ravinuthala | 19-09-2009 | 9 | 7.2 |  | 31.7.2010
106 | - do - | Addanki | Dharmavaram |  | 9 | 1.54 | Sri A.Venkata Rao, | - | Columns raised upto roof level . Work cancelled. RE submitted for Rs.12.00 Lakhs RAS awaited
107 | - do - | J.Pangulur | Muppavaram |  | 9 | 8.05 | Sri Tanneeru Ramanaiah, | 21.7.2010
108 | - do - | J.Pangulur | Ramkur |  | 9 | 7.41 | Sri T.Chandra Sekhar Rao | 7.8.2010
|  |  | TOTAL : |  | 153 | 119.29
NELLORE
109 | NLR | Udayagiri | Kurrapalli | 19-09-2009 | 9 | 7.5192 | MKJV P Reddy | 29.08.2012 | Work Completed
110 | - do - | Marripadu | Ponguru |  | 9 | 7.9292 | MKJV P Reddy | 17.03.2011 | Work Completed
111 | - do - | Anantha sagaram | Bommavaram |  | 9 | 8.1432 | AR Constructions | 11.05.2012 | Work Completed
112 | - do - | Kaluvai | Pedagopavaram |  | 9 | 8.4003 | YKM Reddy | 17.06.2010 | Work Completed
113 | - do - | Rapur | Jorepalli |  | 9 | 8.0889 | Y.K. Mohan Reddy | 17.06.2010 | Work Completed
114 | - do - | Daggavolu | Daggavolu |  | 9 | 8.4133 | Y.K. Mohan Reddy | 20.10.2010 | Work Completed
115 | - do - | Sullurpet | Illupuru |  | 9 | 8.3657 | Y.K. Mohan Reddy | 25.02.2011 | Work Completed
116 | - do - | V.giri | Paravolu |  | 9 | 7.6673 | Ch. Murali Krishna | 02.11.2011 | Work Completed
117 | - do - | Vakadu | Andalamala |  | 9 | 8.4112 | Y.K. Mohan Reddy, | 13.09.2010 | Work Completed
|  |  | TOTAL : |  | 81 | 72.9384
CHITTOOR
118 | CTR | Thamballapalli | Gopidinne | 19-09-2009 | 9 | 7.73 | Sri. C. Venkateswara Reddy | 15-11-10 | Work Completed
119 | - do - | Varadaipalem | Santhavellore |  | 9 | 9 | M/s. I. Muni Mohan Reddy | 30-09-10 | Work Completed
120 | - do - | G.D. Nellore | Mukkalathuru |  | 9 | 8.7 | M/s. Madanapalle | 25-04-10 | Work Completed
121 | - do - | Kalikiri | K.Reddyvaripalle |  | 9 | 8.02 | Sri. M. Chandra Sekhar Reddy | 21-07-10 | Work Completed
122 | - do - | Renigunta | Karakambadi | 19-09-2009 | 9 | 9 | Sri. P. Jaya Prakash Narayana | 30-11-10 | Work Completed
123 | - do - | Thottambedu | Poyya |  | 9 | 9 | Sri. M. Bharath Kumar | 30-11-10 | Work Completed
124 | - do - | Pulicherla | Mangalampeta |  | 9 | 8.74 | Sri. M. Bharath Kumar | 07-04-10 | Work Completed
125 | - do - | Yerravaripalem | Bodevandlapalle |  | 9 | 8.88 | Sri. K. Maheswara Reddy | 31-12-10 | Work Completed
126 | - do - | S.R. Puram | N.R.Puram |  | 9 | 8.64 | Sri. M. Bhupathi Reddy | 22-04-10 | Work Completed
127 | - do - | Nagari | Damarapakam |  | 9 | 8.6 | Sri. M. Bhupathi Reddy | 28-02-11 | Work Completed
|  |  | TOTAL : |  | 90 | 86.31
ANANTHAPUR
128 | ATP | Peddavaduguru | Chinthalacheruvu | 19-09-2009 | 9 | 8.35 | Sri.P.Raja Reddy. | 31-10-2010 | Work Completed
129 | - do - | Putlur | Kadavakallu |  | 9 | 5.86 | Sri.A.Narendranath Reddy. | 31-11-2011 | Work Completed
130 | - do - | Singanamala | E.Sodanapalli |  | 9 | 7.84 | Sri.P.Muthyalappa. | 31-7-2010 | Work Completed
131 | - do - | Chilamathur | Veerapuram |  | 9 | 7.51 | Sri.G.Narayana Swamy | 10-11-2013 | Work Completed
132 | - do - | P.Kottalapalli | Undebanda |  | 9 | 7.13 | Sri.V.Sudhakar. | 31-10-2010 | Work Completed
133 | - do - | Bommanahal | Govindawada |  | 9 | 7.34 | Sri.B.Sivaiah. | 8-6-2010 | Work Completed
134 | - do - | Bramhasamudram | Konapuram |  | 9 | 6.93 | Sri.B.Sivaiah. | 5-8-2010 | Work Completed
135 | - do - | Gudibanda | Phalaram |  | 9 | 6.92 | Sri.V.Venkatappa. |  | Work Completed
136 | - do - | Gandlapenta | Godduvelagala |  | 9 | 7.6 | Sri.B.Muthalappa. | 10-5-2010 | Work Completed
137 | - do - | Puttaparthy | Jagarajupalli |  | 9 | 8.09 | Sri.N.Chenna Kesava Reddy. | 17-11-2010 | Work Completed
138 | - do - | Somandepalli | Mandadi |  | 9 | 7.29 | Sri.E.Sudharshan Reddy. | 31-10-2012 | Work Completed
|  |  | TOTAL : |  | 99 | 80.86
KADAPA
139 | YSR | Kondasunkesula | Kondasunkesula | 19-09-2009 | 9 | 8.22 | Sri N. Gurappa, | 30.01.2012 | Work completed & FB paid
140 | - do - | Morrayapalli | Morrayapalli |  | 9 | 7.87 | M/S Durga Constructions, | 06.2012 | Work completed & FB paid
141 | - do - | Potladurthi | Potladurthi |  | 9 | 8.3 | Sri P. Narapu Reddy, | 15.05.2012 | Work completed & FB paid
142 | - do - | Bodithippannapadu | Bodithippannapadu |  | 9 | 8.41 | Sri N. Adinarayana Reddy, | 18.06.2012 | Work completed & FB paid
143 | - do - | Thallapalli | Thallapalli |  | 9 | 7.12 | Sri P.Rama Gangi Reddy, | 07.2012 | Work completed & FB paid
144 | - do - | Konduru | Konduru |  | 9 | 8.4 | Sri P.Rama Gangi Reddy, | 29.11.2012 | Work completed & FB paid
145 | - do - | Vandadi | Vandadi |  | 9 | 7.13 | Sri R. Srinivasulu, | 07/2012 | Work completed & FB paid
146 | - do - | Munnelli | Munnelli |  | 9 | 7.14 | A.Venkate- swarlu, | 06/2012 | Work completed & FB paid
147 | - do - | Palugaripalli | Palugaripalli |  | 9 | 8.33 | Sri A. Venka-teswarlu, | 01.11.2011 | Work completed & FB paid
148 | - do - | T.Kammapalli | T.Kammapalli |  | 9 | 7.39 | Sri M.V. Ramanjaneyulu, | 08/2012 | Work completed & FB paid
149 | - do - | Peddajonnavaram | Peddajonnavaram |  | 9 | 7.66 | Sri S. Chandra Sekhar, | 28.08.2012 | Work completed & FB paid
150 | - do - | Gurrappagaripalli | Gurrappagaripalli |  | 9 | 8.21 | Sri K. Lakshimi Sekhar Reddy, | 31.12.2012 | Work completed & FB paid
|  |  | TOTAL : |  | 108 | 94.18
KURNOOL
151 | KNL | Ahobilam | Bachipalli | 19-09-2009 | 9 | 8.41 | M.Suresh | 11.08.2010 | Completed & FB paid
152 | - do - | Sirivella | Grumpamandinne |  | 9 | 8.39 | J.V.Narayana Reddy | 24.07.2010 | Completed & FB paid
153 | - do - | Rudravaram | B.Nagireddy Palli |  | 9 | 8.41 | J.V.Narayana Reddy | 24.07.2010 | Completed & FB paid
154 | - do - | Pamulapadu | Thummalur |  | 9 | 8.08 | B.Haumantha Reddy | 28.06.2010 | Completed & FB paid
155 | - do - | Pamulapadu | Vanala |  | 9 | 8.41 | C.Nagarjuna Reddy | 27.12.2010 | Completed & FB paid
156 | - do - | Pamulapadu | Iskala |  | 9 | 8.4 | A.Syed Hussain | 30.06.2010 | Completed & FB paid
157 | - do - | Chagalamarri | Chinnavangali |  | 9 | 8.39 | M.Sanjeeva Rayudu | 31.07.2010 | Completed & FB paid
158 | - do - | Chagalamarri | Thodendla palli |  | 9 | 8.4 | M.Sanjeeva Rayudu | 17.07.2010 | Completed & FB paid
159 | - do - | Chagalamarri | Settiveedu |  | 9 | 8.38 | M.Sanjeeva Rayudu | 30.03.2011 | Completed & FB paid
160 | - do - | Perusomula | Giddalur |  | 9 | 8.41 | V.Balachandra Reddy | 05.06.2010 | Completed & FB paid |  | -3150
161 | - do - | Owk | Ramapuram |  | 9 | 8.41 | C.Venkata Rami Reddy | 29.06.2010 | Completed & FB paid
162 | - do - | Chapirevula | Pulimaddi |  | 9 | 8.48 | K.Pulla Reddy | 28.04.2010 | Completed & FB paid
163 | - do - | Bethamcherla | Guttapalli |  | 9 | 8.41 | M.Visvanath | 08.07.2010 | Completed & FB paid
164 | - do - | Daivamdinne | Yerrakota |  | 9 | 8.4 | K.Seetha Rami Reddy | 30.10.2010 | Completed & FB paid
|  |  | TOTAL : |  | 126 | 117.38
|  |  | Grand Total : |  | 1492.5 | 1303.3884
|  | Add establishment charges@ 7% |  |  |  | 91.2372
|  | TOTAL : |  |  |  | 1394.6255
1492.5

## STATUS (hidden)
WORK WISE ABSTRACT
STATUS OF ALL SC WORKS UNDER NRHM
Sl. No. | Name of the District | A/S amount (Rs. in lakhs) | No. of works | Status of works | [5 empty] | Expected month of completion |  |  | Expected month of completion
|  |  |  | Completed | Site problems | Work not takenup | Tender stage | Work to be started | Works progress | July-13 | Aug-13 | Sep-13 | Aug | Sep-13 | Oct-13 or after
SUB-CENTERS
1 | 271 SUB-CENTERS | 2439 | 271 | 258 |  | 8 |  |  | 5 | 2 | 1 | 2 | 3 | 2
2 | 366 SUB-CENTERS
| I. 348 SC | 3132 | 348 | 249 | 11 | 7 | 22 | 4 | 55 | 27 | 22 | 12 | 32 | 7 | 16
| II. 18 SC | 251 | 18 |  | 3 |  |  | 4 | 11 |  | 9 | 2 | 9 | 2
3 | 151 SUB-CENTERS
| I. 136 SC | 1224 | 136 | 71 | 15 | 1 | 10 | 5 | 34 |  |  |  | 21 | 4 | 9
| II. 15 SC | 210 | 15 |  | 1 |  |  | 1 | 13 |  |  |  | 6 | 7
| TOTAL | 7256 | 788 | 578 | 30 | 16 | 32 | 14 | 118 | 29 | 32 | 16 | 71 | 22 | 25

## ABS 271 Sub. (hidden)
STATUS OF 271 SUB-CENTERS UNDER NRHM 21-05-2011
Sl. No. | Name of the District | Administrative sanction amount (Rs. in lakhs) | No. of works | Stage of Work | [6 empty] | Work not takenup | Expindeture (Rs. In lakhs) | Remarks
|  |  |  | Tender process / Tender stage | Site problem if any | Below basement level | Basement level | Roof level | Slab laid | Completed
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Srikakulam | 117 | 13 | 0 | 0 | 1 | 0 | 1 | 8 | 3 | 0 | #REF! |  | 13 | 13 | 0
2 | Vizianagaram | 72 | 8 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | #REF! |  | 8 | 8 | 0
3 | Vishakhapatnam | 162 | 18 | 0 | 0 | 1 | 1 | 0 | 6 | 10 | 0 | #REF! |  | 18 | 18 | 0
4 | East Godavari | 153 | 17 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | 2 | #REF! |  | #REF! | 17 | 0
5 | West Godavari | 99 | 11 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 0 | #REF! |  | 11 | 11 | 0
6 | Krishna | 99 | 11 | 0 | 0 | 1 | 0 | 0 | 0 | 10 | 0 | #REF! |  | 11 | 11 | 0
7 | Guntur | 117 | 13 | 0 | 0 | 1 | 0 | 1 | 3 | 8 | 0 | #REF! |  | 13 | 13 | 0
8 | Prakasam | 153 | 17 | 0 | 0 | 0 | 1 | 1 | 5 | 10 | 0 | #REF! |  | 17 | 17 | 0
9 | Nellore | 81 | 9 | 0 | 0 | 0 | 0 | 2 | 1 | 6 | 0 | #REF! |  | 9 | 9 | 0
10 | Chittoor | 90 | 10 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 0 | #REF! |  | 10 | 10 | 0
11 | Kadapa | 108 | 12 | 0 |  | 0 |  | 2 | 2 | 8 | 0 | #REF! |  | 12 | 12 | 0
12 | Ananthapur | 99 | 11 | 0 | 0 | 0 | 0 | 0 | 2 | 9 | 0 | #REF! |  | 11 | 11 | 0
13 | Kurnool | 126 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | #REF! |  | 14 | 14 | 0
14 | Mahaboobnagar | 108 | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 0 | #REF! |  | 12 | 12 | 0
15 | Ranga Reddy | 90 | 10 | 0 | 2 | 0 | 0 | 0 | 1 | 7 | 0 | #REF! |  | 10 | 10 | 0
16 | Medak | 90 | 10 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 0 | 36.86 |  | 10 | 10 | 0
17 | Nizamabad | 117 | 13 | 0 | 0 | 0 | 0 | 0 | 2 | 11 | 0 | #REF! |  | 13 | 13 | 0
18 | Adilabad | 99 | 11 | 0 | 1 | 1 | 0 | 1 | 1 | 7 | 0 | #REF! |  | 11 | 11 | 0
19 | Karimnagar | 126 | 14 | 0 | 2 | 0 | 1 | 1 | 7 | 3 | 0 | #REF! |  | 14 | 14 | 0
20 | Warangal | 135 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | #REF! |  | 15 | 15 | 0
21 | Khammam | 117 | 13 |  | 1 | 1 | 0 | 0 | 0 | 9 | 2 | #REF! |  | 13 | 13 | 0
22 | Nalgonda | 81 | 9 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 0 | 43.84 |  | 9 | 9 | 0
| TOTAL | 2439 | 271 | 0 | 6 | 6 | 3 | 9 | 57 | 186 | 4 | #REF! |  | 271 | 271 | 0
[9 empty] | Add Supervision charges |  |  | #REF!
[9 empty] | Grand Total Expenditure |  |  | #REF!

## 29411 (hidden)
ABSTRACT Construction of CEMONC Centres, Birth Waiting Homes
S.No | Year | Total sanctioned (No.) | Started (No.) | Completed (No.) | Handed over (No.) | To be completed | Works not taken up | Financial out lay (Rs. In lakhs) | Amount Released (Rs. In lakhs) | Expenditure (Rs. In lakhs) | Balance Amount (Rs. In lakhs) | Remarks | Remarks | Page No.
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 13 | 13
A) | CEMONC CENTERS
| 2007-08 | 151 | 121 | 119 | 119 | 2 | 30 | 6535.8 | 6535.8 | 6489.6891 | 0 |  | Out of (2) CEMONC Centres to be completed, 1 No. at Giddaluru in Prakasam Dist. needs Revised Administrative Approval and site is not available for the other at Kamareddy in Nizamabad Dist. | 1 - 13
B) | BIRTH WAITING HOMES
| 2006-07 | 38 | 37 | 37 | 37 | 0 | 1 | 384.8 | 384.8 | 377.6137 | 0 |  | GH,Chintoor in Khammam Dist. was differed. | 14 - 18
C) | OTHER WORKS:
|  | 2 | 2 | 1 | 1 | 1 |  | 602.5 | 548.5 | #REF! | 54 |  |  | 19
(sub center funds utilized for Nilofor Hospital)
D) | SUBCENTERS
| 2009-10 (NRHM) | 271 | 260 | 169 | 169 | 91 | 11 | 2439 | 2080 | #REF! | 359 |  |  | 20 - 43
E) | INCOMPLETE PHCs
|  | 5 | 5 | 5 | 5 | 0 | 0 | 45.63 | 45.63 | 45.63 | 0 |  |  | 44
CENTRES OF EXCELLENCE FOR MATERNAL AND CHILDREN'S HEALTH
F) | 2010-11 | 5 | 5 |  |  | 5 |  | #REF! | 600 | #REF! | #REF! |  |  | 45
| TOTAL | [6 empty] | #REF! | 10194.73 | #REF! | #REF!

## NRHM Action plan (2) (hidden)
NRHM ACTION PLAN 2010-11
Sl. No. | Name of the work | No. | Number of Beds | Unit Cost in (Rs. In lakhs) | Date of handing over to user department | Total Cost (Rs. In lakhs) | REMARKS
1 | Sub-Centers | 500 |  | 9 |  | 4500 | List to be received
2 | Primary Health Centers | 50 |  |  |  | 3000 | List to be received based on proposed new plan at an estimate amount of Rs.40.00 lakhs per each PHC
3 | Construction of Maternal and Childred centers at MGM Hospital, Warangal |  | 50 |  |  | 500 | Administrative sanction to be received.
4 | Construction of Maternal and Childred centers at SVRR Hospital, Tirupathi |  | 300 |  |  | 1000 | Amount sanctioned for procurment of equipment
5 | Construction of Maternal and Childred centers at Nilofer Hospital, Hyderabad |  | 300 |  |  | 1000 | Work is in progress
6 | Construction of Maternal and Childred centers at Petlaburz Hospital, Hyderabad |  | 100 |  |  | 1000 | Tenders to be placed beforeTender Committee
7 | Construction of Maternal and Childred centers at District Hospital, Nellore |  | 100 |  |  | 500 | Administrative sanction to be received.
| TOTAL:: |  |  |  |  | 11500
Note on B3: Procdg.No.426/RCH-II/2008, dt.29.07 08

## Sheet1 (hidden)
Construction of (271) Sub-Centres under NRHM
Sl. No. | Name of the Sub-Cenre | Administrative sanction amount (Rs. in lakhs) | Stage of Work | [8 empty] | Name of Scheme / Work | Ref. to Administrative Approval | Amount of Administrative Approval (Rs.in lakhs) | Ref. to Technical Sanction | Amount of Technical Sanction | Agreed Date of Completion | Probable Date of Completion | Physical Progress | Physical Progress | Expenditure to the end of Previous Year | Budget Allocation during Year (Rs.in lakhs) | Expenditure (Rs.in lakhs) |  |  | Cumulative Expenditure (Rs.in lakhs) | Remarks
|  |  | Tender process / Tender stage | Site problem if any | Below basement level | Basement level | Roof level | Slab laid | Completed | Expindeture (Rs. In lakhs) | Remarks | [8 empty] | Cumulative |  |  | To end of Previous Month | During Month | Total
1 | [11 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 6 | 7
SRIKAKULAM
1 | Metturu | 9 | - | - | - | - | - | - | Yes | 6.74 | Work completed and handed over | Metturu | ..do.. | 9 |  | 9 |  |  | Work ompleted and handed over on 13.3.2011. | Work completed and handed over | 6.74 | … | … | … | … | 7.77 |  | 1
2 | Dabbapadu / Ravichandri | 9 | - | - | - | - | - | Yes | - | 3.33 | Plastering is in progress | Dabbapadu / Ravichandri | ..do.. | 9 |  | 9 |  |  | Work completed. |  | 3.33 | … | … | … | … | 6.34 |  | 2
3 | Mandasa | 9 | - | - | - | - | - | - | Yes | 8.3 | Work completed. Final bill paid. | Mandasa | ..do.. | 9 |  | 9 |  |  | Work ompleted and handed over on 7.6.2010 |  | 8.3 | … | … | … | … | 8.3 |  | 3
4 | Koduru | 9 | - | - | - | - | - | Yes | - | 4.94 | Finishing are in progress | Koduru | ..do.. | 9 |  | 9 |  |  | Work completed. |  | 4.94 | … | … | … | … | 4.94 |  | 4
5 | Govindapuram | 9 | - | - | - | - | - | Yes | - | 6.6 | Nearing completion. Power supply connection to be given | Govindapuram | ..do.. | 9 |  | 9 |  |  | Work completed and handed over on 28.10.11 |  | 6.6 | … | … | … | … | 8.37 |  | 5
6 | Bhagiradhapuram | 9 | - | - | - | - | - | Yes | - | 6.46 | Nearing completion. Power supply connection to be given | Bhagiradhapuram | ..do.. | 9 |  | 9 |  |  | Work completed and handed over on 17.11.2011 |  | 6.46 | … | … | … | … | 6.46 |  | 6
7 | Dharmavaram | 9 | - | - | - | - | - | Yes | - | 4.6 | Painting is in progress. | Dharmavaram | ..do.. | 9 |  | 9 |  |  | Work completed and handed over on 8.11.2011 |  | 4.6 | … | … | … | … | 7 |  | 7
8 | Penubarthi | 9 | - | - | - | - |  | Yes | - | 3.61 | Nearing completion. Power supply connection to be given | Penubarthi | ..do.. | 9 |  | 9 |  |  | Work completed and handed over on 24.12.2011 |  | 3.61 | … | … | … | … | 6.29 |  | 8
9 | P.V.Palem | 9 | - | - | - | - | - | - | Yes | 6.33 | Work completed. Final bill to be paid. | P.V.Palem | ..do.. | 9 |  | 9 |  |  | Work completed and handed over on 21.1.11 | Work completed. Final bill to be paid. | 6.33 | … | … | … | … | 7.56 |  | 9
| TOTAL : | 81 | [7 empty] | 50.91 |  | 2: TOTAL :; 4: 81; 6: 81; Cumulative 7: 50.91; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 63.03 | 10
VIZIANAGARAM | [27 empty] | 11
10 | Pedanadipalli | 9 | - | - | - | - |  | - | Yes | 8.3 | Work completed. Final bill paid. | Pedanadipalli | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 | 28/09-10 | 9 | 31.05.10 | 31.01.11 | Work completed and handed over on 07.03.2011. | Work completed. | 3.87 |  | 4.43 | 0 | 4.43 | 8.3 |  | 12
11 | Bondapalli | 9 | - | - | - | - | - | Yes | - | 3.91 | Doors & windows fixed. | Bondapalli | ..do.. | 9 | 30/09-10 | 9 | 24.05.10 | 31.08.11 | Work completed and handedover on.21.11.11 |  | 3.91 |  | 0 | 0 | 0 | 8.38
12 | Pedabantupalli | 9 | - | - | - | - | - | Yes | - | 3.84 | Doors & windows procured. | Pedabantupalli | ..do.. | 9 | 31/09-10 | 9 | 31.05.10 | 31.08.11 | Work completed and handedover on 19.10.11 |  | 3.84 |  | 0 | 0 | 0 | 8.34 |  | 13
| TOTAL : | 27 | [7 empty] | 16.05 |  | 2: TOTAL :; 4: 27; 6: 27; Cumulative 7: 11.62; Cumulative 8: 0; To end of Previous Month 9: 4.43; During Month 10: 0; Total 11: 4.43; Total 6: 25.02 | 17
VISHAKHAPATNAM | [27 empty] | 18
13 | Pudimadaka | 9 | - | - | - | - | - | - | Yes | 8.12 | Work completed and handed over | Pudimadaka | Rc.No.315/FW/P2/2008, dt,13.09.2008, 24.03.2009 of CFW. | 9 | 44/EE-VSP/10.11.09 | 9 | 10.04.10 |  | Work completed and handed over on 30.07.10 | Completed and handed over on 30.07.10 | 8.126 | … | … | … | 0 | 8.126 |  | 19
14 | Thotata | 9 |  | - | - | - | - | - | Yes | 4.61 | Work completed | Thotata | ..do.. | 9 | 49/EE-VSP/10.11.09 | 9 | 18.04.10 | 30.04.11 | Work completed amd handed over on 19.11.2011 | work completed and ready for handing over and external power connection is to be given. | 4.613 | … | … | … | 0 | 7.121 |  | 20
15 | Batajangala Palem | 9 | - | - | - | - | - | - | Yes | 6.54 | work completed. Electrical connections are in progress. | Batajangala Palem | ..do.. | 9 | 47/EE-VSP/10.11.09 | 9 | 18.04.10 | 30.04.11 | Work completed & Handed over on 19.11.2011 |  | 6.546 | … | … | 0.18 | 0.18 | 8.116 |  | 21
16 | Koligotla-II | 9 | - |  | - | - | - | - | Yes | 5.97 | Work completed. | Koligotla-II | ..do.. | 9 | 43/EE-VSP/10.11.09 | 9 | 18.04.10 | 30.04.11 | Work completed & Handed over on 28.11.2011 |  | 5.97 | … | … | … | 0 | 8.124 |  | 22
17 | Dibbidi | 9 | - | - | - | - | - | - | Yes | 6.22 | Work completed | Dibbidi | ..do.. | 9 | 42/EE-VSP/10.11.09 | 9 | 18.04.10 | 30.04.11 | Work completed & Handed over on 20.10.2011 |  | 6.227 | .. | .. | … | 0 | 8.202 |  | 23
18 | Vadarevupalli (Vadrapalli) | 9 | - | - | - | - | - | - | Yes | 8.16 | Completed | Vadarevupalli (Vadrapalli) | ..do.. | 9 | 48/EE-VSP/10.11.09 | 9 | 21.04.10 |  | Work completed & Handed over 08.09.10 | Completed and handedover on 08.07.10 | 8.16 | … | … | … | 0 | 8.16 |  | 24
19 | Arubupalem | 9 | - | - | - | - | - | - | Yes | 6.04 | Work completed. Fixing of electrical fixtures is in progress. | Arubupalem | ..do.. | 9 | 46/EE-VSP/10.11.09 | 9 | 10.04.10 | 31.05.11 | Work completed & Ready for handing over | Work completed and ready for handingover. | 6.044 | … | … | .. | 0 | 7.694 |  | 25
20 | Kullupadu | 9 | - | - | - | - | - | Yes | - | 4.97 | Laying of tiles work is in progress. | Kullupadu | ..do.. | 9 | 61/EE-VSP/30.12.09 | 9 | 22.07.10 | 30.04.11 | Work completed & Handed over on 21.10.2011 |  | 4.979 | … | … | … | 0 | 8.18 |  | 26
21 | Tadiput | 9 | - | - | - | - | - | - | Yes | 6.47 | Work completed. Fixing of electrical fixtures is in progress. | Tadiput | ..do.. | 9 | 59/EE-VSP/30.12.09 | 9 | 22.07.10 | 30.04.11 | Work completed and handedover on 14.09.2011. |  | 5.849 | … | 0.623 | … | 0.623 | 8.331 |  | 27
22 | Kandamamidi | 9 | - | - | - | - | - | - | Yes | 6.12 | Work completed. Fixing of electrical fixtures is in progress. | Kandamamidi | ..do.. | 9 | 57/EE-VSP/30.12.09 | 9 | 03.07.10 | 30.04.11 | Work completed and handedover on 14.11.2011. |  | 6.121 | … | … | … | 0 | 8.242 |  | 28
23 | Nandimpalem | 9 | - | - | - | - | - | - | Yes | 8.1 | Work completed and handed over on 19.01.11. | Nandimpalem | ..do.. | 9 | 66a)/EE-VSP/22.01.10 | 9 | 23.06.10 |  | Work completed & Handed over on 19.01.2011 | Work Completed and handed over on 19.01.11 | 8.109 | … | … | … | 0 | 8.109 |  | 29
24 | Raju Pakalu | 9 | - | - | - | - |  | Yes | - | 4.275 | Painting work is in progress. | Raju Pakalu | ..do.. | 9 | 59/EE-VSP/30.12.09 | 9 | 02.07.10 | 31.05.11 | Completed & Handed over on 29.10.2011 |  | 4.275 | … | … | … | 0 | 8.215 |  | 30
25 | Bailakinchangi | 9 | - | - | - | - |  | Yes | - | 5.07 | Plasterings completed and water supply lines work is in progress. | Bailakinchangi | ..do.. | 9 | 65/EE-VSP/22.01.10 | 9 | 22.04.10 | 31.05.11 | Work completed & Handing over on 01.12.11 |  | 5.07 | … | … | … | 0 | 8.122 |  | 31
26 | Nimmala Paleru | 9 | - | - |  | - | - | Yes | - | 4.41 | Plasterings completed and water supply lines work is in progress. | Nimmala Paleru | ..do.. | 9 | 66/EE-VSP/22.01.10 | 9 | 22.07.10 | 31.05.11 | Work completed and handedover on |  | 4.413 | … | … | … | 0 | 8.204 |  | 32
27 | Pattam | 9 | - | - | - | - | - | Yes | - | 6.57 | Work completed and to be handed over. | Pattam | ..do.. | 9 | 64a)/EE-VSP/22.01.10 | 9 | 22.07.10 | 30.04.11 | Work completed & Handed over on 12.09.2011 |  | 6.571 | … | … | … | 0 | 8.252 |  | 33
| TOTAL : | 135 | [7 empty] | 91.645 |  | TOTAL : |  | 135 |  | 135 |  |  |  | 0 | 91.073 | 0 | 0.623 | 0.18 | 0.803 | 121.198
EAST GODAVARI | [27 empty] | 34
28 | Palacherla | 9 | - | - | - | - | - | - | Yes | 8.17 | Completed | Palacherla | Rc. No: 315/FW/P2/2008; Dated: 19-09-2009 of CFW. | 9 | 53/2009-10; Dt.09.11.2009. | 9 | 08.03.2010 | 08.06.2010 | Work completed. Final bill paid | Work completed. | 4.64 | 19.01 | 3.53 | … | 3.53 | 8.17 |  | 34
29 | Vedurupaka | 9 | - | - | - | - | - | Yes | - | 4.45 | Flooring sanitary and electrical works are in progress | Vedurupaka | ..do.. | 9 | 45/2009-10; Dt.09.11.2009. | 9 | 28.04.2010 | 31.07.2011 | Work completed. Balance funds required | Painting work is in progress. | 4.45 |  | … | … | … | 4.45 |  | 35
30 | Injaram | 9 | - | - | - | - | - | - | Yes | 4.74 | Completed | Injaram | ..do.. | 9 | 28/2011-12; Dt. 01.07.2011 | 9 | 08.03.2010 | 08.03.2010 | Work completed. Final bill paid | Tenders called for and to be opened on 12.07.2011. | 4.74 |  | … | … | … | 8.17 |  | 36
31 | Sakurru | 9 | - | - | - | - | - | - | Yes | 6.03 | Completed | Sakurru | ..do.. | 9 | 47/2009-10; Dt.09.11.2009. | 9 | 28.03.2010 | 31.05.2010 | Work completed. Balance funds required | Work completed. | 3.74 |  | 2.29 | … | 2.29 | 6.03 |  | 37
32 | Pedagarlapudi | 9 | - | - | - | - | - | Yes | - | 5.58 | Electrical works are in progress | Pedagarlapudi | ..do.. | 9 | 29/2011-12; Dt. 01.07.2011 | 9 | 18.04.2010 | 18.04.2010 | Work completed. Final bill paid | Tenders called for and to be opened on 12.07.2011. | 5.58 |  | … | … | … | 8.18 |  | 38
33 | Thimmapuram | 9 | - | - | - | - | - | - | Yes | 8.33 | Work completed | Thimmapuram | ..do.. | 9 | 54/2009-10; Dt.09.11.2009. | 9 | 16.03.2010 | 15.06.2010 | Work completed. Final bill paid | Work completed. | 5.5 |  | 2.83 | … | 2.83 | 8.33 |  | 39
34 | Gontavanipalem | 9 | - | - | - | - | - | - | Yes | 1.92 | Work completed | Gontavanipalem | ..do.. | 9 | 58/2009-10; Dt.09.11.2009. | 9 | 04.04.2010 | 04.07.2010 | Work completed.Final bill paid | Work completed. | 1.92 |  | … | … | … | 8.14 |  | 41
35 | Kindra | 9 | - | - | - | - | - | - | Yes | 8.35 | Work completed | Kindra | ..do.. | 9 | 55/2009-10; Dt.09.11.2009. | 9 | 07.04.2010 | 18.06.2010 | Work completed. Final bill paid | Work completed and handed over. | 8.35 |  | … | … | … | 8.35 |  | 42
36 | Fokespeta | 9 | - | - | - | - | - | - | Yes | 2.47 | Work completed | Fokespeta | ..do.. | 9 | 56/2009-10; Dt.09.11.2009. | 9 | 08.03.2010 | 08.06.2010 | Work completed. Final bill paid | Work completed. | 2.47 |  | … | … | … | 8.24 |  | 43
37 | Bhimpalli | 9 | - | - | - | - | - | Yes | - | 4.03 | Flooring, sanitary and electrical works are in progress. | Bhimpalli | ..do.. | 9 | 51/2009-10; Dt.09.11.2009. | 9 | 2.5.2010 | 31.07.2011 | Work completed. Balance funds required | Flooring, sanitary and electrical works are in progress. | 4.03 |  | … | … | … | 4.03 |  | 44
38 | Ameenabada | 9 | - | - | - | - | - | Yes | - | 2.38 | Flooring is in progress | Ameenabada | ..do.. | 9 | 57/2009-10; Dt.09.11.2009. | 9 | 09.03.2010 | 31.07.2011 | Work completed. Balance funds required | Flooring is in progress. | 2.38 |  | … | … | … | 2.38 |  | 45
39 | Maredumilli | 9 | - | - | - | - | - | Yes | - | 4.74 | Flooring sanitary and electrical works are in progress | Maredumilli | ..do.. | 9 | 50/2009-10; Dt.09.11.2009. | 9 | 28.04.2010 | 31.07.2011 | Work completed. Balance funds required | Flooring, sanitary and electrical works are in progress. | 4.26 |  | … | … | … | 4.26 |  | 46
40 | U.Jagannadapuram | 9 | - | - | - | - | - | - | Yes | 8.26 | Work completed | U.Jagannadapuram | ..do.. | 9 | 49/2009-10; Dt.09.11.2009. | 9 | 28.03.2010 | 28.03.2010 | Work completed. Final bill paid | Work completed and handed over. | 5.18 |  | 3.08 |  | 3.08 | 8.26 |  | 47
41 | Someswaram | 9 | - | - | - | - | - | - | Yes | 4.89 | Flooring, sanitary and electrical works are in progress. | Someswaram | ..do.. | 9 | 46/2009-10; Dt.09.11.2009. | 9 | 20.03.2010 | 31.07.2011 | Work completed. Balance funds required | Work completed. | 4.89 |  | … | … | … | 4.89 |  | 48
42 | Nadakuduru | 9 | - | - | - | - | - | - | Yes | 7.28 | Work completed | Nadakuduru | ..do.. | 9 | 6/2010-11; Dt.13.4.2010. | 9 | 5.8.2010 | 05.08.2010 | Work completed.Final bill paid | Work completed. | 7.28 |  | … | 0.48 | 0.48 | 8.26 |  | 49
| TOTAL : | 135 | [7 empty] | 81.62 |  | 2: TOTAL :; 4: 135; 6: 135; Cumulative 7: 69.41; Cumulative 8: 19.01; To end of Previous Month 9: 11.73; During Month 10: 0.48; Total 11: 12.21; Total 6: 100.14
WEST GODAVARI
43 | Kommugudem | 9 | - | - | - | - | - | - | Yes | 8.26 | Work completed | Kommugudem | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 |  | 9 | 01.3.2010 | 01.3.2010 | Work completed. Final bill paid. | Work completed. Final bill paid. | 9 |  |  |  | 0 | 9 |  | 50
44 | Krishtampalem | 9 | - | - | - | - | - | Yes | - | 4.08 | Finishings are in progress | Krishtampalem | ..do.. | 9 |  | 9 | 09.3.2010 | 15.08.2011 | Work completed. |  | 4.08 |  |  |  | 0 | 4.08 |  | 51
45 | Marempalli | 9 | - | - | - | - | - | - | Yes | 5.9 | Work completed. | Marempalli | ..do.. | 9 |  | 9 | 28.3.2010 | 28.3.2011 | Work completed. |  | 5.9 |  |  |  | 0 | 5.9 |  | 52
46 | Ramannapalem | 9 | - | - | - | - | - | - | Yes | 9 | Work completed. | Ramannapalem | ..do.. | 9 |  | 9 | 14.3.2010 | 14.3.2010 | Work completed. Final bill paid. | Work completed. Final bill paid. | 9 |  |  |  | 0 | 9 |  | 53
47 | Mahadevapatnam | 9 | - | - | - | - | - | Yes | - | 7.5 | Finishings are in progress | Mahadevapatnam | ..do.. | 9 |  | 9 | 19.4.2010 | 31.06.2011 | Work completed. Final bill to be paid. |  | 7.5 |  |  |  | 0 | 7.5 |  | 54
48 | Pulla | 9 | - | - | - | - | - | - | Yes | 8.75 | Work completed. | Pulla | ..do.. | 9 |  | 9 | 28.3.2010 | 28-03-11 | Work completed. Final bill paid. | Work completed. Final bill paid. | 8.75 |  |  |  | 0 | 8.75 |  | 55
49 | Kurellagudem | 9 | - | - | - | - | - | - | Yes | 8.8 | Work completed | Kurellagudem | ..do.. | 9 |  | 9 | 2.5.2010 | 28.03.2011 | Work completed. Final bill paid. | Work completed. Final bill paid. | 8.8 |  |  |  | 0 | 8.8 |  | 56
50 | Palangi | 9 | - | - | - | - | - | - | Yes | 9 | Work completed and handed over. | Palangi | ..do.. | 9 |  | 9 | 10.6.2010 | 20.11-2011 | Work completed. Final bill paid. | Work completed. Final bill paid. | 9 |  |  |  | 0 | 9 |  | 57
51 | Rayakuduru | 9 | - | - | - | - | - | - | Yes | 8.8 | Work completed | Rayakuduru | ..do.. | 9 |  | 9 | 5.8.2010 | 15.03-2011 | Work completed. Final bill paid. | Work completed. Final bill paid. | 8.8 |  |  |  | 0 | 8.8 |  | 58
52 | Gollagudem | 9 | - | - | - | - | - | - | Yes | 4.59 | Work completed | Gollagudem | ..do.. | 9 |  | 9 | 4.8.201 | 15.05.2011 | Work completed. Final bill to be paid. |  | 5.6 |  |  |  | 0 | 5.6 |  | 59
| TOTAL : | 90 | [7 empty] | 74.68 |  | 2: TOTAL :; 4: 90; 6: 90; Cumulative 7: 76.43; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 76.43
KRISHNA
53 | Lellagaruvu | 9 | - | - | - | - | - | - | Yes | 8.28 | Work completed | 2: Lellagaruvu; 3: Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 6: Work completed and handed over.; Cumulative 7: 8.28; Total 6: 8.28 | 60
54 | Kodali | 9 | - | - | - | - | - | - | Yes | 8.21 | Work completed | 2: Kodali; 3: ..do..; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 6: Work completed and handed over.; Cumulative 7: 8.21; Total 6: 8.21 | 61
55 | Cherampudi | 9 | - | - | - | - | - | - | Yes | 6.41 | Work completed | 2: Chorampudi; 3: ..do..; 4: 9; 6: 9; 5: Work completed; Cumulative 6: Work completed; Cumulative 7: 8.29; Total 6: 8.29 | 62
56 | Illuru | 9 | - | - | - | - | - | - | Yes | 6.36 | Work completed | 2: Illuru; 3: ..do..; 4: 9; 6: 9; 5: Work completed; Cumulative 6: Work completed; Cumulative 7: 8.26; Total 6: 8.26 | 63
57 | Penumalli | 9 | - | - | - | - | - |  | Yes | 6.36 | Work completed | 2: Penumalli; 3: ..do..; 4: 9; 6: 9; 5: Work completed and inaugurated on 07.02.2011.; Cumulative 6: Work completed; Cumulative 7: 7.98; Total 6: 7.98 | 64
58 | Chevendra | 9 | - | - | - | - | - | - | Yes | 7.63 | Work completed | 2: Chevendra; 3: ..do..; 4: 9; 6: 9; 5: Work completed and inaugurated on 08.02.2011.; Cumulative 6: Work completed; Cumulative 7: 10.38; Total 6: 10.38 | 65
59 | Inapuru | 9 | - | - | - | - | - | - | Yes | 7.96 | Work completed | 2: Inapuru; 3: ..do..; 4: 9; 6: 9; 5: Work completed; Cumulative 6: Work completed; Cumulative 7: 10.33; Total 6: 10.33 | 66
60 | Gottumukkala | 9 | - | - | - | - | - | - | Yes | 8.11 | Work completed and handed over | 2: Gottumukkala; 3: ..do..; 4: 9; 6: 9; 5: Work completed and handed over; Cumulative 6: Work completed and handed over; Cumulative 7: 8.24; Total 6: 8.24 | 67
61 | Navabpeta | 9 | - | - | - | - |  | - | Yes | 8.12 | Work completed | 2: Navabpeta; 3: ..do..; 4: 9; 6: 9; 5: Work completed and handed over; Cumulative 6: Work completed and handed over; Cumulative 7: 8.21; Total 6: 8.21 | 68
62 | Dakaram | 9 | - | - | - |  | - | - | Yes | 5.15 | Work completed | 2: Dakaram; 3: ..do..; 4: 9; 6: 9; 5: Work completed; Cumulative 6: Work completed; Cumulative 7: 8.19; Total 6: 8.19 | 69
| TOTAL : | 72 | [7 empty] | 56.1 |  | 2: TOTAL :; 4: 90; 6: 90; Cumulative 7: 86.37; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 86.37; Total 6: 86.37
GUNTUR
63 | Remidicherla | 9 | - | - | - | - | - | Yes | - | 3.9 | Nearing completion | 2: Remidicherla; 3: Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW; 4: 9; 6: 9; 5: Work completed to be handed over.; Cumulative 7: 4.67; Total 6: 4.67 | 70
64 | Lemalle | 9 | - | - | - | - | - | - | Yes | 4.35 | Work completed | 2: Lemalle; 3: ..do..; 4: 9; 6: 9; 5: Work completed; Cumulative 6: Work completed; Cumulative 7: 8.41; Total 6: 8.36 | 71
65 | Yadavuru | 9 | - | - | - | - | - | Yes | - | 4.25 | Roof slab laid final notice issued ot the contractor | 2: Yadavuru; 3: ..do..; 4: 9; 6: 9; 5: Work completed. Final bill to be paid.; Cumulative 7: 4.25; Total 6: 4.25 | 72
66 | Malladi | 9 | - | - | - | - | - | - | Yes | 5.14 | Work completed | 2: Malladi; 3: ..do..; 4: 9; 6: 9; 5: Work completed; Cumulative 6: Work completed; Cumulative 7: 8.41; Total 6: 8.41 | 73
67 | Kaza-II | 9 | - | - | - | - | - | Yes | - | 5.54 | Nearing completion | 2: Kaza-II; 3: ..do..; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 7: 8.33; Total 6: 8.33 | 74
68 | Chinthalacheruvu | 9 | - | - | - | - | - | - | Yes | 2.56 | Work completed | 2: Chinthalacheruvu; 3: ..do..; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 6: Work completed; Cumulative 7: 8.4; Total 6: 8.4 | 75
69 | Sathuluru - II | 9 | - | - | - | - | - | Yes | - | 5.7 | Nearing completion | 2: Sathuluru - II; 3: ..do..; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 7: 5.7; Total 6: 5.7 | 76
70 | Vellatur | 9 | - | - | - | - | - | Yes | - | 3.18 | Nearing completion | 2: Vellatur; 3: ..do..; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 7: 4.53; Total 6: 4.53 | 77
71 | Nagulavaram | 9 | - | - | - | - | - | Yes | - | 3.76 | Brick masonry in superstructure completed. Plastering work is in progress. | 2: Nagulavaram; 3: ..do..; 4: 9; 6: 9; 5: Work completed and to be handed over.; Cumulative 7: 6.82; Total 6: 6.82 | 78
72 | Peravali | 9 | - | - | - | - | - | - | Yes | 5.32 | Work completed | 2: Peravali; 3: ..do..; 4: 9; 6: 9; 5: Work completed and handed over on 10.03.2011.; Cumulative 6: Work completed.; Cumulative 7: 8.35; Total 6: 8.35 | 79
73 | Kaja-I | 9 | - | - | - | - | Yes | - | - | 0.08 | Columns raised upto roof level. | 2: Kaja-I; 3: ..do..; 4: 9; 6: 9; 5: Work completed and handed over. Final bill to be paid.; Cumulative 7: 4.51; Total 6: 4.51 | 80
| TOTAL : | 27 | [7 empty] | 9.16 |  | 2: TOTAL :; 4: 99; 6: 99; Cumulative 7: 72.38; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 72.33
PRAKASAM
74 | Uppugundur | 9 | - | - | - | - | - | - | Yes | 7.38 | Completed. Final bill to be paid. | Uppugundur | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 | 32/09-10 | 9 | 31.7.10 | 31.3.11 | Work completed. | Work completed. | 7.38 | - | - | - | - | 7.38 |  | 81
75 | Motumala | 9 | - | - | - | - | - | - | Yes | 8.34 | Completed. Final bill to be paid. | Motumala | ..do.. | 9 | 52/09-10 | 9 | 14.8.10 | 15.12.10 | Work completed. | Work completed. | 8.34 | - | - | - | - | 8.34 |  | 82
76 | Pavuluru | 9 | - | - | - | - | - | - | Yes | 7.54 | Completed. Final bill to be paid. | Pavuluru | ..do.. | 9 | 47/09-10 | 9 | 31.7.10 | 15.3.11 | Work completed. | Work completed. | 7.54 | - | - | - | - | 7.54 |  | 83
77 | Somavarappadu | 9 | - | - | - | - | - | - | Yes | 6.71 | Completed. Final bill to be paid. | Somavarappadu | ..do.. | 9 | 42/09-10 | 9 | 31.7.10 | 31.3.11 | Work completed. | Work completed. | 6.71 | - | - | - | - | 6.71 |  | 84
78 | Karavadi | 9 | - | - | - | - | - | Yes | - | 4.34 | Finishings in progress | Karavadi | ..do.. | 9 | 33/09-10 | 9 | 31.7.10 | 31.7.10 | Work completed. | Work completed. | 4.34 | - | - | - | - | 4.34 |  | 85
79 | Konijedu | 9 | - | - | - | - | - | - | Yes | 8.34 | Work completed. Final bill paid. | Konijedu | ..do.. | 9 | 51/09-10 | 9 | 14.8.10 | 14.8.10 | Work completed. | Work completed. | 8.34 | - | - | - | - | 8.34 |  | 86
80 | East Gangavaram | 9 | - | - | - | - | - | - | Yes | 8.19 | Work completed and handed over. Final bill paid. | East Gangavaram | ..do.. | 9 | 43/09-10 | 9 | 31.7.10 | 31.7.10 | Work completed. | Completed | 8.19 | - | - | - | - | 8.19 |  | 87
81 | Thimmanapalem | 9 | - | - | - | - | - | - | Yes | 7.4 | Work completed and handed over. Final bill paid. | Thimmanapalem | ..do.. | 9 | 46/09-10 | 9 | 2.8.10 | 31.3.11 | Work completed. | Work completed. | 7.4 | - | - | - | - | 7.4 |  | 88
82 | Kotikalapudi | 9 | - | - | - | - | - | - | Yes | 5.38 | Work completed. Building to be handed over. | Kotikalapudi | ..do.. | 9 | 34/09-10 | 9 | 31.7.10 | 31.3.11 | Work completed. | Work completed. | 5.38 | - | - | - | - | 5.38 |  | 89
83 | Ravinuthala | 9 | - | - | - | - | - | - | Yes | 3.52 | Work completed. Building to be handed over. | Ravinuthala | ..do.. | 9 | 37/09-10 | 9 | 31.7.10 | 31.3.11 | Work completed. | Completed | 3.52 | - | - | - | - | 3.52 |  | 90
84 | Muppavaram | 9 | - | - | - | - | - | - | Yes | 3.8 | Work completed. Building to be handed over. | Muppavaram | ..do.. | 9 | 46/09-10 | 9 | 21.7.10 | 31.3.11 | Work completed. | Work completed. | 3.8 | - | - | - | - | 3.8 |  | 91
| TOTAL : | 99 | [7 empty] | 70.94 |  | 2: TOTAL :; 4: 99; 6: 99; Cumulative 7: 70.94; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 70.94
NELLORE
85 | Ponguru | 9 | - | - | - | - | - | - | Yes | 4.6 | Work completed and to be handed over. | Ponguru | ..do.. | 9 | 56 /09-10, Dt. 24.12.09 | 9 | 30.09.10 |  | Work completed. | Work completed. | 4.6 | -- | -- | -- | -- | 4.6 |  | 92
86 | Pedagopavaram | 9 | - | - | - | - | - | - | Yes | 8.4 | Building handed over. Final bill paid. | Pedagopavaram | ..do.. | 9 | 39 /09-10, Dt. 13.11.09 | 9 | 07.07.10 |  | Work completed. | Work completed. | 8.4 | -- | -- | -- | -- | 8.4 |  | 93
87 | Jorepalli | 9 | - | - | - | - | - | - | Yes | 8.09 | Building handed over. Final bill paid. | Jorepalli | ..do.. | 9 | 59 /09-10, Dt. 24.12.09 | 9 | 070.8.10 |  | Work completed. | Work completed. | 8.09 | -- | -- | -- | -- | 8.09 |  | 94
88 | Daggavolu | 9 | - | - | - | - | - | - | Yes | 6.01 | Work completed to be handed over | Daggavolu | ..do.. | 9 | 57 /09-10, Dt. 24.12.09 | 9 | 17.09.10 |  | Work completed. | Work completed. | 6.01 | -- | -- | -- | -- | 6.01 |  | 95
89 | Illupuru | 9 | - | - | - | - | - | - | Yes | 6.29 | Work completed and handed over. Final bill to be paid. | Illupuru | ..do.. | 9 | 40 /09-10, Dt. 13.11.09 | 9 | 17.09.10 |  | Work completed. | Work completed. | 6.29 | -- | -- | -- | -- | 6.29 |  | 96
90 | Paravolu | 9 | - | - | - | - | - | Yes | - | 3.8 | Finishings in progress | Paravolu | ..do.. | 9 | 41 /09-10, Dt. 13.11.09 | 9 | 04.08.10 |  | Work completed. | Finishings in Progress | 3.8 | -- | -- | -- | -- | 3.8 |  | 97
91 | Andalamala | 9 | - | - |  | - | - | - | Yes | 4.21 | Completed building handed over, Final bill to be paid | Andalamala | ..do.. | 9 | 58 /09-10, Dt. 24.12.09 | 9 | 17.09.10 |  | Work completed. | Work completed. | 4.21 | -- | -- | -- | -- | 4.21 |  | 98
| TOTAL : | 63 | [7 empty] | 41.4 |  | 2: TOTAL :; 4: 63; 6: 63; Cumulative 7: 41.4; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 41.4
CHITTOOR
92 | Gopidinne | 9 | - | - | - | - | - | - | Yes | 5.83 | Work completed and handed over. Final bill paid. | Gopidinne | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 | 28/EE/APHMHIDC/TPT/09-10 Dt.10-11-09 | 9 |  | 4 Months | Work completed and handed over. Final bill paid. | Work completed. | 5.83 | --- | --- | 1.39 | 1.39 | 7.22. |  | 99
93 | Santhavellore | 9 | - | - | - | - | - |  | Yes | 8.42 | Work completed and handed over. Final bill paid. | Santhavellore | - do - | 9 | 29/EE/APHMHIDC/TPT/09-10 Dt.10-11-09 | 9 |  | 4 Months | Work completed and handed over. Final bill paid. | Work completed. | 8.42 | --- | --- | 0 | 0 | 8.42 |  | 100
94 | Mukkalathuru | 9 | - | - | - | - | - |  | Yes | 5.47 | Work completed and handed over. Final bill paid. | Mukkalathuru | - do - | 9 | 30/EE/APHMHIDC/TPT/09-10 Dt.10-11-09 | 9 |  | 4 Months | Work completed and handed over. Final bill paid. | Work completed. | 5.47 | --- | --- | 2.66 | 2.66 | 8.13 |  | 101
95 | K.Reddyvaripalle | 9 | - | - | - | - | - | - | Yes | 6.18 | Work completed and handed over. Final bill to be paid. | K.Reddyvaripalle | - do - | 9 | 31/EE/APHMHIDC/TPT/09-10 Dt.10-11-09 | 9 |  | 4 Months | Work completed and handed over. Final bill paid. | Work completed. | 5.6 | --- | --- | 0 | 0 | 6.18 |  | 102
96 | Karakambadi | 9 | - | - | - | - | - |  | Yes | 8.44 | Work completed and handed over. Final bill paid. | Karakambadi | - do - | 9 | 32/EE/APHMHIDC/TPT/09-10 Dt.10-11-09 | 9 |  | 4 Months | Work completed and handed over. Final bill paid. | Work completed. | 7.3 | --- | --- | 0 | 0 | 8.44 |  | 103
97 | Poyya | 9 | - | - | - | - | - | - | Yes | 8.43 | Work completed and handed over. Final bill paid. | Poyya | - do - | 9 | 33/EE/APHMHIDC/TPT/09-10 Dt.10-11-09 | 9 |  | 4 Months | Work completed and handed over. Final bill paid. | Work completed. | 5.79 | --- | --- | 0 | 0 | 8.43 |  | 104
98 | Mangalampeta | 9 | - | - | - | - | - |  | Yes | 8.17 | Work completed and handed over. Final bill paid. | Mangalampeta | - do - | 9 | 34/EE/APHMHIDC/TPT/09-10 Dt.10-11-09 | 9 |  | 4 Months | Work completed and handed over. Final bill paid. | Work completed. | 6.26 | --- | --- | 0 | 0 | 8.17 |  | 105
99 | Bodevandlapalle | 9 | - | - | - | - | - | - | Yes | 8.29 | Work completed and handed over. Final bill to be paid. | Bodevandlapalle | - do - | 9 | 35/EE/APHMHIDC/TPT/09-10 Dt.10-11-09 | 9 |  | 4 Months | Work completed and handed over. Final bill paid. | Work completed. | 6.07 | --- | --- | 0 | 0 | 8.29 |  | 106
100 | N.R.Puram | 9 | - | - | - | - | - | - | Yes | 8.04 | Work completed and handed over. Final bill paid. | N.R.Puram | - do - | 9 | 36/EE/APHMHIDC/TPT/09-10 Dt.10-11-09 | 9 |  | 4 Months | Work completed and handed over. Final bill paid. | Work completed. | 6.06 | --- | --- | 0 | 0 | 8.04 |  | 107
| TOTAL : | 54 | [7 empty] | 47.55 |  | 2: TOTAL :; 4: 81; 6: 81; Cumulative 7: 56.8; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 4.05; Total 11: 4.05; Total 6: 64.1
KADAPA
101 | Kondasunkesula | 9 | - | - | - | - | - | - | Yes | 3.28 | Work completed | Kondasunkesula | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 | DR. No:10/ 2009-10, Dt:2-11-09 | 9 | 03.11.10 | -- | Work completed and final bill paid. | Work completed and final bill paid. | 8.19 | --- | --- | --- | --- | 8.19 |  | 108
102 | Morrayapalli | 9 | - | - | - | - | - | - | Yes | 4.79 | Work completed | Morrayapalli | - do - | 9 | DR. No:11/ 2009-10, Dt:2-11-09 | 9 | 04.11.10 | -- | Work completed. | Work completed. | 4.79 | --- | --- | --- | --- | 4.79 |  | 109
103 | Potladurthi | 9 | - | - | - | - | - | - | Yes | 8.3 | Work completed | Potladurthi | - do - | 9 | DR. No:12/ 2009-10, Dt:2-11-09 | 9 | 02.06.10 | -- | Work completed and final bill paid. | Work completed and final bill paid. | 8.3 | --- | --- | --- | --- | 8.3 |  | 110
104 | Bodithippannapadu | 9 | - | - | - | - | - | - | Yes | 4.88 | Work completed | Bodithippannapadu | - do - | 9 | DR. No:13/ 2009-10, Dt:2-11-09 | 9 | 29.06.10 | -- | Work completed and final bill to be paid. | Work completed and final bill to be paid. | 4.88 | 0 | 0 | 1.89 | 1.89 | 8.17 |  | 111
105 | Thallapalli | 9 | - | - | - | - | - | - | Yes | 3.41 | Work completed | Thallapalli | - do - | 9 | DR. No:14/ 2009-10, Dt:2-11-09 | 9 | 29.06.10 | -- | Work completed. | Work completed. | 3.41 | 0 | 0 | 0 | 0 | 7.12 |  | 112
106 | Konduru | 9 | - | - | - | - | - | - | Yes | 8.37 | Work completed | Konduru | - do - | 9 | DR. No:15/ 2009-10, Dt:2-11-09 | 9 | 10.06.10 | -- | Work completed and final bill paid. | Work completed and final bill paid. | 8.37 | --- | --- | --- | --- | 8.37 |  | 113
107 | Vandadi | 9 | - | - | - | - | - | Yes | - | 3.07 | Brick masonry is under progress | Vandadi | - do - | 9 | DR. No:16/ 2009-10, Dt:2-11-09 | 9 | 29.06.10 |  | Work completed. |  | 3.07 | --- | --- | --- | --- | 3.07 |  | 114
108 | Munnelli | 9 | - | - | - | - | - | - | Yes | 2.96 | Work completed | Munnelli | - do - | 9 | DR. No:17/ 2009-10, Dt:2-11-09 | 9 | 09.06.10 |  | Work completed and final bill to be paid. | Work completed and final bill to be paid. | 2.96 | --- | --- | --- | --- | 2.99 |  | 115
109 | Palugaripalli | 9 | - | - | - | - | - | - | Yes | 3.16 | Work completed | Palugaripalli | - do - | 9 | DR. No:19/ 2009-10, Dt:2-11-09 | 9 | 29.06.10 |  | Work completed and final bill paid | Work completed and final bill paid | 8.23 | --- | --- | --- | --- | 8.26 |  | 116
110 | T.Kammapalli | 9 | - | - | - | - | - | Yes | - | 3.07 | Roof slab laid and finishing items are in progress | T.Kammapalli | - do - | 9 | DR. No:20/ 2009-10, Dt:2-11-09 | 9 | 29.06.10 |  | Work completed. |  | 3.07 | --- | --- | --- | --- | 3.07 |  | 117
111 | Peddajonnavaram | 9 | - | - | - | Yes | - | - | - |  | Plinth beam laid | Peddajonnavaram | - do - | 9 | DR. No:07/ 2010-11, Dt:30.10.10 | 9 | 29.06.10 |  | Work completed. |  | 2.15 | --- | --- | --- | --- | 4.18 |  | 118
112 | Gurrappagaripalli | 9 | - | Yes | - | - | - | - | - |  | Earth work for foundation is in progress | Gurrappagaripalli | - do - | 9 | DR. No:07/ 2010-11, Dt:30.10.10 | 9 | 05.06.11 |  | Work completed. |  | 0 | --- | --- | --- | --- | 3.1 |  | 119
| TOTAL : | 18 | [7 empty] | 0 |  | 2: TOTAL :; 4: 108; 6: 108; Cumulative 7: 57.42; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 1.89; Total 11: 1.89; Total 6: 69.61
ANANTHAPUR
113 | Chinthalacheruvu | 9 | - | - | - |  | - | - | Yes | 4.28 | Work completed | Chinthalacheruvu | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW. | 9 | D.R.No.20/2009-10 Dt.3-10-2009 | 9 | (4 Months) 2-3-2010 | 31-10-2010 | Work completed. Final bill to be paid. | Work completed. Final bill to be paid. | 4.28 | 0 | 4.63 | 0 | 4.63 | 8.91 |  | 120
114 | Kadavakallu | 9 | - | - | - | - | - | - | Yes | 2.45 | Work completed | Kadavakallu | - do - | 9 | D.R.No.21 /2009-10 Dt.3-10-2009 | 9 | (4 Months) 17-3-2010 | 31-11-2010 | Work completed. Final bill to be paid. | Work completed. Final bill to be paid. | 2.45 | -- | 3.8 | 0 | 3.8 | 6.25 |  | 121
115 | E.Sodanapalli | 9 | - | - | - | - | - | - | Yes | 2.86 | Work completed. | E.Sodanapalli | - do - | 9 | D.R.No.22 /2009-10 Dt.3-10-2009 | 9 | (4 Months) 16-3-2010 | 31-7-2010 | Work completed. Final bill to be paid. | Work completed. Final bill to be paid. | 2.86 | -- | 3.19 | 0 | 3.19 | 6.05 |  | 122
116 | Undebanda | 9 | - | - | - | - | - | - | Yes | 3.72 | Work completed. | Undebanda | - do - | 9 | D.R.No.24 /2009-10 Dt.3-10-2009 | 9 | (4 Months) 26-3-2010 | 31-10-2010 | Work completed and handed over. | Work completed and handed over. | 3.72 | -- | 3.91 | 0 | 3.91 | 7.63 |  | 123
117 | Govindawada | 9 | - | - | - | - |  | - | Yes | 7.34 | Work completed and handed over | Govindawada | - do - | 9 | D.R.No.25 /2009-10 Dt.3-10-2009 | 9 | (4 Months) 27-4-2010 | 16-6-2010 | Work completed and handed over. | Work completed and handed over. | 7.34 | -- | 0 | 0 | 0 | 7.34 |  | 124
118 | Konapuram | 9 | - | - | - | - | - | - | Yes | 7.4 | Work completed and handed over | Konapuram | - do - | 9 | D.R.No.26 /2009-10 Dt.3-10-2009 | 9 | (4 Months) 27-4-2010 | 4-9-2010 | Work completed and handed over. | Work completed and handed over. | 7.4 | -- | 0 | 0 | 0 | 7.4 |  | 125
119 | Phalaram | 9 | - | - | - | - | - | - | Yes | 3.15 | Work completed. | Phalaram | - do - | 9 | D.R.No.27 /2009-10 Dt.3-10-2009 | 9 | (4 Months) 16-3-2010 | 15-7-2010 | Work icompleted. Final bill to be paid. | Work icompleted. Final bill to be paid. | 3.15 | -- | 2.92 | 0 | 2.92 | 6.07 |  | 126
120 | Godduvelagala | 9 | - | - | - | - | - | - | Yes | 7.84 | Work completed and handed over | Godduvelagala | - do - | 9 | D.R.No.28 /2009-10 Dt.3-10-2009 | 9 | (4 Months) 29-2-2010 | 10-5-2011 | Work completed. Final bill to be paid. | Work completed. Final bill to be paid. | 7.84 | -- | 0 | 0 | 0 | 7.84 |  | 127
121 | Jagarajupalli | 9 | - | - | - | - | - | - | Yes | 8.63 | Work completed | Jagarajupalli | - do - | 9 | D.R.No.29 /2009-10 Dt.3-10-2009 | 9 | (4 Months) 26-3-2010 | 10-5-2010 | Work completed. Final bill to be paid. | Work completed. Final bill to be paid. | 8.63 | -- | 0 | 0 | 0 | 8.63 |  | 128
| TOTAL : | 27 | [7 empty] | 19.62 |  | 2: TOTAL :; 4: 81; 6: 81; Cumulative 7: 47.67; Cumulative 8: 0; To end of Previous Month 9: 18.45; During Month 10: 0; Total 11: 18.45; Total 6: 66.12
KURNOOL
122 | Bachipalli | 9 | - | - | - | - | - | - | Yes | 8.4 | Work completed and handed over. Final bill to be paid. | Bachipalli | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 | 50/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.41 | -- | -- | -- | -- | 8.41 | -- | 129
123 | Grumpamandinne | 9 | - | - | - | - | - | - | Yes | 8.39 | Work completed and handed over. Final bill to be paid. | Grumpamandinne | - do - | 9 | 51/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.39 | -- | -- | -- | -- | 8.39 | -- | 130
124 | B.Nagireddy Palli | 9 | - | - | - | - | - | - | Yes | 8.41 | Work completed and handed over. Final bill to be paid. | B.Nagireddy Palli | - do - | 9 | 52/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.41 | -- | -- | -- | -- | 8.41 | -- | 131
125 | Thummalur | 9 | - | - | - | - | - | - | Yes | 8.08 | Work completed and handed over. Final bill to be paid. | Thummalur | - do - | 9 | 53/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.09 | -- | -- | -- | -- | 8.09 | -- | 132
126 | Vanala | 9 | - | - | - | - | - | - | Yes | 3.08 | Work completed and handed over. Final bill to be paid. | Vanala | - do - | 9 | 54/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 3.08 | -- | -- | -- | -- | 3.08 | -- | 133
127 | Iskala | 9 | - | - | - | - | - | - | Yes | 8.4 | Work completed and handed over. Final bill to be paid. | Iskala | - do - | 9 | 55/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.4 | -- | -- | -- | -- | 8.4 | -- | 134
128 | Chinnavangali | 9 | - | - | - | - | - | - | Yes | 8.3 | Work completed and handed over. Final bill to be paid. | Chinnavangali | - do - | 9 | 56/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.4 | -- | -- | -- | -- | 8.4 | -- | 135
129 | Thodendla palli | 9 | - | - | - | - | - | - | Yes | 8.4 | Work completed and handed over. Final bill to be paid. | Thodendla palli | - do - | 9 | 57/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.41 |  | -- | -- | -- | 8.41 | -- | 136
130 | Giddalur | 9 | - | - | - | - | - | - | Yes | 8.41 | Work completed and handed over. Final bill to be paid. | Giddalur | - do - | 9 | 59/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.41 |  | -- | -- | -- | 8.41 | -- | 137
131 | Ramapuram | 9 | - | - | - | - | - | - | Yes | 8.41 | Work completed and handed over. Final bill to be paid. | Ramapuram | - do - | 9 | 60/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.41 |  | -- | -- | -- | 8.41 | -- | 138
132 | Pulimaddi | 9 | - | - | - | - | - | - | Yes | 8.41 | Work completed and handed over. Final bill to be paid. | Pulimaddi | - do - | 9 | 61/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.41 |  | -- | -- | -- | 8.41 | -- | 139
133 | Guttapalli | 9 | - | - | - | - | - | - | Yes | 8.41 | Work completed and handed over. Final bill to be paid. | Guttapalli | - do - | 9 | 62/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.41 |  | -- | -- | -- | 8.41 | -- | 140
134 | Yerrakota | 9 | - | - | - | - | - | - | Yes | 8.39 | Work completed and handed over. Final bill to be paid. | Yerrakota | - do - | 9 | 63/ 2009-10 | 9 | -- | -- | Work completed and handed over, final bill to be paid. | Work completed and handed over, final bill to be paid. | 8.4 |  | -- | -- | -- | 8.4 |  | 141
| TOTAL : | 117 | [7 empty] | 103.49 |  | 2: TOTAL :; 4: 117; 6: 117; Cumulative 7: 103.63; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 103.63
MAHABOOBNAGAR
135 | Venkateshwarla bavi | 9 | - | - | - | - | - | - | Yes | 7.02 | Completed & Handed over | Venkateshwarla bavi | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 |  | 9 |  |  | Work completed & handed over | Work completed & handed over | 7.02 | -- | -- | -- | -- | 7.02 |  | 142
136 | Channampally | 9 | - | - | - | - | - | Yes | - | 3.45 | Finishing works are in progress | Channampally | - do - | 9 |  | 9 |  |  | Work completed. |  | 3.45 | -- | -- | -- | -- | 7 |  | 143
137 | Koritical | 9 | - | - | - | - | - | - | Yes | 8.16 | Work completed. | Koritical | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 8.16 | -- | -- | -- | -- | 8.16 |  | 144
138 | Domalapenta | 9 | - | - | - | - | - | - | Yes | 8.4 | Work completed. | Domalapenta | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 8.4 | -- | -- | -- | -- | 8.4 |  | 145
139 | Mukkudigundam | 9 | - | - | - | - | - | - | Yes | 4.95 | Work completed. | Mukkudigundam | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 4.95 | -- | -- | -- | -- | 7.8 |  | 146
140 | Maredimandinne | 9 | - | - | - | - | - | - | Yes | 4.79 | Work completed. | Maredimandinne | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 4.79 | -- | -- | -- | -- | 7.9 |  | 147
141 | Duppally | 9 | - | - | - | - | - | - | Yes | 4.81 | Work completed. | Duppally | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 4.81 | -- | -- | -- | -- | 8.1 |  | 148
142 | Kolpur | 9 | - | - | - | - | - | - | Yes | 8.11 | Work completed. | Kolpur | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 8.11 | -- | -- | -- | -- | 8.11 |  | 149
143 | Pulikal | 9 | - | - | - | - | - | - | Yes | 8.38 | Work completed. | Pulikal | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 8.38 | -- | -- | -- | -- | 8.38 |  | 150
144 | Koppunur | 9 | - | - | - | - | - | - | Yes | 4.16 | Work completed. | Koppunur | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 4.16 | -- | -- | -- | -- | 7.95 |  | 151
145 | Parupalli | 9 | - | - | - | - | - | - | Yes | 7.05 | Work completed. | Parupalli | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 7.05 | -- | -- | -- | -- | 7.05 |  | 152
146 | Linganvai | 9 | - | - | - | - | - | - | Yes | 6.7 | Work completed. | Linganvai | - do - | 9 |  | 9 |  |  | Work completed. | Work completed. | 6.7 | -- | -- | -- | -- | 7.53 |  | 153
| TOTAL : | 108 | [7 empty] | 75.98 |  | 2: TOTAL :; 4: 108; 6: 108; Cumulative 7: 75.98; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 93.4
RANGA REDDY
147 | Indur | 9 | - | - | - | - | - | - | Yes | 3.07 | Work completed. | Indur | - do - | 9 |  | 9 | 21.05.2011 |  | Work completed and handed over. | Work completed and handed over. | 2.84 | 0 | 4.03 | 0 | 4.03 | 6.87 |  | 154
148 | Tormamidi | 9 | - | - | - | - | - | - | Yes | 6.17 | Work completed. | Tormamidi | - do - | 9 |  | 9 | 21.05.2011 |  | Work completed and handed over. | Work completed and handed over. | 5.71 |  | 1.67 |  | 1.67 | 7.38 |  | 155
149 | Barwad | 9 | - | - | - | - | - | - | Yes | 7.79 | Work completed. | Barwad | - do - | 9 |  | 9 | 10.05.2011 |  | Work completed and handed over. | Work completed and handed over. | 7.79 |  | 0.3 |  | 0.3 | 8.09 |  | 156
150 | Korviched | 9 | - | - | - | - | - | Yes | - | 4.26 | Work nearing completion. | Korviched | - do - | 9 |  | 9 | 21.05.2011 |  | Work completed and handed over. | Work completed and handed over. | 3.94 |  | 2.26 |  | 2.26 | 6.2 |  | 157
151 | Ainapur | 9 | - | - | - | - | - | - | Yes | 5.63 | Work completed. | Ainapur | - do - | 9 |  | 9 | 21.05.2011 |  | Work completed and handed over. | Work completed and handed over. | 4.24 |  | 0.96 | 1.33 | 2.29 | 6.53 |  | 158
152 | Bompally | 9 | - |  | - | - | - | - | Yes | 5.14 | Work completed. | Bompally | - do - | 9 |  | 9 | 21.05.2011 |  | Work completed and handed over. | Work completed and handed over. | 4.75 |  | 2.79 | 0 | 2.79 | 7.54 |  | 159
153 | Yella Konda | 9 | - | - | - | - | - | - | Yes | 7.47 | Work completed. | Yella Konda | - do - | 9 |  | 9 | 10.05.2011 |  | Work completed and handed over. | Work completed and handed over. | 7.47 |  | 0.3 |  | 0.3 | 7.77 |  | 160
154 | Nagaram | 9 | - | - | - | - | - | - | Yes | 6.36 | Work completed. | Nagaram | - do - | 9 |  | 9 | 01.06.2011 |  | Work completed and handed over. | Work completed and handed over. | 5.88 |  | 2 |  | 2 | 7.88 |  | 161
| TOTAL : | 72 | [7 empty] | 45.89 |  | 2: TOTAL :; 4: 72; 6: 72; Cumulative 7: 42.62; Cumulative 8: 0; To end of Previous Month 9: 14.31; During Month 10: 1.33; Total 11: 15.64; Total 6: 58.26
MEDAK
155 | Singoor | 9 | - | - | - | - | - | - | Yes | 4.87 | Work completed and handed over | Singoor | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW. | 9 |  | 9 |  |  | Work completed and final bill to be submitted | Work completed and final bill to be submitted | 7.19 | -- | -- | -- | -- | 8.38 |  | 162
156 | Gongloor | 9 | - | - | - | - | - | - | Yes | 4.75 | Work completed and handed over | Gongloor | - do - | 9 |  | 9 |  |  | Work completed and handed over. | Work completed and handed over. | 4.75 | -- | -- | -- | -- | 7.98 |  | 163
157 | Chinthakunta | 9 | - | - | - | - | - | - | Yes | 4.42 | Work completed and handed over | Chinthakunta | - do - | 9 |  | 9 |  |  | Work completed and handed over. | Work completed and handed over. | 4.42 | -- | -- | -- | -- | 7.36 |  | 164
158 | Almaipet | 9 | - | - | - | - | - | - | Yes | 4.56 | Work completed and handed over | Almaipet | - do - | 9 |  | 9 |  |  | Work completed and handed over. | Work completed and handed over. | 4.56 | -- | -- | -- | -- | 7.73 |  | 165
159 | Balwanthpur | 9 | - | - | - | - | - | - | Yes | 6.44 | Work completed and to be handed over | Balwanthpur | - do - | 9 |  | 9 |  |  | Work completed and handed over. | Work completed and handed over. | 7.26 | -- | -- | -- | -- | 8.41 |  | 166
160 | Dhamaracheru | 9 | - | - | - | - | - | - | Yes | 4.13 | Work completed and handed over. Power supply to be given. | Dhamaracheru | - do - | 9 |  | 9 |  |  | Work completed | Work completed | 4.13 | -- | -- | -- | -- | 8.35 |  | 167
161 | Habsipur | 9 | - | - | - | - | - | - | Yes | 4.61 | Work completed and to be handed over | Habsipur | - do - | 9 |  | 9 |  |  | Work completed and handed over. | Work completed and handed over. | 4.61 | -- | -- | -- | -- | 7.63 |  | 168
| TOTAL : | 63 | [7 empty] | 33.78 |  | 2: TOTAL :; 4: 63; 6: 63; Cumulative 7: 36.92; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 55.84
NIZAMABAD
162 | Manala | 9 | - | - | - | - | - | - | Yes | 5.96 | Work completed and to be handed over. Power supply to be given. | Manala | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 | 2/2009-10 Dt:11.11.2009 | 9 | 28.04.2010 |  | Work completed and handed over 06.05.2011. | Work completed and handed over 06.05.2011. | 8.51 | -- | -- | -- | -- | 8.51 |  | 169
163 | Pandimadgu | 9 | - | - | - | - | - | Yes | - | 2.76 | Plastering is in progress | Pandimadgu | - do - | 9 | 3/2009-10 Dt:11.11.2009 | 9 | 28.04.2010 | 31.07.2011 | Work completed and to be handed over. | Sanitary & electrical items tobe taken up. | 2.76 | -- | -- | -- | -- | 4.38 |  | 170
164 | Ramadugu | 9 | - | - | - | - | - | - | Yes | 6.64 | Work completed and handed over. | Ramadugu | - do - | 9 | 4/2009-10 Dt:11.11.2009 | 9 | 28.04.2010 | ……….. | Work completed and handed over 28.04.2011 | Work completed and handed over 28.04.2011 | 8.96 | -- | -- | -- | -- | 8.96 |  | 171
165 | Godmegaon | 9 | - | - | - | - | - | - | Yes | 6.89 | Work completed and to be handed over. | Godmegaon | - do - | 9 | 5/2009-10 Dt:11.11.2009 | 9 | 15.04.2010 | ……….. | Work completed and to be handed over. | Work completed and to be handed over. | 8.97 | -- | -- | -- | -- | 8.97 |  | 172
166 | Embura | 9 |  | - | - | - | - | - | Yes | 2.97 | Work completed and to be handed over. | Embura | - do - | 9 | 6/2009-10 Dt:11.11.2009 | 9 | 18.04.2010 |  | Work completed and to be handed over. | Work completed and to be handed over. | 8.97 | -- | -- | -- | -- | 8.97 |  | 173
167 | Nagalgaon | 9 | - | - | - | - | - | - | Yes | 8.31 | Work completed and handed over on 05.06.2010. | Nagalgaon | - do - | 9 | 7/2009-10 Dt:11.11.2009 | 9 | 18.04.2010 |  | Work completed and Handed over on 05-06-2010. | Work completed and Handed over on 05-06-2010. | 8.89 | -- | -- | -- | -- | 8.89 |  | 174
168 | Kankal | 9 | - | - | - | - | - | - | Yes | 5.12 | Work completed and handed over on 27.03.2011. | Kankal | - do - | 9 | 8/2009-10 Dt:11.11.2009 | 9 | 24.04.2010 |  | Work completed and handed over on 27.03.2011 | Work completed and Handed over on 27.03.2011 | 8.97 | -- | -- | -- | -- | 8.97 |  | 175
169 | Somarpet | 9 |  | - | - | - | - | - | Yes | 5.91 | Work completed and to be handed over. | Somarpet | - do - | 9 | 9/2009-10 Dt:11.11.2009 | 9 | 18.05.2010 |  | Work completed and handed over. | Work completed and to be handed over. | 6.13 | -- | -- | -- | -- | 8.66 |  | 176
170 | Jangam | 9 | - | - | - | - | - | - | Yes | 7.65 | Work completed and to be handed over. | Jangam | - do - | 9 | 10/2009-10 Dt:11.11.2009 | 9 | 04.05.2010 |  | Work completed and to be handed over. | Work completed and to be handed over. | 8.98 | -- | -- | -- | -- | 8.98 |  | 177
171 | Machapoor | 9 | - | - | - | - | - | - | Yes | 5.09 | Work completed and to be handed over. | Machapoor | - do - | 9 | 11/2009-10 Dt:11.11.2009 | 9 | 30.04.2010 | ……….. | Work completed and handed over 03.05.2011 | Work completed and handed over 03.05.2011 | 6.44 |  | 1.95 |  | 1.95 | 8.39 |  | 178
172 | Peddagulla | 9 | - | - | - | - | - | - | Yes | 8.14 | Work completed and handed over. Final bill to be paid. | Peddagulla | - do - | 9 | 12/2009-10 Dt:11.11.2009 | 9 | 18.04.2010 | ……….. | Work completed and Handed over 26.04.2010 | Work completed and Handed over 26.04.2010 | 8.71 | -- | -- | -- | -- | 8.71 |  | 179
173 | Babapur | 9 | - | - | - |  | - | Yes | - | 2.71 | Plasterings completed and water supply, sanitary & electrical work is in progress. | Babapur | - do - | 9 | 13/2009-10 Dt:11.11.2009 | 9 | 27.04.2010 | 31.07.2011 | Work completed and to be handed over. | Except Electrical & water supply all other items are completed | 2.71 | -- | -- | -- | -- | 7.12 |  | 180
174 | Madapur | 9 | - | - | - | - | - | - | Yes | 5.7 | Work completed and handed over. | Madapur |  | 9 | 2/2010-11 Dt:20.05.2010 | 9 | 01.09.2010 | ……….. | Work completed and handed over 02.02.2011 | Work completed and handed over 02.02.2011 | 8.84 | -- | -- | -- | -- | 8.84 |  | 181
| TOTAL : | 117 | [7 empty] | 73.85 |  | 2: TOTAL :; 4: 117; 6: 117; Cumulative 7: 97.84; Cumulative 8: 0; To end of Previous Month 9: 1.95; During Month 10: 0; Total 11: 1.95; Total 6: 108.35
ADILABAD
175 | Nippani | 9 | - | - | - | - | - | - | Yes | 6.38 | Work completed and handed over on 14.03.2011. Final bill paid. | Nippani | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 |  | 9 |  |  | Work completed and handed over on 14.03.2011. Final bill paid. | Work completed and handed over on 14.03.2011. Final bill paid. | 62.1 | -- | -- | -- | -- | 73.69 |  | 182
176 | Pochhara | 9 | - | Yes | - | - | - | - | - | - | Work stopped due to land dispute. | 2: Pochhara; 3: - do -; 4: 9; 6: 9; Total 7: Work stopped due to land dispute.
177 | Jatherla | 9 | - | - | - | - | - | - | Yes | 5.42 | Work completed. | 2: Jatherla; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 6: Completed and handed over. | 183
178 | Bheemaram | 9 | - | - | - | - | - | - | Yes | 6.3 | Work completed. | 2: Bheemaram; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 6: Work completed and handed over. | 184
179 | Dahegoan | 9 | - | - | - | - | Yes | - | - | 2.42 | Slab to be laid | 2: Dahegoan; 3: - do -; 4: 9; 6: 9; 5: Work completed. | 185
180 | Pandalwada | 9 | - | - | - | - | - | - | Yes | 8.24 | Work completed. | 2: Pandalwada; 3: - do -; 4: 9; 6: 9; 5: Completed and handed over.; Cumulative 6: Completed and handed over. | 186
181 | Pulimadugu | 9 | - | - | - | - | - | - | Yes | 8.28 | Work completed and handed over on 10.03.2011. Final bill paid. | 2: Pulimadugu; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over on 10.03.2011. Final bill paid.; Cumulative 6: Work completed and handed over on 10.03.2011. Final bill paid. | 187
182 | Nagala Konda | 9 | - | - | - | - | - | - | Yes | 7.36 | Work completed. | 2: Nagala Konda; 4: 9; 6: 9; 5: Work completed.; Cumulative 6: Work completed. | 188
183 | Gummunur B(Girnoor) | 9 | - | - | - | - | - | Yes | - | 2 | Brick work is in progress | 2: Gummunur B (Girnoor); 3: - do -; 4: 9; 6: 9; 5: Work completed. | 189
184 | Bhoraj | 9 | - | - | - | - | - | - | Yes | 8.31 | Work completed and handed over on 10.03.2011. Final bill paid. | 2: Bhoraj; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over on 10.03.2011. Final bill paid.; Cumulative 6: Work completed and handed over on 10.03.2011. Final bill paid. | 190
| TOTAL : | 90 | [7 empty] | 54.71 |  | 2: TOTAL :; 4: 90; 6: 90; Cumulative 7: 62.1; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 73.69
KARIMNAGAR
185 | Gunded | 9 | - | - | - | - | - | - | Yes | 9.59 | Work completed on 31.03.2010. Final bill paid. | Gunded | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW. | 9 | 5/2008-09, Dt:11.08.2008 | 9 | 17.12.08 | - | Completed on 31.03.2010 Final bill paid. | Work completed and handed over on 27.04.2011. Final bill paid. | 8.61 |  | 0 | 0 | 0 | 8.61 | - | 191
186 | Nimmampally | 9 | - | - | - | - |  | Yes | - | 7.1 | Plastering work is in progress | Nimmampally | - do - | 9 | 9/2008-09, Dt:11.08.2008 | 9 | 16.12.08 | - | Completed & Handed over on 03.04.2011 & Final bill paid | Work completed and handed over on 03.04.2011 & Final bill to be paid | 7.03 | - | 0 | 0 | 0 | 8.06 | - | 192
187 | Chikodu | 9 | - | - | - | - | - | - | Yes | 5.14 | Work completed. Final bill to be paid. | Chikodu | - do - | 9 | 19/2009-10, Dt:18.11.2009 | 9 | 25.03.10 | - | Completed & Handed over on 28.05.2011 Final bill to be paid | Work completed & Handed over on 28.05.2011 Final bill to be paid | 5.14 | - | 0 | 0 | 0 | 5.14 | - | 193
188 | Veernapally | 9 | - | - | - | - | - | - | Yes | 5.92 | Work completed and handed over on 09.05.2011. Final bill to be paid. | Veernapally | - do - | 9 | 8/2008-09, Dt:11.08.2008 | 9 | 25.03.10 | - | Completed & Handed over on 09.05.2011 Final bill to be paid | Work completed & Handed over on 09.05.2011 Final bill to be paid | 5.92 | - | 0 | 0 | 0 | 7.46 | - | 194
189 | Ramanapeta | 9 | - | - | - | - | - | Yes | - | 5.9 | Nearing completion | Ramanapeta | - do - | 9 | 36/2009-10, Dt:16.12.2009 | 9 | 27.04.10 | - | Completed & Handed over on 01.06.2011Final bill paid | Work completed & Handed over on 01.06.2011 | 3.89 | - | 2.01 | 0 | 2.01 | 8.4 | - | 195
190 | Garjanapally | 9 | - | - | - | - |  | Yes | - | 4.52 | Nearing completion | Garjanapally | - do - | 9 | 7/2008-09, Dt:11.08.2008 | 9 | 16.12.08 | - | Completed & Handed over on 17.11.2011 Final bill to be paid | Work completed & Handed over on 28.05.2011 Final bill to be paid | 4.52 | - | 1.65 | 0 | 1.65 | 8.01 | - | 196
191 | Pathpaka | 9 | - | - | - | Yes | - | - | - | 1.85 | Columns raised upto roof level. | Pathpaka | - do - | 9 | 11/2008-09, Dt:11.08.2008 | 9 | 16.12.08 | 30.06.11 | Completed & Handed over on 12.12.2011 Final bill to be paid |  | 1.85 | - | 0 | 1.42 | 1.42 | 8.09 | - | 197
192 | Akkanapalli | 9 | - | - | - | - | - | Yes | - | - | Slab laid. | Akkanapalli | - do - | 9 | 14/2009-10, Dt:18.12.2009 | 9 | 25.03.10 | 30.06.11 | Completed & Handed over on 18.11.2011 Final bill paid |  | 1.54 | - | 1.18 | 0 | 1.18 | 4.43 | - | 198
193 | Kandugula | 9 | - | - | - | - | - | Yes | - | 1.3 | Finishings are in progress | Kandugula | - do - | 9 | 16/2009-10, Dt:18.11.2009 | 9 | 25.03.10 | 31.01.11 | Completed & Handed over on 18.11.2011 Final bill to be paid |  | 2.2 | - | 0 | 0 | 0 | 6.46 | - | 199
194 | Aknoor | 9 | - | - | - | - | - | Yes | - | 1.8 | Brick work completed. | Aknoor | - do - | 9 | 6/2008-09, Dt:11.08.2008 | 9 | 01.06.09 | 31.08.11 | Work completed. |  | 3.53 | - | 0 | 0 | 0 | 4.72 | - | 198
195 | Chelpur-I | 9 | - | - | - | - | - | Yes | - | 2.72 | Slab laid. Brick work is in progress. | Chelpur-I | - do - | 9 | 15/2009-10, Dt:18.11.2009 | 9 | 25.03.10 | 31.08.11 | Completed and handed over on 29.12.2011 |  | 1.4 | - | 1.32 | 0 | 1.32 | 7.18 | - | 199
| TOTAL : | #REF! | [7 empty] | #REF! |  | 2: TOTAL :; 4: 99; 6: 99; Cumulative 7: 45.63; Cumulative 8: 0; To end of Previous Month 9: 6.16; During Month 10: 1.42; Total 11: 7.58; Total 6: 76.56
WARANGAL
196 | Rudragudem | 9 | - | - | - | - | - | - | Yes | 8.62 | Work completed and handed over. | 2: Rudragudem; 3: Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 6: Work completed and handed over.; Cumulative 7: 8.62; Total 6: 9 | 200
197 | Mondraigudem | 9 | - | - | - | - | - | - | Yes | 6.14 | Work completed. | 2: Mondraigudem; 3: - do -; 4: 9; 6: 9; 5: Work completed.; Cumulative 6: Work completed.; Cumulative 7: 6.14; Total 6: 9 | 201
198 | Pogulapalli | 9 | - | - | - | - | - | - | Yes | 8.22 | Work completed. | 2: Pogulapalli; 3: - do -; 4: 9; 6: 9; 5: Work completed.; Cumulative 6: Work completed.; Cumulative 7: 8.22; Total 6: 9 | 202
199 | Kamaram | 9 | - | - | - | - | - | - | Yes | 8.29 | Work completed. | 2: Kamaram; 3: - do -; 4: 9; 6: 9; 5: Work completed.; Cumulative 6: Work completed.; Cumulative 7: 8.29; Total 6: 9 | 203
200 | Marrigudem | 9 | - | - | - | - | - | - | Yes | 8.12 | Work completed. | 2: Marrigudem; 3: - do -; 4: 9; 6: 9; 5: Work completed.; Cumulative 6: Work completed.; Cumulative 7: 8.12; Total 6: 9 | 204
201 | Modugudem | 9 | - | - | - | - | - | - | Yes | 8.57 | Work completed. | 2: Modugudem; 3: - do -; 4: 9; 6: 9; 5: Work completed.; Cumulative 6: Work completed.; Cumulative 7: 8.57; Total 6: 9 | 205
202 | Marrimitta | 9 | - | - | - | - | - | - | Yes | 8.68 | Work completed and handed over | 2: Marrimitta; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over; Cumulative 6: Work completed and handed over; Cumulative 7: 8.68; Total 6: 9 | 206
203 | Incherla | 9 | - | - | - | - | - | - | Yes | 8.38 | Work completed and handed over | 2: Incherla; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over; Cumulative 6: Work completed and handed over; Cumulative 7: 8.38; Total 6: 9 | 207
204 | Uyyalawada | 9 | - | - | - | - | - | - | Yes | 8.43 | Work completed and handed over | 2: Uyyalawada; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over; Cumulative 6: Work completed and handed over; Cumulative 7: 8.43; Total 6: 9 | 208
205 | Mungimadugu | 9 | - | - | - | - | - | - | Yes | 8.78 | Work completed and handed over | 2: Mungimadugu; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over; Cumulative 6: Work completed and handed over; Cumulative 7: 8.78; Total 6: 9 | 209
206 | Uggampalli | 9 | - | - | - | - | - | - | Yes | 8.61 | Work completed and handed over | 2: Uggampalli; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over; Cumulative 6: Work completed and handed over; Cumulative 7: 8.61; Total 6: 9 | 210
207 | Redyala | 9 | - | - | - | - | - | - | Yes | 8.61 | Work completed and handed over | 2: Redyala; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over; Cumulative 6: Work completed and handed over; Cumulative 7: 8.61; Total 6: 9 | 211
208 | Peddavangara | 9 | - | - | - | - | - | - | Yes | 8.61 | Work completed. | 2: Peddavangara; 3: - do -; 4: 9; 6: 9; 5: Work completed.; Cumulative 6: Work completed.; Cumulative 7: 8.61; Total 6: 9 | 213
209 | Narlapur | 9 | - | - | - | - | - | - | Yes | 7.95 | Work completed and handed over. | 2: Narlapur; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 6: Work completed and handed over.; Cumulative 7: 7.95; Total 6: 9 | 214
210 | Reddygudem | 9 | - | - | - | - | - | - | Yes | 8.62 | Work completed and handed over. | 2: Reddygudem; 3: - do -; 4: 9; 6: 9; 5: Work completed and handed over.; Cumulative 6: Work completed and handed over.; Cumulative 7: 8.62; Total 6: 9 | 215
| TOTAL : | 135 | [7 empty] | 124.63 |  | 2: TOTAL :; 4: 135; 6: 135; Cumulative 7: 124.63; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 0; Total 11: 0; Total 6: 135
KHAMMAM
211 | Beerapalli | 9 | - | - | - | - | - | - | Yes | 8.37 | Work completed. | Beerapalli | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 |  | 9 | 4 Months | 4 Months | Work completed handed over | Work completed handed over |  |  | 5.92 | 2.45 | 8.37 | 8.37 |  | 216
212 | Yatalakunta | 9 | - | - | - | - | - | - | Yes | 8.42 | Work completed. | Yatalakunta | - do - | 9 |  | 9 | 4 Months | 4 Months | Work completed handed over | Work completed handed over |  |  | 5.87 | 2.55 | 8.42 | 8.42 |  | 217
213 | Thimminenipalem | 9 | - | - | - | - | - | - | Yes | 2.25 | Work completed. | Thimminenipalem | - do - | 9 |  | 9 | 4 Months | 4 Months | Work completed handed over | Work completed handed over |  |  | 2.25 | - | 2.25 | 2.25 |  | 218
214 | Marturpeta | 9 | - | - | - | - | - | - | Yes | 4.75 | Work completed. | Marturpeta | - do - | 9 |  | 9 | 4 Months | 4 Months | Work completed | Work completed |  |  | 3.25 | 1.5 | 4.75 | 4.75 |  | 219
215 | Chandrugonda | 9 | - | - | - | - | - | - | Yes | 3.75 | Work completed. | Chandrugonda | - do - | 9 |  | 9 | - | - | Work completed handed over | Work completed handed over |  |  | - | 3.75 | 3.75 | 3.75 |  | 220
216 | Jagannadapuram | 9 | Yes | - | - | - | - | - | - |  | 3rd recall | Jagannadapuram | - do - | 9 |  | 9 | - | - | Work completed under LWE funds. | - |  |  | - | - | - |  |  | 221
217 | Regupally | 9 | - | - | - | - | - | - | Yes | 8.42 | Work completed. | Regupally | - do - | 9 |  | 9 | 4 Months | 4 Months | Work completed handed over | Work completed handed over |  |  | 5.35 | 3.07 | 8.42 | 8.42 |  | 222
218 | Uppaka | 9 | - | Yes | - | - | - | - | - |  | Site problem | Uppaka | - do - | 9 |  | 9 | - | - | Work completed |  |  |  | - | - | - |  |  | 223
219 | Kommugudem | 9 | Yes | - | - | - | - | - | - |  | 3rd recall | Kommugudem | - do - | 9 |  | 9 | - | - | Work completed |  |  |  | - | - | - |  |  | 224
220 | Utkoor | 9 | - | - | - | - | - | - | Yes | 4.69 | Work completed. | Utkoor | - do - | 9 |  | 9 | 4 Months | 4 Months | Work completed | Work completed |  |  | 3.44 | 1.25 | 4.69 | 4.69 |  | 225
221 | Pragallapalli | 9 | - | - | - | - | - | - | Yes | 8.32 | Work completed. | Pragallapalli | - do - | 9 |  | 9 | 4 Months | 4 Months | Work completed handed over | Work completed handed over |  |  | 5.92 | 2.4 | 8.32 | 8.32 |  | 226
222 | Ankammavarigudem | 9 | - | - | - | - | - | - | Yes | 8.32 | Work completed. | Ankammavarigudem | - do - | 9 |  | 9 | 4 Months | 4 Months | Work completed handed over | Work completed handed over |  |  | 6.08 | 2.24 | 8.32 | 8.32 |  | 227
| TOTAL : | 108 | [7 empty] | 57.29 |  | 2: TOTAL :; 4: 108; 6: 108; Cumulative 7: 0; Cumulative 8: 0; To end of Previous Month 9: 38.08; During Month 10: 19.21; Total 11: 57.29; Total 6: 57.29
NALGONDA
223 | Urlugonda | 9 | - | - | - | - | - | - | Yes | 3.12 | Work completed. | Urlugonda | Proceedings NO.315/FW/P2/2008, dt.19-9-2009 of CFW | 9 | 18 / 09-10 / 09.11.09 | 9 | 01.06.11 |  | Work completed. | Work completed. | 3.12 | 0 | 0 | 3.31 | 3.31 | 6.43 |  | 228
224 | Inupamula | 9 | - | - | - | - | - | Yes | - | 4.27 | Plastering completed & Flooring is in progress. | Inupamula | - do - | 9 | 19 / 09-10 / 09.11.09 | 9 | 10.05.10 | 30.08.11 | Work completed. |  | 4.27 | - | - | - | - | 4.27 |  | 229
225 | Lingala | 9 | - | - | - | - | - | - | Yes | 6.16 | Work completed. | Lingala | - do - | 9 | 20 / 09-10 / 09.11.09 | 9 | 10.05.10 |  | Work completed. | Work completed. | 6.16 | - | - | - | - | 6.16 |  | 230
226 | Utkur | 9 | - | - | - | - | - | - | Yes | 6.85 | Work completed. | Utkur | - do - | 9 | 21/ 09-10/ 09.11.09 | 9 | 21.05.10 |  | Work completed. | Work completed. | 6.85 | - | - | - | - | 6.85 |  | 231
227 | Gummadavelly | 9 | - | - | - | - | - | Yes | - | 4.84 | Plastering completed | Gummadavelly | - do - | 9 | 22/ 09-10/ 09.11.09 | 9 | 10.05.10 |  | Work completed. | Work completed. | 4.84 | - | - | - | - | 4.84 |  | 232
228 | Kathalguda | 9 | - | - | - | - | - | - | Yes | 6.19 | Work completed. | Kathalguda | - do - | 9 | 23/ 09-10/ 09.11.09 | 9 | 15.05.10 |  | Work completed. | Work completed. | 6.19 | - | - | - | - | 6.19 |  | 233
229 | Jalpura | 9 | - | - | - | - | - | Yes | - | 4.4 | Work completed. | Jalpura | - do - | 9 | 24/ 09-10/ 09.11.09 | 9 | 01.06.10 |  | Work completed. | Work completed. | 4.4 | - | - | - | - | 4.4 |  | 234
230 | Kuchipudithanda | 9 | - | - | - | - | - | - | Yes | 5.6 | Work completed. | Kuchipudithanda | - do - | 9 | 25/ 09-10/ 09.11.09 | 9 | 10.05.10 |  | Work completed. | Work completed. | 5.6 | - | - | - | - | 5.6 |  | 235
231 | Dondapadu | 9 | - | - | - | - | - | - | Yes | 5.08 | Work completed | Dondapadu | - do - | 9 | 26/ 09-10/ 09.11.09 | 9 | 10.05.10 |  | Work completed. | Work completed. | 5.08 | - | - | - | - | 5.08 |  | 236
| TOTAL : | 81 | [7 empty] | 46.51 |  | 2: TOTAL :; 4: 81; 6: 81; Cumulative 7: 46.51; Cumulative 8: 0; To end of Previous Month 9: 0; During Month 10: 3.31; Total 11: 3.31; Total 6: 49.82
| Grand Total : | #REF! | [5 empty] | Grand Total : |  | #REF! |  | 2: Grand Total :; 4: 2079; 6: 2079; Cumulative 7: 1243.653; Cumulative 8: 19.01; To end of Previous Month 9: 220.363; During Month 10: 31.87; Total 11: 260.483; Total 6: 1668.528
4700000