## co.p (2)
Dt:19.01.2016
MATERNITY & CHILD HEALTH CENTRE OF EXCELLENCE
0

## 8 MCH ABS
MONTH WISE ABSTRACT
MATERNITY & CHILD HEALTH CENTRE OF EXCELLENCE PHASE-I
Sl. No. | District | AS/RAS amount (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up (6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other dept | Site problem | RAS awaited or etc | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | Nellore | 575 | 539.34 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
2 | Chittoor | 1050 | 1002.16 |  | 2 |  |  |  |  | 2 | 2 |  |  | 2 |  | 2
3 | Kurnool | 200 | 131.66 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
| TOTAL | 1825 | 1673.16 |  | 4 |  |  |  |  | 4 | 4 |  |  | 4 |  | 4

## 8 MCH PR
MATERNITY & CHILD HEALTH CENTRE OF EXCELLENCE PHASE-I
Sl. No | Name of District | HOD | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | Amount sanctioned (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Agreement / Tentative date of completion
1 | CTR |  | Construction of New Pediatric ward and maternity ward to S.V.R.R. Hospital, Tirupathi (NRHM), Chittoor District. | 15.06.2007 | 550 | 549.87 | M/s.I.Munimohan Reddy & Co | 31-12-2008
2 | CTR |  | Construction of 2nd floor over New Pediatric ward at S.V.R.R.G.G. Hospital, Tirupathi in Chittoor District. | 16-11-2010 | 500 | 452.29 | M/s.I.Munimohan Reddy & Co | 10-10-2011
3 | NLR |  | Construction of Maternal and Children centres 100 Bedded District Hospital at Nellore | 16-11-2010 | 575 | 539.34 | V. Prasad Naidu, Nellore | 11-11-2012
4 | KNL |  | Developing the Srisailam Project Hospital into a multi specialty hospital at Srisailam for Primitive Tribal Group of CHENCHU, Kurnool. | 18.08.2011 | 200 | 131.66 | B.Aleem Miah | 30-09-2012
|  |  | Total |  | 1825 | 1673.16
|  | Add establishment charges@ 7% |  |  |  | #REF!
|  | TOTAL : |  |  |  | #REF!

## Maty.child (hidden)
Scheme : Centres of Excellence for Maternal and Children's Health
Sl. No. | Name of the location | Reference to Administrative Approval | Administrative Sanction (Rs.in lakhs) | Expenditure (Rs.in lakhs) | Stage of work | Expected date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Strengthening of Maternity Centre with 450 beds in Niloufer Hospital, Hyderabad. | G.O. Ms. No. 318, Dt.16-11-2010 of HM&FW (D2) Dept., | 2060 | 1700 | Block-I Roof Slabs laid for all floors, Brick work, Plastering , Flooring, Dadooing completed. Internal Water supply and Electrical works in progress. Block-B Roof slabs laid for all floors. Brick work and plastering works completed. Flooring Dadooing internal Water Supply and Electrical wroks in progress. Block-C Roof slabs laid for all floors. Brick masonry work completed. Plastering works in progress | 31.12.2012
2 | Construction of Maternal and Childred centers at Petlaburz Hospital, Hyderabad | -do- | 1650 | 0 | Estimates over existing Block-A under preparation by M/s. S.S. Consultants
3 | Construction of Maternal and Childred centres at MGM Hospital, Warangal | -do- | 400 | 176.8 | Finishing's are in progress | 31.08.2012
4 | Construction of 2nd floor over New Pediatric ward at S.V.R.R.G.G. Hospital, Tirupathi in Chittoor District. | -do- | 500 | 361.22 | Work completed to be handed
5 | Construction of Maternal and Childred centres at District Hospital, Nellore | -do- | 500 | 297.88 | RAS to be received for Rs. 575.00 Lakhs | 30-09-2012
6 | Construction of Additional Accommodation in existing MCH block on first floor in old GGH, Vijayawada | Rc.No: 112/SPMU-NRHM/2011, Dated: 15.07.2011 of the CFW, Hyderabad. | 300 | 79.67 | Slab laid. Brick work is in progress.
| TOTAL: |  | 5110 | 2535.9

## 19 MCH ABS
ABSTRACT
MATERNITY & CHILD HEALTH CENTRE OF EXCELLENCE
Sl. No. | District | Administrative sanction (Rs.in lakhs) | Technical Sanction Amount |  |  | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up (6-10) | Status of takenup works |  |  | Final bill |  | Building
|  |  | Part - A TS / RAS (GF & FF) | Part - B (Additional Floors ) | Total (4+5) |  | Taken up by other dept | Site problem | RAS awaited or etc | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | Srikakulam | 2000 | 1110 | 890 | 2000 | 1 |  |  |  |  | 1 |  |  | 1 |  | 1 |  | 1
Part - A
Part - B
2 | Krishna | 300 | 300 | 0 | 300 | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
3 | Vizianagaram | 1000 | 1000 | 0 | 1000 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1
4 | Visakhapatnam | 1300 | 1300 | 0 | 1300 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 |  | 1
5 | East Godavari | 1400 | 1200 | 200 | 1400 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1
Part - A
Part - B
6 | West Godavari | 1700 | 1200 | 500 | 1700 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 |  | 1
Part - A
Part - B
7 | Krishna | 1050 | 1050 | 0 | 1050 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 |  | 1
8 | Guntur | 1000 | 1000 | 0 | 1000 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 |  | 1
9 | Chittoor | 2000 | 1150 | 850 | 2000 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 |  | 1
Part - A
Part - B
10 | Kurnool | 2000 | 1200 | 800 | 2000 | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1
Part - A
Part - B
| TOTAL | 13750 | 10510 | 3240 | 13750 | 10 |  |  |  |  | 10 | 9 | 0 | 1 | 1 | 9 | 4 | 6
13750

## 19 MCH
MATERNITY & CHILD HEALTH CENTRE OF EXCELLENCE PHASE-II
Part - A
Sl. No | Name of District | HOD | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of agency | Physical Progress |  |  | Plan Approved
[5 empty] | TS/ RE Amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Probable date of completion
1 | EG | APVVP | DH, Rajahmundry, East Godavari Dist. | 13.08.2012 | 1200 | 733.79 | M/s. DGB constructions PVT Ltd | 31.08.2015 | Work completed, final bill to be paid & Building handed over |  | Not approved
2 | KRISHNA | DME | GGH, Vijayawada,Krishna Dist. | 15.07.2011 /13.08.2012 | 300 | 204.05 | M/s. Rama Raju Constructions | 01.11.2012 | Work completed, final bill paid & Building handed over |  | Not approved
3 | CTR | APVVP | DH, Chittoor Dist. | 13.08.2012 | 1150 | 1042.68 | Sri.V.Prasad Naidu | 31.12.2014 | Work completed, final bill to be paid & Building handed over |  | Not approved
4 | KNL | APVVP | DH Nandyal, Kurnool Dist. | 13.08.2012 | 1200 | 930.19 | M/s NJR Constructions Pvt., Ltd., | 03.08.2015 | Work completed, final bill to be paid & Building handed over |  | Not approved
5 | VZNG | APVVP | DH, Vizianagaram. | 13.08.2012 | 1000 | 704.78 | Sri. A.Balarama Raju | 3 0.09.2015 | Work completed, final bill to be paid & Building Not handed over |  | Not approved
6 | VSP | APVVP | DH, Anakapalli, Visakhapatnam Dist. | 13.08.2012 | 1300 | 749.51 | Sri. A.Balarama Raju | 3 0.09.2015 | Work completed, final bill to be paid & Building to be handed over |  | Not approved
7 | KRI | APVVP | DH, Machilipatnam, Krishna Dist. | 13.08.2012 | 1050 | 832.88 | M/s. Haya greeve Infratech Projects ltd | 31.10.2015 | Work completed, final bill to be paid & Building to be handed over |  | Not approved
8 | WG | APVVP | DH, Eluru, West Godavari Dist. | 13.08.2012 | 1200 | 771.75 | M/s. Rajyalakshmi Builders | 30.11.2015 | Work completed, final bill to be paid & Building to be handed over |  | Not approved
9 | GNT | APVVP | DH, Tenali, Guntur Dist. | 13.08.2012 | 1000 | 601.74 | M/s. DJPR Constructions PVT LTD | 30.11.2015 | Work completed, final bill to be paid & Building to be handed over |  | Not approved
10 | SKLM | DME | RIMS, Srikakulam. | 13.08.2012 | 1110 | 350.03 | Sri K.Anantharao, |  | Workis in Progress / Slab laid | 30.06.2016 | Approved by RIMS Director & Superintendent
|  |  | TOTAL |  | 10510 | 6921.4
Part - B
1 | SKLM | DME | RIMS, Srikakulam. | 13.08.2012 | 890 |  |  |  | Tender Stage
2 | EG | APVVP | DH, Rajahmundry, East Godavari Dist. | 13.08.2012 | 200 |  |  |  | Work to be takenup
3 | WG | APVVP | DH, Eluru, West Godavari Dist. | 13.08.2012 | 500 |  |  |  | Tender Stage
4 | CTR | APVVP | DH, Chittoor Dist. | 13.08.2012 | 850 |  |  |  | Tender Stage
5 | KNL | APVVP | DH Nandyal, Kurnool Dist. | 13.08.2012 | 800 |  |  |  | Tender Stage
|  |  | TOTAL |  | 3240 | 0
|  |  | GRAND TOTAL |  | 13750 | 6921.4

## 2 MCH ABS
MONTH WISE ABSTRACT
MATERNITY & CHILD HEALTH CENTRE OF EXCELLENCE PHASE-III
Sl. No. | District | Administrative sanction (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up (6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other dept | Site problem | RAS awaited or etc | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | East Godavari | 2000 |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  | 1 |  | 1
2 | Guntur | 2000 |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  | 1 |  | 1
| TOTAL | 4000 |  |  | 2 |  |  |  |  | 2 |  | 2 |  |  | 2 |  | 2

## 2 MCH PR
MATERNITY & CHILD HEALTH CENTRE OF EXCELLENCE PHASE-III
Sl. No | Name of District | HOD | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | Amount sanctioned (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Agreement / Tentative date of completion
1 | EG |  | MCH block in GGH at Kakinada in East Godavari District Civil: Rs.1460.00 lakhs Equipment: Rs.540 lakhs | 21.07.2014 | 2000 |  |  |  | Agreement to be concluded
2 | GNT |  | MCH block in GGH at Guntur | 02.08.2014 | 2000 |  |  |  | Agreement to be concluded
|  |  | Total |  | 4000 | 0
|  | Add establishment charges@ 7% |  |  |  | #REF!
|  | TOTAL : |  |  |  | #REF!
6000
0