## co.p (2)
Dt:19.01.2016
Institute of Pregnant Women at Tirupathi
0

## 8 MCH ABS
MONTH WISE ABSTRACT
Sl. No. | District | Administrative sanction (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up (6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other dept | Site problem | RAS awaited or etc | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | Phase I | 2010 | 1883.39 |  | 1 |  |  |  | 0 | 1 | 1 |  |  |  | 1 | 1
2 | Phase II | 3720 | 590.86 |  | 1 |  |  |  | 0 | 1 |  |  | 1 |  | 1 |  | 1
| TOTAL | 5730 | 2474.25 |  | 2 |  |  |  | 0 | 2 | 1 | 0 | 1 | 0 | 2 | 1 | 1

## 8 MCH PR
Institute for Pregnant Women at Tirupathi
Sl. No | Name of District | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
|  |  |  | Amount sanctioned (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Agreement / Tentative date of completion
PHASE - I
1 | CTR | Establishment of Institute for Pregnant Women in SVRR, Govt., General Hospital, Tirupathi, Chittoor Dist. | 29.03.2012, | 2010 | 1883.39 | M/s. I. Muni Mohan Reddy & Co., |  | Work completed & final bill to be paid
PHASE - II
2 | CTR | Institute of Pregnant Women at Tirupathi | 19.12.2014 | 3720 | 590.86 | M/s. I. Munimohan Reddy & Co., |  | Roof Level Fourth floor roof slab completed for A,B,C blocks Plinth Beam completed for D,E,F blocks, Roof slab Centering is in progress for D block FF, Columns laying Centering is in progress for for E block FF. Brick work is in progress for A block 4th Floor. | 03.05.2016
2885.55

## Maty.child (hidden)
Scheme : Centres of Excellence for Maternal and Children's Health
Sl. No. | Name of the location | Reference to Administrative Approval | Administrative Sanction (Rs.in lakhs) | Expenditure (Rs.in lakhs) | Stage of work | Expected date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7
1 | Strengthening of Maternity Centre with 450 beds in Niloufer Hospital, Hyderabad. | G.O. Ms. No. 318, Dt.16-11-2010 of HM&FW (D2) Dept., | 2060 | 1700 | Block-I Roof Slabs laid for all floors, Brick work, Plastering , Flooring, Dadooing completed. Internal Water supply and Electrical works in progress. Block-B Roof slabs laid for all floors. Brick work and plastering works completed. Flooring Dadooing internal Water Supply and Electrical wroks in progress. Block-C Roof slabs laid for all floors. Brick masonry work completed. Plastering works in progress | 31.12.2012
2 | Construction of Maternal and Childred centers at Petlaburz Hospital, Hyderabad | -do- | 1650 | 0 | Estimates over existing Block-A under preparation by M/s. S.S. Consultants
3 | Construction of Maternal and Childred centres at MGM Hospital, Warangal | -do- | 400 | 176.8 | Finishing's are in progress | 31.08.2012
4 | Construction of 2nd floor over New Pediatric ward at S.V.R.R.G.G. Hospital, Tirupathi in Chittoor District. | -do- | 500 | 361.22 | Work completed to be handed
5 | Construction of Maternal and Childred centres at District Hospital, Nellore | -do- | 500 | 297.88 | RAS to be received for Rs. 575.00 Lakhs | 30-09-2012
6 | Construction of Additional Accommodation in existing MCH block on first floor in old GGH, Vijayawada | Rc.No: 112/SPMU-NRHM/2011, Dated: 15.07.2011 of the CFW, Hyderabad. | 300 | 79.67 | Slab laid. Brick work is in progress.
| TOTAL: |  | 5110 | 2535.9