## cov.p
Dt:19.01.2016
Construction of Community Health and Nutrition Cluster Offices (CHNCs) under NRHM for the year 2010-11

## abs81 (hidden)
ABSTRACT
Construction of Community Health and Nutrition Cluster Offices (CHNCs) under NRHM for the year 2011-12
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Status of works | [5 empty] | Work to be completed |  |  |  | Expenditure (Rs.in lakhs) | Remarks
|  |  |  | Site problem | Not taken up | Tender stage | Work to be started | Work is in progress | Work Completed | 30.04.2012 | 31.05.2012 | 30.06.2012 | 31.07.2012
1 | Srikakulam | 10 | 2 |  | 2 | [8 empty] | 7.06 | Requesting for New building.
2 | Vizianagaram | 15 | 3 |  |  |  |  | 1 | 2 | 1 |  |  |  | 13.85
3 | Visakhapatnam | 10 | 2 |  | 1 |  |  |  | 1 |  |  |  |  | 3.467 | To be executed by Tribal Welfare in Agency area.
4 | East Godavari | 20 | 4 |  |  |  |  | 3 | 1 |  | 3 |  |  | 17.52
5 | West Godavari | 5 | 1 |  |  |  |  | 1 |  |  | 1 |  |  | 1.78
6 | Krishna | 30 | 6 | 2 |  |  |  |  | 4 |  |  |  |  | 26.39
7 | Guntur | 5 | 1 | 1 | [9 empty] | 4.41 | Requesting for New building as there is no space in the existing hospital.
8 | Prakasam | 35 | 7 | 3 | 1 | 3 | [5 empty] | 3 |  | 13.4 | For (6) works differed as there is no space in the existing hospitals. Village (Kapur) not found.
9 | Nellore | 20 | 4 |  |  | 1 |  |  | 3 |  |  | 1 |  | 16.6827
10 | Chittoor | 20 | 4 | 4 | [9 empty] | 15.34 | Requesting for new construction.
11 | Ananthapur | 25 | 5 | 5 | [9 empty] | 0 | Requesting for new construction.
12 | Kadapa | 5 | 1 | 1 | [9 empty] | 4.29 | Doctors are demanding for new construction.
13 | Kurnool | 10 | 2 | [5 empty] | 2 |  |  |  |  | 9.36
14 | Mahaboobnagar | 25 | 5 | 5 | [9 empty] | #REF! | Building dilapidated since not taken up.
15 | Ranga Reddy | 20 | 4 | 4 | [9 empty] | #REF! | Site not available.
16 | Nalgonda | 5 | 1 |  |  |  |  | 1 |  |  |  | 1 |  | #REF!
17 | Medak | 30 | 6 | 1 |  |  |  | 2 | 3 |  | 1 |  | 1 | #REF! | For one notice issued to the contractor to start the work and For one work Medical Officer not permitted to start the work.
18 | Nizamabad | 20 | 4 | 2 | 1 |  |  |  | 1 |  |  |  |  | #REF! | Not taken up since functioning in the existing CEMONC building.
19 | Warangal | 30 | 6 | [5 empty] | 6 |  |  |  |  | #REF!
20 | Khammam | 25 | 5 |  |  |  |  | 1 | 4 |  |  | 1 |  | #REF! | New building required.
21 | Karimnagar | 25 | 5 |  | 2 |  |  |  | 3 |  |  |  |  | #REF! | Buildings dilapidated so two works not taken up.
22 | Adilabad | 15 | 3 |  |  |  |  | 2 | 1 |  | 1 | 1 |  | #REF!
| TOTAL | 405 | 81 | 28 | 7 | 4 | 0 | 11 | 31 | 1 | 6 | 7 | 1 | #REF!
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## abs monthwise
MONTH WISE ABSTRACT
Construction of Community Health and Nutrition Cluster Offices (CHNCs) under NRHM for the year 2011-12
Sl.No. | District | AS / RAS amount (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up 6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other department/Scheme | Site problem | RAS awaited | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | SKLM | 10 | 7.06 |  | 2 |  |  |  | 0 | 2 | 2 |  |  | 2 |  | 2
2 | VZM | 15 | 13.85 |  | 3 |  |  |  | 0 | 3 | 3 |  |  | 3 |  | 3
3 | VSP | 10 | 3.467 |  | 2 | 1 |  |  | 1 | 1 | 1 |  |  | 1 |  | 1
4 | EG | 20 | 17.52 | 1.37 | 4 |  |  |  | 0 | 4 | 4 |  |  | 3 | 1 | 3 | 1
5 | WG | 5 | 1.78 |  | 1 |  |  | 1 | 1 | 0 | 0
6 | KRI | 30 | 26.39 |  | 6 |  |  |  | 0 | 6 | 6 |  |  | 6 |  | 6
7 | GNT | 5 | 4.41 | 0.59 | 1 |  |  |  | 0 | 1 | 1 |  |  |  | 1 | 1
8 | PKSM | 35 | 13.4 |  | 7 | 4 |  |  | 4 | 3 | 3 |  |  | 3 |  | 3
9 | NLR | 20 | 16.6827 |  | 4 |  |  |  | 0 | 4 | 4 |  |  | 4 |  | 4
10 | CTR | 20 | 15.34 |  | 4 | 1 |  |  | 1 | 3 | 3 |  |  | 3 |  | 3
11 | ATP | 25 | 0 |  | 5 | 5 |  |  | 5 | 0 | 0
12 | KDP | 5 | 4.29 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
13 | KNL | 10 | 9.36 |  | 2 |  |  |  | 0 | 2 | 2 |  |  | 2 |  | 2
| TOTAL | 210 | 133.5497 | 1.96 | 42 | 11 | 0 | 1 | 12 | 30 | 30 | 0 | 0 | 28 | 2 | 29 | 1

## details
Construction of Community Health and Nutrition Cluster Offices (CHNCs) under NRHM
Sl. No. | Name of District | Block/Manadal | Name of Centre | Date/Month of Work Sanctioned | Financial Progress |  | Name of Execution Agency | Physical Progress |  |  | Final bill |  | Building
[5 empty] | AS / RAS amount (Rs.in lakhs) | Expenditure (Rs in lakhs) |  | If complete - Date/ Month of Work Completion | If not completed - Stage of Progress | Tentative date of Completion | Paid | Not Paid | Handed Over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
DISTRICT : SRIKAKULAM
1 | SKLM | Ranasthalam | Ranasthalam | 09.12.2010 | 5 | 4.7 | Sri L.Prabhakarao | 16.3.13
2 | ..do.. | Kaviti | Kavity |  | 5 | 2.36 | Sri A.Sathyannarayana | 30.6.2013
|  |  | Sub-total |  | 10 | 7.06
DISTRICT : VIZIANAGARAM
3 | VZM | G L puram | Bhadragiri (Gummalakshmipuram) | 09.12.2010 | 5 | 4.14 | J.B.Chowdary | 15.12.11
4 | ..do.. | Chinamerangi | Chinamerangi |  | 5 | 5 | J.B.Chowdary | 19.05.12
5 | ..do.. | Kurupam | Kurupam |  | 5 | 4.71 | G.Appala Naidu | 15.12.11
|  |  | Sub-total |  | 15 | 13.85
DISTRICT : VISAKHAPATNAM
6 | VSP | Kotauratla | Kotauratla | 09.12.2010 | 5 | 3.467 | Sri P.N.V.Ramana | 15.10.11
7 | ..do.. |  | Munchingput |  | 5 |  |  |  | Taken up by Tribal Welfare Department.
|  |  | Sub-total |  | 10 | 3.467
DISTRICT : EAST GODAVARI
8 | EG | Yeleswaram | Yeleswaram | 09.12.2010 | 5 | 3.63 | M/s Bhavana Constructions | 31.08.2012 |  |  |  | NP |  | NH
9 | ..do.. | Gokavaram | Gokavaram |  | 5 | 4.63 | N. Srinivasa Rao, Yanam. | 03.04.2012
10 | ..do.. | Pitapuram | Pitapuram |  | 5 | 4.65 | M. Rambabu, Pithapuram. | 31.12.2011
11 | ..do.. | Peddapudi | Peddapudi |  | 5 | 4.61 | M/s The Babu SCLCCS | 30.11.2011
|  |  | Sub-total |  | 20 | 17.52
DISTRICT : WEST GODAVARI
12 | WG | Chintalapudi | Chintalapudi | 09.12.2010 | 5 | 1.78 | Sri KVSSS.Varma Raju | … | Roof slab laid and contract was terminated under 60(a).For balance work tender to be invited after RAS is received
|  |  | Sub-total |  | 5 | 1.78
DISTRICT : KRISHNA
13 | KRI | Guduru | Guduru | 09.12.2010 | 5 | 4.66 | Sri T.Saibaba | 22-2-2012.
14 | ..do.. | Mylavaram | Mylavaram |  | 5 | 3.85 | Sri N.Govinda Rao | 14-3-2013.
15 | ..do.. | Nuzvid | Nuzvid |  | 5 | 4.33 | Sri N.Govinda Rao | 30-4-2013.
16 | ..do.. | Tiruvvuru | Tiruvvuru |  | 5 | 4.65 | Sri N.Govinda Rao | 10-1-2012.
17 | ..do.. | Kaikalluru | Kaikalluru |  | 5 | 4.24 | M/s Anil constructions, MTM | 17-7-2012
18 | ..do.. | Kankipadu | Kankipadu |  | 5 | 4.66 | Sri N.Govinda Rao | 30-10-2011.
|  |  | Sub-total |  | 30 | 26.39
DISTRICT : GUNTUR
19 | GNT | Nagaram | Nagaram | 09.12.2010 | 5 | 4.41 | Sri J.Rajesh | 17-12-12 |  |  |  | no | yes
|  |  | Sub-total |  | 5 | 4.41
DISTRICT : PRAKASAM
20 | PKSM | Kapur | Kapur | 09.12.2010 | 5 |  | - |  | No such village in Prakasam District
21 | ..do.. | Ulavapadu | Ulavapadu |  | 5 | 4.33 | Sri.P.VenkataReddy | 25.9.2012
22 | ..do.. | Kanigiri | Kanigiri |  | 5 |  | - |  | Not feasible
23 | ..do.. | Yerragondapalem | Yerragondapalem |  | 5 |  | Sri.G.Venkateswarlu |  | Not feasible
24 | ..do.. | Podili | Podili |  | 5 | 4.55 | Sri S.Haranath Reddy | 15.11.2011 |  |  | Yes |  | Yes
25 | ..do.. | Giddaluru | Giddaluru | 09.12.2010 | 5 |  | - |  | Not feasible
26 | ..do.. | Pamuru | Pamuru |  | 5 | 4.52 | Sri.K.Ramesh | 31.7.2013
|  |  | Sub-total |  | 35 | 13.4
DISTRICT : NELLORE
27 | NLR | Alluru | Alluru | 09.12.2010 | 5 | 4.1291 | Y. Krishnaiah | 28-02-2012
28 | ..do.. | Vinjamuru | Vinjamuru |  | 5 | 3.7723 | SK. Muthahar Basha | 15-09-2013
29 | ..do.. | Venkatachalam | Venkatachalam |  | 5 | 4.0945 | Y. Krishnaiah | 30-03-2012
30 | ..do.. | Podalakuru | Podalakuru |  | 5 | 4.6868 | J. Pullaiah | 29-11-2011
|  |  | Sub-total |  | 20 | 16.6827
DISTRICT : CHITTOOR
31 | CTR | Vayalpadu | Vayalpadu | 09.12.2010 | 5 | 2.49 | Sri. M. Mallikarjuna Reddy | -- | Work stopped due to upgradation of CHC into 100 Bedded Hospital |  |  | np |  | nh
32 | ..do.. | Kalikiri | Kalikiri |  | 5 | 4.8 | Sri. N. Tirumala Prakasam | 30-07-2013
33 | ..do.. | Sathiveedu | Sathiveedu |  | 5 | 4.48 | Sri. B. Nagaraju | 31.12.2013
34 | ..do.. | Putturu | Putturu |  | 5 | 3.57 | Sri. D. Ganesh Kumar | 31.03.2014
|  |  | Sub-total |  | 20 | 15.34
DISTRICT : ANANTAPUR
35 | ATP | Penukonda | Penukonda | 09.12.2010 | 5 | 0 |  |  | Medical Officer's of the concerned were raised objection for renovation of the existing old building they are requested for new building.
36 | ..do.. | Kalyandurg | Kalyandurg |  | 5 | 0
37 | ..do.. | Raidurg | Raidurg |  | 5 | 0
38 | ..do.. | Kanekal | Kanekal |  | 5 | 0
39 | ..do.. | Madakasira | Madakasira |  | 5 | 0
|  |  | Sub-total |  | 25 | 0
DISTRICT : KADAPA
40 | YSR | Kamalapuram | Kamalapuram | 09.12.2010 | 5 | 4.29 | A.Venkata Subbaiah | 07.01.2013
|  |  | Sub-total |  | 5 | 4.29
DISTRICT : KURNOOL
41 | KNL | Orvakallu | Orvakallu | 09.12.2010 | 5 | 4.68 | B.Rami Reddy | 18.11.2011
42 | ..do.. | Yalluru | Yalluru |  | 5 | 4.68 | J.V.Narayana Reddy | 10.12.2011
|  |  | Sub-total |  | 10 | 9.36
|  |  | GRAND TOTAL |  | 210 | 133.5497
|  | Add establishment charges@ 7% |  |  |  | 9.3485
|  | TOTAL : |  |  |  | 142.8982