## covp
| Date: 02.02.2013 | Dt:19.01.2016
FRUs (First Referral Units) Grade - I & II Hospitals for the year 2012-13 Under NRHM

## abs
MONTH WISE ABSTRACT
FRUs (First Referral Units) Grade - I & II Hospitals for the year 2012-13 Under NRHM
Sl. No. | District | AS / RAS amount (Rs. in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up (6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other dept | Site problem | RAS awaited or etc | Total (7+8+9) |  | Completed | Work to be started | Works progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | Srikakulam | 59.5 | 35.11 |  | 6 |  |  |  |  | 6 | 6 |  |  | 6 |  | 6
2 | Vizianagaram | 79.42 | 72.31 |  | 6 |  |  |  |  | 6 | 6 |  |  | 6 |  | 6
3 | Visakhapatnam | 104 | 94.087 |  | 7 |  |  |  |  | 7 | 7 |  |  | 7 |  | 7
4 | East Godavari | 103.05 | 88.82 | 5.34 | 14 |  |  |  |  | 14 | 14 |  |  | 13 | 1 | 13 | 1
5 | West Godavari | 68 | 52.96 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
6 | Krishna | 19.5 | 12.32 |  | 3 |  |  |  |  | 3 | 3 |  |  | 3 |  | 3
7 | Guntur | 64.1 | 56.37 |  | 12 |  |  |  |  | 12 | 12 |  |  | 12 |  | 12
8 | Prakasam | 37.5 | 19.51 | 15.27 | 4 |  |  |  |  | 4 | 3 |  | 1 |  | 3 | 3 | 1
9 | Nellore | 31.01 | 26.25 |  | 4 |  |  |  |  | 4 | 4 |  |  | 4 |  | 4
10 | Chittoor | 74.6 | 58.85 | 0.5 | 6 |  |  |  |  | 6 | 6 |  |  | 6 | 1 | 6
11 | Ananthapur | 52.92 | 44.98 |  | 7 |  |  |  |  | 7 | 7 |  |  | 7 |  | 7
12 | Kadapa | 212 | 111.16 | 15.4 | 6 |  |  |  |  | 6 | 5 | 1 |  | 5 | 1 | 5 | 1
13 | Kurnool | 100.7 | 51.89 | 41.63 | 16 |  |  |  |  | 16 | 15 | 1 |  | 15 | 1 | 15 | 1
| TOTAL | 1006.3 | 724.617 | 78.14 | 92 | 0 | 0 | 0 | 0 | 92 | 89 | 2 | 1 | 85 | 7 | 88 | 4

## 249 list(civil&equip)
FRUs (First Referral Units) Grade - I & II Hospitals for the year 2012-13 Under NRHM
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
SRIKAKULAM
1 | SKLM |  | AH Tekkali | 17.05.2012 | 0.5 | 0.44 | Sri Ch.Venkatarao | 06.01.2013
2 | -do- | Rajam | AH Rajam |  | 1 | 0.87 | Sri T.Govinda Reddy | 13.3.2013.
3 | -do- | Palasa | CHC Palasa |  | 8 | 7.4 | Sri Y.Srinivas Rao | 30.6.2013
4 | -do- | Narasannapeta | CHC Narasannapeta |  | 5 | 4.63 | Sri K.V.Ramana | 16.3.2013.
5 | -do- | Sompeta | CHC Sompeta |  | 5 | 4.61 | Sri Y.Srinivas Rao | 29.01.2013.
6 | -do- | Kotturu | CHC Kotturu |  | 40 | 17.16 | Sri K.Ganapathi Rao | 31.07.2015
7 | -do- |  | AH Palakonda |  | 0
8 | -do- |  | CHC Pathapatnam (T) |  | 0
9 | -do- |  | CHC Ichchapuram |  | 0
10 | -do- |  | CHC Seethampeta (T) |  | 0
|  |  | Sub-total |  | 59.5 | 35.11
VIZIANAGARAM
11 | VZM | Bobbili | CHC Bobbili | 17.05.2012 | 8.4 | 8.32 | J.B.Chowdary, Contractor, Bobbili, | 28.02.13
12 | -do- | Bhogapuram | CHC Bhogapuram |  | 34.42 | 30.31 | Ch.Suryanarayana, | 30.07.13
13 | -do- | Gajapathinagaram | CHC Gajapathinagaram |  | 6.5 | 5.39 | G.Appala Naidu, | 30.04.13
14 | -do- | Cheepurupalli | CHC Cheepurupalli |  | 3.3 | 3.22 | Sri K.Chandra Naidu, | 15.06.13
15 | -do- | Saluru | CHC Saluru |  | 5.6 | 5.57 | G.Rama krishan, | 30.06.13
16 | -do- | Kurupam | CHC Kurupam |  | 21.2 | 19.5 | B.Lokanadam | 30.06.14
17 | -do- |  | AH S Kota |  | 0
18 | -do- |  | AH Parvathipuram |  | 0
|  |  | Sub-total |  | 79.42 | 72.31
VISAKHAPATNAM
19 | VSKP | Gajuwaka | CHC Aganampudi | 17.05.2012 | 4 | 3.71 | M/s Surya Associates | 04.11.12
20 | -do- | K.Kotapadu | CHC K.Kotapadu |  | 7 | 5.58 | Sri A.V.G.Jagganadha Rao, | 20.11.12
21 | -do- | Araku | CHC Araku |  | 13 | 12.03 | Sri T.Jaya Krishna | 14.02.13
22 | -do- | Chintapalli | CHC Chintapalli |  | 40 | 35.75 | Sri T.Eswara Rao, | 31.12.2014
23 | -do- | Bheemunipatnam | CHC Bheemunipatnam |  | 5 | 4.637 | Sri M.Pydi Raju, | 02.01.13
24 | -do- | Chodavaram | CHC Chodavaram |  | 30 | 27.74 | Sri A.V.G.Jagannadha Rao | 31.01.2014
25 | -do- | Yellamanchili | CHC Yellamanchili |  | 5 | 4.64 | Sri K.A.Rama Rao, | 08.11.12
26 | -do- |  | AH Anakapalli |  | 0 |  |  |  | --
27 | -do- |  | AH Narsipatnam |  | 0 |  |  |  | --
28 | -do- |  | CHC Paderu |  | 0 |  |  |  | --
29 | -do- |  | CHC Munchingput |  | 0 |  |  |  | --
30 | -do- |  | CHC Nakkapalli |  | 0 |  |  |  | --
|  |  | Sub-total |  | 104 | 94.087
EAST GODAVARI
31 | EG | Rajahmundry | DH Rajahmundry | 17.05.2012 | 7 | 6.35 | Sri S. Harinadha Rao, | 30.06.2013
32 | -do- | Amalapuram | AH Amalapuram |  | 5 | 4.67 | Sri P.R.K. Varma, | 30.04.2013
33 | -do- | Ramachandra puram | AH R.C. Puram |  | 5.1 | 3.73 | M/s Sitha ramanjaneya | 30.04.2013
34 | -do- | Tuni | AH Tuni |  | 8 | 7.24 | N. Prasada Rao | 30.04.2013
35 | -do- | Peddapuram | AH Peddapuram |  | 15 | 13.91 | Sri Y. Prakasa Rao, | 30.10.2013
36 | -do- | Prathipadu | CHC Prathipadu |  | 5 | 4.67 | N. Prasada Rao | 30.04.2013
37 | -do- | Razole | AH Razole |  | 6 | 5.05 | M/s Sitha ramanjaneya Constructions | 30.04.2013
38 | -do- | Kothapeta | AH Kothapeta |  | 6 | 5.51 | B. Krishna Rao | 30.04.2013
39 | -do- | Tallarevu | CHC Tallarevu |  | 4 | 3.74 | M/s Sitha ramanjaneya Constructions | 30.04.2013
40 | -do- | Pithapuram | CHC Pithapuram |  | 7.95 | 7.42 | V. Srinivasa Rao | 30.06.2013
41 | -do- | Jaggampeta | CHC Jaggampeta |  | 9 | 3.66 | M/s Navanirman Techno. Build, Hyd. | 30.06.2013 |  |  | NP | Building Handed Over r Not....
42 | -do- | Sankhavaram | CHC Rowthulapudi |  | 10 | 9.33 | M/s Navanirman Techno. Build, | 31.10.2013
43 | -do- | Kadiyam | CHC Kadiyam |  | 10 | 8.88 | Sri S. Harinadha Rao, | 31.10.2013
44 | -do- | Kapileswara puram | CHC Kapileswarapuram |  | 5 | 4.66 | Sri P.R.K. Varma | 30.04.2013
45 | -do- |  | Rampachodavaram |  | 0
46 | -do- |  | Addateegala |  | 0
|  |  | Sub-total |  | 103.05 | 88.82
WEST GODAVARI
47 | WG | Bhimadole | CHC Bhimadolu | 17.05.2012 | 68 | 52.96 | M/s. Sachin build Tech., Vizag | 30.06.2014
48 | -do- |  | CHC Narsapur |  | 0 |  |  |  | --
49 | -do- |  | CHC Palakollu |  | 0 |  |  |  | --
50 | -do- |  | CHC Bhimavaram |  | 0 |  |  |  | --
51 | -do- |  | CHC Kovvuru |  | 0 |  |  |  | --
52 | -do- |  | CHC Chintalapudi |  | 0 |  |  |  | --
53 | -do- |  | AH Tanuku |  | 0 |  |  |  | --
54 | -do- |  | AH Tadepalligudem |  | 0 |  |  |  | --
55 | -do- |  | AH Jangareddygudem |  | 0 |  |  |  | --
56 | -do- |  | DH Eluru |  | 0 |  |  |  | --
57 | -do- |  | CHC Akiveedu |  | 0 |  |  |  | --
|  |  | Sub-total |  | 68 | 52.96
KRISHNA
58 | KRI | Machilipatnam | DH Machilipatnam | 17.05.2012 | 8 | 4.69 | Ch.Thimma Raju | 24-10-2013
59 | -do- | Avanigadda | AH Avanigadda |  | 5.5 | 4.18 | J.Rajesh, | 14-01-2013
60 | -do- | Gudiwada | AH Gudivada |  | 6 | 3.45 | Sri Ch.Ravisree babu, | 28-09-2013
61 | -do- |  | AH Nuzividu |  | 0 |  |  |  | --
62 | -do- |  | AH Nandigama |  | 0 |  |  |  | --
63 | -do- |  | CHC Kankipadu |  | 0 |  |  |  | --
64 | -do- |  | CHC Mylavaram |  | 0 |  |  |  | --
65 | -do- |  | CHC Vuyyur |  | 0 |  |  |  | --
66 | -do- |  | CHC Kaikaluru |  | 0 |  |  |  | --
67 | -do- |  | CHC Jaggaipet |  | 0 |  |  |  | --
68 | -do- |  | CHC Challapalli |  | 0 |  |  |  | --
69 | -do- |  | AH Thiruvuru |  | 0 |  |  |  | --
70 | -do- |  | CHC Vissannapet |  | 0 |  |  |  | --
71 | -do- |  | CHC Gannavaram |  | 0 |  |  |  | --
|  |  | Sub-total |  | 19.5 | 12.32
GUNTUR
72 | GNT | Bapatla | AH Bapatla | 7.05.2012 | 5 | 4.65 | Sri K.Murali Krishna | 25-4-2013
73 | -do- | Narasaroapet | AH Narsaraopeta |  | 5 | 4.69 | Sri M.Yeleswara Reddy. | 22-2-2013
74 | -do- | Sattenapalli | CHC Sattenapally |  | 3 | 2.65 | Sri T.Govinda Reddy. | 31-7-2013
75 | -do- | Chilakaluripet | CHC Chilkaluripeta |  | 5 | 4.84 | Sri K.Srinivasa Rao. | 04.04.2013
76 | -do- | Macherla | CHC Macherla |  | 5 | 4.69 | Sri A.Chenna Kesava Reddy | 08.03.2012
77 | -do- | Vinukonda | CHC Vinukonda |  | 4.1 | 3.79 | Sri M.Yeleswara Reddy. | 9.01.2013
78 | -do- | Tenali | DH Tenali |  | 5 | 4.68 | Sri K.Poornachandra Rao | 8.02.2013
79 | -do- | Nizampatnam | CHC Nizampatnam |  | 5 | 4.63 | Sri N.Bala Kotaiah. | 41308
80 | -do- | Ponnuru | CHC Ponnuru |  | 5 | 4.65 | Sri N.Bala Kotaiah. | 18-1-13
81 | -do- | Peddakurapadu | CHC Peddakurapadu |  | 10 | 9.36 | Sri K.Poornachandra Rao | 41369
82 | -do- | Ipur | CHC Ipur |  | 2 | 1.85 | Sri T.Govinda Reddy. | 18-7-13
83 | -do- | Gurajala | CHC Gurajala |  | 10 | 5.89 | Sri A.Chenna Kesava Reddy | 31-7-2013
84 | -do- |  | CHC Repally |  | 0
85 | -do- |  | CHC Amaravathi |  | 0
86 | -do- |  | CHC Nagaram |  | 0
87 | -do- |  | CHC Prathipadu |  | 0
|  |  | Sub-total |  | 64.1 | 56.37
PRAKASAM
88 | PKSM | Markapuram | AH Markapuram | 17.05.2012 | 3.5 | 1.49 | Sri.V.S.RamiReddy | 30.06.2014 |  |  | NP |  | 2.01
89 | -do- | Chirala | AH Chirala |  | 13 | 10.28 | Sri.S.V.Koteswararao | 31.7.2013
90 | -do- | Kanigiri | CHC Kanigiri |  | 8 | 2.74 | Sri P.Venkata Reddy | 31.5.2013 |  |  | NP | Handed Over | 5.26
91 | -do- | Cumbum | CHC Cumbum |  | 13 | 5 | Sri G.Ravi & Sri.B.Venkata Ramana Reddy, | - | Super structure is in progress | 29.02.2016 |  |  | 8
92 | -do- |  | AH Kandukuru |  | 0 |  |  |  | --
93 | -do- |  | CHC Giddaluru |  | 0 |  |  |  | --
|  |  | Sub-total |  | 37.5 | 19.51
NELLORE
94 | NLR | Nellore | DH Nellore | 17.05.2012 | 5 | 4.34 | S. Sandani Basha, Nellore | 01.03.2013
95 | -do- | Gudur | AH Gudur |  | 7.01 | 6.52 | V. Mallikarjuna | 18.12.2012
96 | -do- | Kavali | AH Kavali |  | 2 | 1.57 | D. Ayyappa Reddy | 29.12.2012
97 | -do- | Nellore | MCH Nellore (jubilee Hospital) |  | 17 | 13.82 | Laxmi Prasuna Constructions, | 30.06.2013
98 | -do- |  | CHC Udayagiri |  | 0 |  |  |  | --
99 | -do- |  | CHC Venkatagiri |  | 0 |  |  |  | --
100 | -do- |  | CHC Naidupeta |  | 0 |  |  |  | --
101 | -do- |  | CHC Kota |  | 0 |  |  |  | --
102 | -do- |  | CHC Sullurpeta |  | 0 |  |  |  | --
|  |  | Sub-total |  | 31.01 | 26.25
CHITTOOR
103 | CTR | Kuppam | AH Kuppam | 17.05.2012 | 1.7 | --- | M/s. Sumasree Constructions | 13.04.2014
104 | -do- | Madanapalli | AH Madanapalli |  | 59.5 | 47.54 | Sri. S. Subramanya Reddy | 30-05-14
105 | -do- | Puttur | CHC Puttur |  | 0.4 | 0.37 | Sri. B. Nagaraju | work completed
106 | -do- | Srikalahasti | AH Srikalahasti |  | 5 | 3.86 | Sri. Y. Bhuvn Kumar | 15.11.2013
107 | -do- | Kalikiri | CHC Kalikiri |  | 0.5 | --- | Sri. M.Mallikharjuna Reddy | 15.11.2013 |  |  | NP
108 | -do- |  | AH Palamaneru |  | 0 | ---
109 | -do- | Nagari | AH Nagari |  | 7.5 | 7.08 | Sri. Y. Bhuvn Kumar | 20-05-2013
110 | -do- |  | AH Piler |  | 0
111 | -do- |  | DH Chittoor |  | 0
112 | -do- |  | CHC Bangarupalem |  | 0
|  |  | Sub-total |  | 74.6 | 58.85
ANANTAPUR
113 | ATP | Penukonda | AH Penukonda | 17.05.2012 | 16 | 13.3 | Sri.P.Muthyalappa | 2-6-2013
114 | -do- | Dharmavaram | AH Dharmavarm |  | 20 | 16 | Sri.B.Muthyalappa. | 4-6-2013
115 | -do- | Nallamada | CHC Nallamada |  | 7.5 | 6.81 | K.Lakshmi Reddy | 5-6-2013
116 | -do- |  | CHC Tadipatri |  | 0.7 | 0.65 | Sri.S.Amzad Hussain | Work Completed
117 | -do- |  | CHC Rayadurg |  | 1.36 | 1.33 | Sri.T.Obilesu | Work Completed
118 | -do- |  | CHC Konakondla |  | 3.36 | 3.15 | Sri.N.Balakrishna | Work Completed
119 | -do- |  | DH Hindupur |  | 4 | 3.74 | Sri.P.Muthyalappa | Work Completed
120 | -do- |  | CHC Pamidi |  | 0 |  |  |  | --
121 | -do- |  | CHC Tanakal |  | 0 |  |  |  | --
122 | -do- |  | CHC Singanamala |  | 0 |  |  |  | --
123 | -do- |  | CHC Uravakonda |  | 0 |  |  |  | --
124 | -do- |  | AH Gooty |  | 0 |  |  |  | --
125 | -do- |  | AH Madakasira |  | 0 |  |  |  | --
126 | -do- |  | AH Kadiri |  | 0 |  |  |  | --
127 | -do- |  | AH Guntakal |  | 0 |  |  |  | --
|  |  | Sub-total |  | 52.92 | 44.98
KADAPA
128 | YSR |  | DH Proddutur | 17.05.2012 | 0 |  |  |  | --
129 | -do- | Rayachoti | CHC Rayachoti |  | 3 | 2.37 | S.Abdul Shukur | work completed and final bill paid
130 | -do- | Rajampet | CHC Rajampet |  | 50 | 42.67 | N.prakash. | work completed & Final bill paid
131 | -do- | Jammalamadugu | CHC Jammalamadugu |  | 7 | 2.31 | B.Narasimha Reddy | completed
132 | -do- | Vempalli | CHC Vempalli |  | 2 | 1.43 | S.P.Jayachandra reddy | completed
133 | -do- | Badvel | CHC Badvel |  | 57 | 41.6 | V.Raja Gopal Reddy |  | Work started & stopped due to HT lines passed over the building. 1st agency closed. Tenders are invited for the balance work |  |  | 15.4
[5 empty] | 70 |  |  |  | Tender Process is in progress
134 | -do- | Lakkireddypalli | CHC Lakkireddypalli |  | 23 | 20.78 | T.maheswara Reddy | 30.11.2013
|  |  | Sub-total |  | 212 | 111.16
KURNOOL
135 | KNL | Adoni | MCH Adoni | 17.05.2012 | 6.5 | 6.08 | G.Sanjay | 05.01.2013
136 | -do- | Nandyala | DH Nandyala |  | 3.5 | 3.2 | O.Veera Reddy | 24.12.2012
137 | -do- | Allagadda | CHC Allagadda |  | 9.3 | 6.1 | E.Viswanath Reddy | 25.01.2013
138 | -do- | Alur | CHC Alur |  | 8.45 | 7.92 | K.Sreedhar Reddy | 30.07.2013
139 | -do- | Atmakur | CHC Atmakur |  | 2.5 | 2.24 | M/s Yerragudur Vadde | 07.01.2013
140 | -do- | Banaganapalli | CHC Banaganipalli |  | 2.5 | 2.31 | O.Veera Reddy | 24.01.2013
141 | -do- | Dhone | CHC Dhone |  | 2.5 | 2.19 | Jayaramudu | 01.02.2013
142 | -do- | Kodumur | CHC Kodumur |  | 2.5 | 2.33 | M.Mahaboob Baig | 29.01.2013
143 | -do- | Koilakuntlka | CHC Koilakuntla |  | 3 | 2.79 | N.Mahesh | 24.01.2013
144 | -do- | Nandikotkur | CHC Nandikotkur |  | 2.5 | 2.31 | N.Venugopal Reddy | 28.01.2013
145 | -do- | Panyam | CHC Panyam |  | 42 | 0.37 |  |  | Site recently finalized & tenders to be invited
146 | -do- | Pathikonda | CHC Pathikonda | 17.05.2012 | 3 | 2.48 | M.Mahaboob Baig | 02.02.2013
147 | -do- | Sundipenta | CHC Sunnipenta |  | 3 | 2.81 | S.Deva Raju | 01.02.2013
148 | -do- | Veldurthi | CHC Veldurthi |  | 2 | 1.87 | G.Ramanjaneyulu | 18.01.2013
149 | -do- | Velugodu | CHC Velugodu |  | 0.5 | 0.46 | M.Sekhar | 30.01.2013
150 | -do- | Yemmiganur | CHC Yemmiganur |  | 6.95 | 6.43 | V.Krishna | 22.01.2013
151 | -do- |  | CHC Midthur |  | 0 |  |  |  | --
152 | -do- |  | CHC Orvakallu |  | 0 |  |  |  | --
|  |  | Sub-total |  | 100.7 | 51.89
|  |  | Grand total |  | 1006.3 | 724.617
|  | Add establishment charges@ 7% |  |  |  | 50.7232
|  | TOTAL : |  |  |  | 775.3402

## civil (hidden)
FRUs (First Referral Units) Grade - I & II Hospitals for the year 2012-13 Under NRHM
Sl. No. | Name of the Location | Administrative Sanction Reference No. | Administrative sanction (civil) (Rs.in lakhs) | Exepnditure (Rs.in lakhs) | Stage of work | Expected date of comletion
SRIKAKULAM
1 | AH Tekkali | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 0.5 |  | Work is in progress. | 30.11.2012
2 | AH Rajam |  | 1 |  | Work is in progress. | 30.11.2012
3 | CHC Palasa |  | 8 |  | Work is in progress. | 30.11.2012
4 | CHC Narasannapeta |  | 5 |  | Work is in progress. | 30.11.2012
5 | CHC Sompeta |  | 5 |  | Work is in progress. | 30.11.2012
6 | CHC Kotturu |  | 40 |  | Tenders being invited.
| Sub-total |  | 59.5
VIZIANAGARAM
7 | CHC Bobbili | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 8.4 |  | Work to be started.
8 | CHC Bhogapuram |  | 34.42 |  | Tenders invited.
9 | CHC Gajapathinagaram |  | 6.5 |  | Work to be started.
10 | CHC Chipurpally |  | 3.3 |  | Work to be started.
11 | CHC Saluru |  | 5.6 |  | Work to be started.
12 | CHC Kurupam |  | 21.2 |  | Tenders invited.
| Sub-total |  | 79.42
VISAKHAPATNAM
13 | CHC Aganampudi | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 4 |  | Work is in progress. | 30.11.2012
14 | CHC K.Kotapadu |  | 7 |  | Work to be started.
15 | CHC Araku |  | 13 |  | Tender is in progress.
16 | CHC Chintapalli |  | 40 |  | Tender is in progress.
17 | CHC Bheemunipatnam |  | 5 |  | Work is in progress. | 30.11.2012
18 | CHC Chodavaram |  | 30 |  | Tender is in progress.
19 | CHC Yellamanchili |  | 5 |  | Work is in progress. | 30.11.2012
| Sub-total |  | 104
EAST GODAVARI
20 | DH Rajahmundry | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 7 |  | Tenders opening on 16.10.2012.
21 | AH Amalapuram |  | 5 |  | Tenders opening on 16.10.2012.
22 | AH R.C. Puram |  | 5.1 |  | Tenders opening on 16.10.2012.
23 | AH Tuni |  | 8 |  | Tenders opening on 16.10.2012.
24 | AH Peddapuram |  | 15 |  | Tenders opening on 16.10.2012.
25 | CHC Prathipadu |  | 5 |  | Tenders opening on 16.10.2012.
26 | AH Razole | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 6 |  | Tenders opening on 16.10.2012.
27 | AH Kothapeta |  | 6 |  | Tenders opening on 16.10.2012.
28 | CHC Tallarevu |  | 4 |  | Tenders opening on 16.10.2012.
29 | CHC Pithapuram |  | 7.95 |  | Tenders opening on 16.10.2012.
30 | CHC Jaggampeta |  | 9 |  | Tenders opening on 16.10.2012.
31 | CHC Rowthulapudi |  | 10 |  | Tenders opening on 16.10.2012.
32 | CHC Kadiyam |  | 10 |  | Tenders opening on 16.10.2012.
33 | CHC Kapileswarapuram |  | 5 |  | Tenders opening on 16.10.2012.
| Sub-total |  | 103.05
WEST GODAVARI
34 | CHC Bhimadolu | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 68 |  | Tenders to be invited in HO
| Sub-total |  | 68
KRISHNA
35 | DH Machilipatnam | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 8 |  | Tender is in progress.
36 | AH Avanigadda |  | 5.5 |  | Tender is in progress.
37 | AH Gudivada |  | 6 |  | Tender is in progress.
| Sub-total |  | 19.5
GUNTUR
38 | AH Bapatla | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 5 |  | Tender invited.
39 | AH Narsaraopeta |  | 5 |  | Tender invited.
40 | CHC Sattenapally |  | 3 |  | Tender invited.
41 | CHC Chilkaluripeta |  | 5 |  | Tender invited.
42 | CHC Macherla |  | 5 |  | Tender invited.
43 | CHC Vinukonda |  | 4.1 |  | Tender invited.
44 | DH Tenali |  | 5 |  | Tender invited.
45 | CHC Nizampatnam |  | 5 |  | Tender invited.
46 | CHC Ponnuru |  | 5 |  | Tender invited.
47 | CHC Peddakurapadu |  | 10 |  | Tender invited.
48 | CHC Ipur |  | 2 |  | Tender invited.
49 | CHC Gurajala |  | 10 |  | Tender invited.
| Sub-total |  | 64.1
PRAKASAM
50 | AH Markapuram | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 3.5 |  | Tenders are finalized
51 | AH Chirala |  | 13 |  | Tenders invited.
52 | CHC Kanigiri |  | 8 |  | Tenders invited.
53 | CHC Cumbum |  | 13 |  | Tenders invited.
| Sub-total |  | 37.5
NELLORE
54 | DH Nellore | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 5 |  | Alternate proposal sought.
55 | AH Gudur |  | 7.01 |  | Tender process is in progress.
56 | AH Kavali |  | 2 |  | Work is in progress. | 31.10.2012
57 | MCH Nellore |  | 17 |  | Estimates under preparation.
| Sub-total |  | 31.01
CHITTOOR
58 | AH Kuppam | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 1.7 |  | Tenders being invited.
59 | AH Madanapalli |  | 59.5 |  | Tenders being invited in Head Office.
60 | CHC Puttur |  | 0.4 |  | Tenders being invited.
61 | AH Srikalahasti |  | 5 |  | Tenders being invited.
62 | CHC Kalikiri |  | 0.5 |  | Tenders being invited.
63 | AH Nagari |  | 7.5 |  | --
| Sub-total |  | 74.6
ANANTAPUR
64 | AH Penukonda | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 16 |  | Estimates under preparation.
65 | AH Dharmavarm |  | 20 |  | Estimates under preparation.
66 | CHC Nallamada |  | 7.5 |  | Estimates under preparation.
67 | CHC Tadipatri |  | 0.7 |  | Estimates under preparation.
68 | CHC Rayadurg |  | 1.36 |  | Estimates under preparation.
69 | CHC Konakondla |  | 3.36 |  | Estimates under preparation.
70 | DH Hindupur |  | 4 |  | Estimates under preparation.
| Sub-total |  | 52.92
KADAPA
71 | CHC Rayachoti |  | 3 |  | Tenders finalized on 15.10.2012.
72 | CHC Rajampet |  | 50 |  | Tenders being invited in Head Office.
73 | CHC Jammalamadugu |  | 7 |  | Work to be started.
74 | CHC Vempalli |  | 2 |  | Work to be started.
75 | CHC Badvel |  | 127 |  | Tenders being invited in Head Office.
76 | CHC Lakkireddypalli |  | 23 |  | Tender is in progress.
| Sub-total |  | 212
KURNOOL
77 | MCH Adoni | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 6.5 |  | Tender will be finalized on 15.10.2012.
78 | DH Nandyala |  | 3.5 |  | Tender will be finalized on 15.10.2012.
79 | CHC Allagadda |  | 9.3 |  | Tender will be finalized on 15.10.2012.
80 | CHC Alur |  | 8.45 |  | Tender will be finalized on 15.10.2012.
81 | CHC Atmakur |  | 2.5 |  | Tender will be finalized on 15.10.2012.
82 | CHC Banaganipalli |  | 2.5 |  | Tender will be finalized on 15.10.2012.
83 | CHC Dhone |  | 2.5 |  | Tender will be finalized on 15.10.2012.
84 | CHC Kodumur |  | 2.5 |  | Tender will be finalized on 15.10.2012.
85 | CHC Kovelakuntla |  | 3 |  | Tender will be finalized on 15.10.2012.
86 | CHC Nandikotkur |  | 2.5 |  | Tender will be finalized on 15.10.2012.
87 | CHC Panyam |  | 42 |  | Tender will be finalized on 15.10.2012.
88 | CHC Pathikonda |  | 3 |  | Tender will be finalized on 15.10.2012.
89 | CHC Sunnipenta |  | 3 |  | Tender will be finalized on 15.10.2012.
90 | CHC Veldurthi |  | 2 |  | Tender will be finalized on 15.10.2012.
91 | CHC Velugodu | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 0.5 |  | Tender will be finalized on 15.10.2012.
92 | CHC Yemmiganur |  | 6.95 |  | Tender will be finalized on 15.10.2012.
| Sub-total |  | 100.7
MAHABOOBNAGAR
93 | DH Mahaboobnagar | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 10 |  | Work is in progress. | 30.11.2012
94 | AH Gadwal |  | 3.5 |  | Work is in progress. | 30.11.2012
95 | AH Nagarkurnool |  | 4.8 |  | Work is in progress. | 20.10.2012
96 | AH Wanaparthy |  | 2.5 |  | Work is in progress. | 30.11.2012
97 | AH Narayanpet |  | 4.5 |  | Work is in progress. | 20.10.2012
98 | CHC Kalwakurthy |  | 8.5 |  | Work is in progress. | 30.11.2012
99 | CHC Badepally |  | 4.5 |  | Work is in progress. | 30.11.2012
100 | CHC Shadnagar |  | 4.5 |  | Work is in progress. | 20.10.2012
101 | CHC Maktal |  | 2.5 |  | Work is in progress. | 20.10.2012
102 | CHC Atmakur |  | 4.5 |  | Work is in progress. | 30.11.2012
103 | CHC Kodangal |  | 2 |  | Work is in progress. | 20.10.2012
104 | CHC Palem |  | 3.5 |  | Work is in progress. | 30.11.2012
105 | CHC kosigi |  | 4.5 |  | Work is in progress. | 20.10.2012
106 | CHC Kollapur |  | 2.5 |  | Work is in progress. | 30.11.2012
107 | CHC Achampet (T) |  | 2.5 |  | Work is in progress. | 20.10.2012
| Sub-total |  | 64.8
RANGAREDDY
108 | DH Tandur | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 7 |  | Tenders being invited.
109 | AH Kondapur |  | 2.85 |  | Work is in progress. | 30.11.2012
110 | CHC Vikarabad |  | 1.5 |  | Work is in progress. | 30.11.2012
111 | CHC Hayathnagar |  | 2.5 |  | Work is in progress. | 30.11.2012
| Sub-total |  | 13.85
NALGONDA
112 | DH Nalgonda | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 30 |  | Tender is in process.
113 | AH Miryalguda |  | 41.25 |  | Tender is in process.
114 | AH Huzurnagar |  | 8 |  | Tender is in process.
115 | AH Suryapet |  | 5 |  | Tender is in process.
116 | AH Nagarjunasagar |  | 6.35 |  | Tender is in process.
117 | AH Devarakonda |  | 12.15 |  | Tender is in process.
118 | AH Bhongari |  | 4.35 |  | Tender is in process.
119 | AH Ramannapet |  | 8 |  | Tender is in process.
120 | CHC Kodad |  | 20 |  | Tender is in process.
121 | CHC Choutuppal |  | 12.5 |  | Tender is in process.
| Sub-total |  | 147.6
MEDAK
122 | AH Zaheerabad | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 1.2 |  | Estimates under preparation.
123 | AH Medak |  | 1 |  | Estimates under preparation.
124 | MCH Siddipet |  | 5 |  | Estimates under preparation.
125 | DH Sangareddy |  | 1.5 |  | Estimates under preparation.
126 | CHC Jogipet | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 1 |  | Estimates under preparation.
127 | CHC Narayankhed |  | 2.5 |  | Estimates under preparation.
128 | CHC Narsapur |  | 2 |  | Estimates under preparation.
129 | CHC Gajwel |  | 2.5 |  | Estimates under preparation.
130 | CHC Sadasivpet |  | 2.5 |  | Estimates under preparation.
131 | CHC Ramayampet |  | 2.5 |  | Estimates under preparation.
| Sub-total |  | 21.7
NIZAMABAD
132 | DH Nizambad | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 2 |  | Estimates under preparation.
133 | CHC Varni |  | 9.29 |  | -do-
134 | CHC Dichpally |  | 3.5 |  | -do-
135 | AH Kamareddy |  | 3 |  | -do-
136 | AH Bodhan |  | 2 |  | -do-
137 | CHC Yellareddy |  | 1.5 |  | -do-
138 | CHC Balkonda |  | 22.5 |  | -do-
139 | CHC Bichkunda |  | 10 |  | -do-
140 | CHC Pitlam |  | 10 |  | -do-
141 | CHC Gandhari |  | 4.4 |  | -do-
| Sub-total |  | 68.19
WARANGAL
142 | DH Janagaon | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 14.5 |  | Estimates under preparation.
143 | AH Mahbubabad |  | 10 |  | -do-
144 | CHC Mulugu |  | 7 |  | -do-
145 | CHC Narsampet |  | 12 |  | -do-
146 | CHC Eturunagaram |  | 20 |  | -do-
| Sub-total |  | 63.5
KHAMMAM
147 | AH Sathupalli | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 5 |  | Tender being finalized.
148 | AH Bhadrachalam |  | 5 |  | Tender being finalized.
149 | AH Kothagudem |  | 5 |  | Tender being finalized.
150 | DH Khammam |  | 10 |  | Tender being finalized.
151 | AH Palvancha |  | 5 |  | Tender being finalized.
152 | CHC Penubally |  | 4 |  | Tender being finalized.
153 | CHC Venkatapuram |  | 3 |  | Tender being finalized.
154 | CHC Kunavaram |  | 2 |  | Tender being finalized.
155 | CHC Madhira |  | 3 |  | Tender being finalized.
156 | CHC Yellandu |  | 3 |  | Tender being finalized.
157 | CHC Chinturu |  | 2 |  | Tender being finalized.
| Sub-total |  | 47
KARIMNAGAR
158 | DH Karimnagar | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 2 |  | Tenders process is in progress.
159 | AH Jagithyal |  | 1 |  | Tenders process is in progress.
160 | AH Siricilla |  | 5 |  | Tenders process is in progress.
161 | AH Godavarikani |  | 5 |  | Tenders process is in progress.
162 | CHC Huzurabad | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 8 |  | Tenders process is in progress.
163 | CHC Peddapalli |  | 5 |  | Tenders process is in progress.
164 | CHC Korutla |  | 4 |  | Tenders process is in progress.
165 | CHC Mulkanoor |  | 4 |  | Tenders process is in progress.
166 | CHC Jammikunta |  | 5 |  | Tenders process is in progress.
167 | CHC Gambhiraopet |  | 5 |  | Tenders process is in progress.
168 | CHC Vemulawada |  | 4 |  | Tenders process is in progress.
169 | CHC Hansabad |  | 7 |  | Tenders process is in progress.
170 | CHC Rayakal |  | 7.5 |  | Tenders process is in progress.
171 | CHC Metpally |  | 5 |  | Tenders process is in progress.
172 | CHC Mahadevpur |  | 5 |  | Tenders process is in progress.
173 | CHC Manthani |  | 8.5 |  | Tenders process is in progress.
| Sub-total |  | 81
ADILABAD
174 | AH Mancherial | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 12.05 |  | Tender is in progress.
175 | MCH Nirmal |  | 10.5 |  | Estimates under preparation.
176 | CHC Sirpur T |  | 1.5 |  | Tender is in progress.
177 | AH Bhainsa |  | 5.85 |  | LOA issued.
178 | CHC Utnoor |  | 10.65 |  | Tender is in progress.
179 | CHC Asifabad |  | 17.25 |  | Transimitted to ITDA Dept.
180 | CHC Jainoor |  | 5.5 |  | Tender is in progress.
181 | CHC Boath |  | 39.85 |  | Tender is in progress.
| Sub-total |  | 103.15
| Grand total |  | 1617.09

## equip (hidden)
FRUs (First Referral Units) Grade - I & II Hospitals for the year 2012-13 Under NRHM
Sl. No. | Name of the Location | Administrative Sanction Reference No. | Admin. sanction Equipment (Rs.in lakhs) | Exepnditure (Rs.in lakhs) | Stage of work | Expected date of comletion
SRIKAKULAM
1 | AH Tekkali | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 0.489
2 | AH Rajam |  | 0.281
3 | CHC Palasa |  | 0.873
4 | CHC Narasannapeta |  | 0.905
5 | CHC Sompeta |  | 0.513
6 | CHC Kotturu |  | 3.679
7 | AH Palakonda |  | 2.239
8 | CHC Pathapatnam (T) |  | 0.232
9 | CHC Ichchapuram |  | 0.297
10 | CHC Seethampeta (T) |  | 3.038
| Sub-total |  | 12.546
VIZIANAGARAM
11 | CHC Bobbili | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 6.297
12 | CHC Bhogapuram |  | 0.06
13 | CHC Gajapathinagaram |  | 5.272
14 | CHC Chipurpally |  | 2.248
15 | CHC Saluru |  | 6.979
16 | CHC Kurupam |  | 0.112
17 | AH S Kota |  | 4.782
18 | AH Parvathipuram |  | 4.782
| Sub-total |  | 30.532
VISAKHAPATNAM
19 | CHC Aganampudi | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 2.278
20 | CHC K.Kotapadu |  | 0.172
21 | CHC Araku |  | 2.432
22 | CHC Chintapalli |  | 3.372
23 | CHC Bheemunipatnam |  | 1.784
24 | CHC Chodavaram |  | 2.224
25 | CHC Yellamanchili |  | 2.52
26 | AH Anakapalli |  | 4.6
27 | AH Narsipatnam |  | 0.892
28 | CHC Paderu |  | 1.742
29 | CHC Nakkapalli |  | 0.12
| Sub-total |  | 22.136
EAST GODAVARI
30 | AH Amalapuram |  | 3.117
31 | AH R.C. Puram |  | 4.811
32 | AH Peddapuram |  | 4.57
33 | CHC Prathipadu |  | 0.12
34 | AH Razole | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 0.156
35 | AH Kothapeta |  | 2.571
36 | CHC Rowthulapudi |  | 1.25
37 | CHC Kapileswarapuram |  | 0.06
38 | Rampachodavaram |  | 4.601
39 | Addateegala |  | 4.601
| Sub-total |  | 25.857
WEST GODAVARI
40 | CHC Bhimadolu | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 1.616
41 | CHC Narsapur |  | 0.138
42 | CHC Palakollu |  | 6.931
43 | CHC Bhimavaram |  | 6.171
44 | CHC Kovvuru |  | 2.032
45 | CHC Chintalapudi |  | 1.75
46 | AH Tanuku |  | 3.612
47 | AH Tadepalligudem | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 2.11
48 | AH Jangareddygudem |  | 3.56
49 | DH Eluru |  | 6.171
50 | CHC Akiveedu |  | 1.915
| Sub-total |  | 36.006
KRISHNA
51 | AH Avanigadda |  | 4.079
52 | AH Gudivada |  | 5.937
53 | AH Nandigama |  | 0.24
54 | CHC Mylavaram |  | 0.768
55 | CHC Vuyyur |  | 2.945
56 | AH Thiruvuru |  | 2.283
| Sub-total |  | 16.252
GUNTUR
57 | AH Bapatla | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 5.072
58 | AH Narsaraopeta |  | 2.964
59 | CHC Sattenapally |  | 4.023
60 | CHC Chilkaluripeta |  | 1.867
61 | CHC Macherla |  | 2.312
62 | CHC Vinukonda |  | 4.599
63 | DH Tenali |  | 7.472
64 | CHC Nizampatnam |  | 1.22
65 | CHC Ponnuru |  | 1.651
66 | CHC Peddakurapadu |  | 2.817
67 | CHC Ipur |  | 2.328
68 | CHC Gurajala |  | 3.629
69 | CHC Repally |  | 4.063
70 | CHC Amaravathi |  | 1.292
71 | CHC Nagaram |  | 1.618
72 | CHC Prathipadu |  | 5.002
| Sub-total |  | 51.929
PRAKASAM
73 | AH Markapuram | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 1.589
74 | AH Chirala |  | 3.125
75 | CHC Kanigiri |  | 0.26
76 | CHC Cumbum |  | 1.852
77 | AH Kandukuru |  | 3.239
78 | CHC Giddaluru |  | 3.239
| Sub-total |  | 13.304
NELLORE
79 | DH Nellore | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 3.192
80 | AH Gudur |  | 5.748
81 | AH Kavali |  | 5.985
82 | MCH Nellore |  | 5.758
83 | CHC Udayagiri |  | 6.208
84 | CHC Venkatagiri |  | 6.208
85 | CHC Naidupeta |  | 6.208
86 | CHC Kota |  | 6.208
87 | CHC Sullurpeta |  | 6.208
| Sub-total |  | 51.723
CHITTOOR
88 | AH Kuppam | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 3.157
89 | AH Madanapalli |  | 6.46
90 | CHC Puttur |  | 2.958
91 | AH Srikalahasti |  | 6.697
92 | CHC Kalikiri |  | 7.017
93 | AH Palamaneru |  | 1.066
94 | AH Nagari |  | 8.006
95 | DH Chittoor |  | 4.61
96 | CHC Bangarupalem |  | 4.909
| Sub-total |  | 44.88
ANANTAPUR
97 | AH Penukonda | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 4.142
98 | AH Dharmavarm |  | 6.03
99 | CHC Nallamada |  | 3.582
100 | CHC Tadipatri |  | 3.976
101 | CHC Rayadurg |  | 0.22
102 | CHC Konakondla |  | 3.537
103 | DH Hindupur |  | 4.687
104 | CHC Uravakonda |  | 3.016
105 | AH Gooty |  | 2.41
106 | AH Kadiri |  | 3.48
107 | AH Guntakal |  | 0.36
| Sub-total |  | 35.44
KADAPA
108 | DH Proddutur | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 155
109 | CHC Rayachoti |  | 2.143
110 | CHC Rajampet |  | 5.43
111 | CHC Jammalamadugu |  | 3.778
112 | CHC Vempalli |  | 4.18
113 | CHC Badvel |  | 4.856
114 | CHC Lakkireddypalli |  | 0.337
| Sub-total |  | 175.724
KURNOOL
115 | MCH Adoni | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 4.352
116 | DH Nandyala |  | 4.352
117 | CHC Allagadda |  | 5.852
118 | CHC Alur |  | 5.852
119 | CHC Atmakur |  | 5.852
120 | CHC Banaganipalli |  | 4.252
121 | CHC Dhone |  | 4.602
122 | CHC Kodumur |  | 1.887
123 | CHC Kovelakuntla | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 5.852
124 | CHC Nandikotkur |  | 5.852
125 | CHC Pathikonda |  | 3.742
126 | CHC Sunnipenta |  | 2.642
127 | CHC Veldurthi |  | 1.707
128 | CHC Velugodu |  | 1.267
129 | CHC Yemmiganur |  | 4.252
130 | CHC Orvakallu |  | 1.527
| Sub-total |  | 63.842
MAHABOOBNAGAR
131 | DH Mahaboobnagar | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 5.708
132 | AH Gadwal |  | 2.377
133 | AH Wanaparthy |  | 1.08
134 | AH Narayanpet |  | 1.952
135 | CHC Kalwakurthy |  | 2.714
136 | CHC Badepally | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 1.333
137 | CHC Shadnagar |  | 0.11
138 | CHC Maktal |  | 6.278
139 | CHC Atmakur |  | 5.168
140 | CHC Kodangal |  | 4.654
141 | CHC Palem |  | 4.609
142 | CHC kosigi |  | 3.008
143 | CHC Kollapur |  | 5.513
144 | CHC Achampet (T) |  | 2.839
| Sub-total |  | 47.343
RANGAREDDY
145 | DH Tandur | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 8.469
146 | AH Kondapur |  | 5.284
147 | CHC Vikarabad |  | 1.944
148 | CHC Hayathnagar |  | 5.892
| Sub-total |  | 21.589
NALGONDA
149 | DH Nalgonda | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 3.42
150 | AH Miryalguda |  | 1.76
151 | AH Huzurnagar |  | 2.852
152 | AH Suryapet |  | 1.6
153 | AH Nagarjunasagar |  | 1.46
154 | AH Devarakonda |  | 1.792
155 | AH Bhongari |  | 3.802
156 | AH Ramannapet |  | 3.142
157 | CHC Kodad |  | 2.838
158 | CHC Choutuppal |  | 3.145
159 | CHC Nakrekal |  | 3.834
| Sub-total |  | 29.645
MEDAK
160 | AH Zaheerabad | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 6.156
161 | AH Medak |  | 6.131
162 | MCH Siddipet |  | 5.64
163 | DH Sangareddy |  | 2.77
164 | CHC Jogipet | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 2.23
165 | CHC Narayankhed |  | 1.44
166 | CHC Narsapur |  | 5.274
167 | CHC Gajwel |  | 2.382
168 | CHC Sadasivpet |  | 3.78
169 | CHC Ramayampet |  | 0.56
| Sub-total |  | 36.363
NIZAMABAD
170 | DH Nizambad | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 4.22
171 | CHC Varni |  | 1.832
172 | CHC Dichpally |  | 2.439
173 | AH Kamareddy |  | 1.68
174 | AH Bodhan |  | 0.23
175 | CHC Yellareddy |  | 4.402
176 | CHC Balkonda |  | 2.859
177 | CHC Bichkunda | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 2.949
178 | CHC Pitlam |  | 2.949
179 | CHC Gandhari |  | 5.42
180 | CHC Navipet |  | 2.859
181 | AH Banswada |  | 4.342
182 | CHC Madnoor |  | 4.753
183 | CHC Dharpally |  | 2.799
| Sub-total |  | 43.733
WARANGAL
184 | DH Janagaon | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 1.091
185 | AH Mahbubabad |  | 4.916
186 | CHC Mulugu |  | 3.528
187 | CHC Narsampet |  | 5.269
188 | CHC Eturunagaram |  | 2.303
189 | CHC Wardhannapet |  | 1.388
| Sub-total |  | 18.495
KHAMMAM
190 | AH Sathupalli | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 4.56
191 | AH Bhadrachalam |  | 8.691
192 | AH Kothagudem |  | 9.038
193 | DH Khammam |  | 4.62
194 | AH Palvancha |  | 7.675
195 | CHC Penubally |  | 1.066
196 | CHC Kunavaram |  | 3.421
197 | CHC Chinturu |  | 4.917
| Sub-total |  | 43.988
KARIMNAGAR
198 | DH Karimnagar | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 5.79
199 | AH Jagithyal |  | 8.825
200 | AH Siricilla |  | 5.748
201 | AH Godavarikani |  | 7.94
202 | CHC Peddapalli |  | 1.043
203 | CHC Metpally |  | 3.712
204 | CHC Manthani |  | 5.559
| Sub-total |  | 38.617
ADILABAD
205 | MCH Nirmal | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 7.258
206 | CHC Sirpur T |  | 0.679
207 | AH Bhainsa |  | 2.424
208 | CHC Utnoor |  | 4.997
209 | CHC Asifabad |  | 4.457
210 | CHC Boath |  | 3.629
| Sub-total |  | 23.444
| Grand total |  | 883.388

## without amnt (hidden)
FRUs (First Referral Units) Grade - I & II Hospitals for the year 2012-13 Under NRHM
Sl. No. | Name of the Location | Administrative Sanction Reference No. | Sanction amount |  |  | Exepnditure (Rs.in lakhs) | Stage of work | Expected date of comletion
|  |  | Civil (Rs.in lakhs) | Equipment (Rs.in lakhs) | Total (Rs.in lakhs)
VISAKHAPATNAM
1 | CHC Munchingput |  | 0 | 0 | 0 |  | --
KRISHNA
2 | AH Nuzividu |  | 0 | 0 | 0 |  | --
3 | CHC Kaikaluru |  | 0 | 0 | 0 |  | --
4 | CHC Jaggaipet |  | 0 | 0 | 0 |  | --
5 | CHC Challapalli |  | 0 | 0 | 0 |  | --
6 | CHC Vissannapet |  | 0 | 0 | 0 |  | --
7 | CHC Gannavaram |  | 0 | 0 | 0 |  | --
| Sub-total |  | 0 | 0 | 0
CHITTOOR
8 | AH Piler |  | 0 | 0 | 0 |  | --
ANANTAPUR
9 | CHC Tanakal |  | 0 | 0 | 0 |  | --
10 | CHC Singanamala |  | 0 | 0 | 0 |  | --
11 | AH Madakasira |  | 0 | 0 | 0 |  | --
| Sub-total |  | 0 | 0 | 0
KURNOOL
12 | CHC Midthur |  | 0 | 0 | 0 |  | --
WARANGAL
13 | CHC Dhornakal | Procdgs.Rc.No.67/SPMU-NRHM/2012, dt.17.05.2012 of CH&FW | 0 | 0 | 0 |  | --
14 | CHC Thorrur |  | 0 | 0 | 0 |  | --
| Sub-total |  | 0 | 0 | 0