## cov.p
Dt:19.01.2016
Construction of (366) Sub-Centre Building for the year 2010-11 under NRHM

## Sheet2 (hidden)
ABSTRACT
Construction of Sub-centre buildings for the year 2011-12
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Tenders invited | Tenders to be invited | Site to be handed over | Others | Remarks
1 | Srikakulam | 99 | 11 | 7 | 3 | 1
2 | Vizianagaram | 162 | 18 | 8 | 5 | 5
3 | Visakhapatnam | 9 | 1 | 1 |  |  |  | Work to be grounded.
4 | East Godavari | 162 | 18 | 17 | 1 |  |  | Recall for one work.
5 | West Godavari | 126 | 14 | 13 |  |  | 1 | Sub-centre sanction not there in village Koppaka clarification from DM&HO awaited.
6 | Krishna | 216 | 24 |  | 6 | 18 |  | The estimates are above Rs.9.00 lakhs. Hence, orders waited for further action.
7 | Guntur | 189 | 21 | 7 | 7 | 6 | 1 | Rajupalem, Uppalpadu sub-centre overlapped Hence to be deleted.
8 | Prakasam | 180 | 20 | 18 |  | 2
9 | Nellore | 180 | 20 |  | 8 | 12
10 | Chittoor | 216 | 24 | 23 |  |  | 1 | Building already existing alternative proposals to be furnished.
11 | Kadapa | 216 | 24 |  | 23 |  | 1 | Double sanction one sub-centres Kadamasti.
12 | Ananthapur | 207 | 23 |  | 16 | 7
13 | Kurnool | 189 | 21 |  | 16 | 5
14 | Mahaboobnagar | 135 | 15 | 11 |  | 4
15 | Ranga Reddy | 162 | 18 |  |  | 18
16 | Medak | 243 | 27 | 27
17 | Nizamabad | 189 | 21 | 21 |  |  |  | Tenders invited and finalized.
18 | Adilabad | 90 | 10 |  | 10
19 | Karimnagar | 45 | 5 |  |  | 4 | 1 | Building already existing alternative proposals to be furnished.
20 | Warangal | 27 | 3 | 3 |  |  |  | Work to be grounded.
21 | Khammam | 63 | 7 |  | 7
22 | Nalgonda | 189 | 21 |  | 19 | 2
| TOTAL | 3294 | 366 | 156 | 121 | 84 | 5
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## abs monthwise
ABSTRACT
Construction of (366) Sub-centre buildings for the year 2010-11
Sl.No. | District | AS / RAS amount (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up 6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other department/Scheme | Site problem | RAS awaited | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | SKLM | 104.5 | 92.05 | 3.81 | 11 |  |  |  |  | 11 | 11 |  |  | 10 | 1 | 10 | 1 | 1
2 | VZM | 182 | 123.84 | 5.27 | 18 | 1 | 1 | 2 | 4 | 14 | 14 |  |  | 13 | 1 | 13 | 1 | 1
3 | VSP | 12 | 8.884 |  | 1 |  | 0 | 0 | 0 | 1 | 1 |  |  | 1 |  | 1 |  | 0
4 | EG | 187 | 136.39 | 16.56 | 18 | 0 |  | 0 | 0 | 18 | 16 |  | 2 | 15 | 3 | 7 | 11 | 9
5 | WG | 149.15 | 123.72 | 2.09 | 14 |  | 1 |  | 1 | 13 | 13 |  |  | 12 | 1 | 12 | 1 | 1
6 | KRI | 314.89 | 215.935 | 35.54 | 24 | 3 |  | 0 | 3 | 21 | 18 |  | 3 | 18 | 3 | 16 | 5 | 2
7 | GNT | 204 | 187.37 |  | 21 |  |  |  |  | 21 | 21 |  |  | 21 |  | 21 |  | 0
8 | PKSM | 255.75 | 70.53 | 99.25 | 20 | - | 5 | - | 5 | 15 | 6 | 1 | 8 | 5 | 10 | 3 | 12 | 3
9 | NLR | 220 | 147.28 | 28 | 20 | 0 | 1 |  | 1 | 19 | 19 |  |  | 17 | 2 | 17 | 2 | 2
10 | CTR | 216.75 | 211.78 |  | 24 |  |  |  |  | 24 | 24 |  |  | 24 |  | 24 |  | 0
11 | KDP | 246 | 195.4 | 1.54 | 24 |  | 2 |  | 2 | 22 | 22 |  |  | 21 | 1 | 21 | 1 | 1
12 | ATP | 217 | 139.03 |  | 23 |  | 1 | 4 | 5 | 18 | 17 | 1 |  | 17 | 1 | 17 | 1 | 0
13 | KNL | 214.45 | 164.93 | 36.39 | 21 |  |  |  |  | 21 | 18 |  | 3 | 17 | 4 | 17 | 4 | 1
| TOTAL | 2523.49 | 1817.139 | 228.45 | 239 | 4 | 11 | 6 | 21 | 218 | 200 | 2 | 16 | 191 | 27 | 179 | 39 | 21
48.74
2474.75

## abs (hidden)
ABSTRACT
Construction of (366) Sub-centre buildings for the year 2010-11
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Status of works | [5 empty] | Expenditure (Rs.in lakes) | Remarks
|  |  |  | Site problem | Work not taken up | Tender stage | Work to be started | Work is in progress | Work completed
1 | Srikakulam | 99 | 11 |  |  |  | 1 | 8 | 2 | #REF! |  | 11
2 | Vizianagaram | 162 | 18 | 1 | 4 |  |  | 10 | 3 | #REF! |  | 18
3 | Visakhapatnam | 9 | 1 | [5 empty] | 1 | #REF! |  | 1
4 | East Godavari | 162 | 18 |  |  |  | 2 | 12 | 4 | #REF! |  | 18
5 | West Godavari | 126 | 14 |  |  | 1 | 2 | 11 |  | #REF! |  | 14
6 | Krishna | 216 | 24 | 4 |  | 15 | 2 | 3 |  | #REF! | RAS requested for 16 works and 4 recently proposed for RAS. | 24
7 | Guntur | 189 | 21 | 5 | 1 | 1 |  | 9 | 5 | #REF! |  | 21
8 | Prakasam | 180 | 20 | 8 |  |  |  | 12 |  | #REF! |  | 20
9 | Nellore | 180 | 20 | 6 |  | 1 | 1 | 9 | 3 | #REF! | 1 No. Revised Administrative approval requested. | 20
10 | Chittoor | 216 | 24 |  |  |  |  | 16 | 8 | #REF! |  | 24
11 | Ananthapur | 207 | 23 | 1 |  |  | 1 | 14 | 7 | #REF! |  | 23
12 | Kadapa | 216 | 24 | 2 |  |  | 2 | 17 | 3 | #REF! |  | 24
13 | Kurnool | 189 | 21 | 5 |  |  |  | 12 | 4 | #REF! |  | 21
14 | Mahaboobnagar | 135 | 15 |  |  |  |  | 6 | 9 | #REF! |  | 15
15 | Ranga Reddy | 162 | 18 |  | 1 |  | 1 | 13 | 3 | #REF! | Sub-centre work at Motukur was entrusted to PR Dept. and they have taken up the work. | 18
16 | Nalgonda | 189 | 21 |  |  |  | 3 | 16 | 2 | #REF! | 1 No. Location change. | 21
17 | Medak | 243 | 27 | 1 |  | 1 |  | 17 | 8 | #REF! | 1 No. RA awaited. | 27
18 | Nizamabad | 189 | 21 |  |  |  |  | 7 | 14 | #REF! |  | 21
19 | Warangal | 27 | 3 | [5 empty] | 3 | #REF! |  | 3
20 | Khammam | 63 | 7 |  | 6 |  |  | 1 |  | #REF! | 6 works to ITDA. | 7
21 | Karimnagar | 45 | 5 | 1 |  |  |  | 2 | 2 | #REF! |  | 5
22 | Adilabad | 90 | 10 | 1 | 1 |  |  | 5 | 3 | #REF! | 1 No. deleted. | 10
| TOTAL | 3294 | 366 | 35 | 13 | 19 | 15 | 200 | 84 | #REF! |  | 366
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## 366
Construction of 366 Sub-Centres under NRHM
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
DISTRICT : SRIKAKULAM
1 | SKLM | Polaki | Amplam | 09.12.2010 | 9.5 | 8.79 | Sri K.H.V.Prasad | 26.03.13
2 | -do- | L.N.Peta | Dabbapadu |  | 9.5 | 8.83 | Sri R.Arjuna Rao | 22.10.12
3 | -do- | Sreekurmam | Korlam |  | 9.5 | 8.69 | Sri A.Nagaraju | 9.8.2012
4 | -do- | Gara | Calingapatnam |  | 9.5 | 8.69 | Sri P.Narisinga Rao | 19.2.2013.
5 | -do- | Siripuram | Chinakosta |  | 9.5 | 5.69 | M/s. Vijayabhanu V.Mohana Rao | 31.08.2015
6 | -do- | Sompeta | Isukalapalem |  | 9.5 | 8.32 | Sri V.Mohana Rao | 30.6.2013
7 | -do- | Mandasa | Killoi colony |  | 9.5 | 8.69 | M/s. Vijayabhanu | 31.07.2014
8 | -do- | Bhamini | Sathiwada |  | 9.5 | 8.62 | Sri V.Mohana Rao | 19.10.2012
9 | -do- | Mandasa | Chinna Kamba |  | 9.5 | 8.37 | Sri S.Thavitayya | 8.10.2012
10 | -do- | Hiramandalam | Gottipalli |  | 9.5 | 8.76 | Sri M.Laxmanarao | 10.10.2012
11 | -do- |  | Chinnabagga |  | 9.5 | 8.6 | Sri P.Arjuna | 25.10.2012
|  |  | Sub-total |  | 104.5 | 92.05
DISTRICT : VIZIANAGARAM
12 | VZM | S.Kota | Seetharamapuram | 09.12.2010 | 9 | 9 | M/s SCLC Co-Operative Society Ltd | 07.12.12.
13 | ..do.. | L.Kota | Latchampeta |  | 9 | 8.93 | ..do.. | 18.12.12
14 | ..do.. | Vepada | SSR Puram |  | 9 | 8.85 | ..do.. | 26.12.13
15 | ..do.. | Gantyada | Ramavaram |  | 9 | 8.29 | ..do.. | 30.01.14
16 | ..do.. | Nellimarla | Pedaburadipeta |  | 9 | 8.85 | M.V.Ramana Murthy, | 30.08.12
17 | ..do.. | Cheepurupalli | G.Mulagam |  | 9 | 8.97 | K.Srinivasu, | 24.12.12
18 | ..do.. | Dathirajeru | P.Lingavalasa |  | 9 | 9 | G.Nageswara Rao, | 27.06.13
19 | ..do.. | Kurupam | G.Sivada |  | 9 | 8.97 | Sri K.Chandra Naidu, | 26.03.13
20 | ..do.. | Merakamudidham | Somalingapuram |  | 9 | 9 | ..do.. | 30.03.14
21 | ..do.. | Komarada | Amiti |  | 9 | 9 | ..do.. | 15.03.13
22 | ..do.. | Cheepurupalli | Mettapalli |  | 9 | 9 | A.Chinnam Naidu, | 26.06.13
23 | ..do.. | Gurla | Jammu |  | 9 | 8.67 | K.Srinivasu, | 03.03.14
24 | ..do.. | Denkada | Akkivaram |  | 9 | 8.58 | P.Parvatheswara Rao, | 29.09.12
25 | ..do.. | Gantyada | Lakkidam (Thadipudi) |  | 14 | 8.73 | G.Appala Naidu, | 31.08.2015
26 | ..do.. | Kurupam | Pedasakha (Chollapadam) | 09.12.2010 | 9 | - | - | - | Sub-Centre building is being takenup by P.R Department Parvathipuram.
27 | ..do.. | Jiyyammavalasa | RRB Puram (Kondachilakam) |  | 14 |  | M/s Bindu Transmissions & Projects Pvt Ltd, Hyderabad |  | RAS to be received
28 | ..do.. | Pachipenta | Mathumuru (Thangalam) |  | 14 |  | - | - | RAS to be received
29 | ..do.. | Salur | P.Chenneru |  | 14 |  | - | - | Tenders called for no response even (6th call.) Site yet tobe identified
|  |  | Sub-total |  | 182 | 123.84
DISTRICT : VISAKHAPATNAM
30 | VSP | Madugula | J.D.Peta(T) | 09.12.2010 | 12 | 8.884 | M/s Surya | 19.09.11 | Completed
|  |  | Sub-total |  | 12 | 8.884
DISTRICT : EAST GODAVARI
31 | EG | Ramachandrapuram | Draksharamam | 09.12.2010 | 9 | 8.47 | M/s Bhavana Constructions, Kakinada. | 31.12.2012 | Final bill paid
32 | ..do.. | Kapileswarapuram | Nalluru | 09.12.2010 | 11 | 8.33 | K. Raj kumar | 28.02.2012 | Final bill paid
33 | ..do.. | Rajahmundry rural | Katheru |  | 11 | 8.29 | M/s Sri Venkateswara | 30.04.2013 | Final bill paid
34 | ..do.. | Allavaram | Komaragiripatnam-2 |  | 9 | 8.52 | R.V. Srinivasa Rao, | 17.04.2012 | Final bill paid
35 | ..do.. | Kajuluru | Tanukuwada |  | 11 | 8.37 | D. Sriram suryanarayana | 10.04.2012 | Final bill paid
36 | ..do.. | Inavilli | Nedunuru |  | 11 | 8.46 | Ch. Gopal | 30.04.2012 | Final bill paid
37 | ..do.. | Peddapuram | Divili |  | 9 | 1.68 | K. Balakrishna |  | Roof slab laid. Work stopped long back, issued notice to the Contractor.
38 | ..do.. | Katrenikona | Chirayanam |  | 11 | 8.58 | N. Srinivasa Rao | 10.01.2012 | Final bill paid
39 | ..do.. | Kirlampudi | Goneda |  | 9 | 2.63 | T.S.R. Swamy |  | Columns upto roof slab laid. Work stopped due to Hon'ble High court stay.
40 | ..do.. | Korukonda | Sri Rangapatnam-1 |  | 9 | 6.13 | M/s Sri Venkateswara | 30.06.2013 | Final bill to be paid
41 | ..do.. | Malkipuram | Chinthalamori |  | 11 | 8.64 | P.V. Swamy | 25.09.2011 | Final bill paid
42 | ..do.. | Tuni | K.O.Mallavaram |  | 11 | 8.63 | N.Prasada Rao | 21.12.2011 | Final bill paid
43 | ..do.. | Kakinada rural | Suryaraopeta | 09.12.2010 | 12 | 8.66 | R.S.Santharam | 06.06.2012 | Final bill paid
44 | ..do.. | Prathipadu | Peddipalem-1 |  | 11 | 8.41 | K. Muralikrishna | 20.01.2012 | Final bill paid
45 | ..do.. | Rangampeta | Singampalli |  | 11 | 6.98 | M/s Bhavana | 31.05.2013 | Final bill paid
46 | ..do.. | Uppalaguptham | N.Kothapalli |  | 11 | 8.48 | N. Srinivasa Rao, | 31.01.2012 | Final bill paid
47 | ..do.. | Kothapeta | Vadapalem |  | 11 | 8.63 | K. Raj kumar | 28.02.2012 | Final bill paid
48 | ..do.. | Gollaprolu | Dugrada-1 |  | 9 | 8.5 | T.S.R. Swamy | 31.07.2013 | Final bill paid
|  |  | Sub-total |  | 187 | 136.39
DISTRICT : WEST GODAVARI
49 | WG | AKIVEEDU | Dumpagadapa | 09.12.2010 | 10.6 | 9.83 | Y.Lakshmana Rao, | 30.05.2013
50 | ..do.. | YALAMANCHILI | Kanakayalanka |  | 11.25 | 10.53 | S.V.Bhagavan Rao | 31.03.2013
51 | ..do.. | BHIMAVARAM | Dongapindi |  | 11.4 | 9.31 | S.V.Bhagavan Rao | 30.06.2013
52 | ..do.. | BHIMAVARAM | Kothapusalamarru |  | 9 | 8.67 | S.V.Bhagavan Rao, | 30.06.2013
53 | ..do.. | K.V.Kota | Kallacheruvu |  | 9.6 | 9.01 | Sri.T.Mallaiah | 31.03.2013
54 | ..do.. | NARASAPURAM | Kopparru |  | 9 | 8.28 | Sri G.Venkata Rao | 30.06.2013
55 | ..do.. | Polavaram | K.Pattiseema(T) |  | 9 | 8.15 | Sri.G.Srinivasa Reddy | 30.06.2013
56 | ..do.. | PALAKOLLU | Tilapudi |  | 11.5 | 10.72 | Sri.Gokaraju Venkata Rao | 31.03.2013
57 | ..do.. | MOGALTHURU | Pathapadu |  | 10.3 | 9.37 | S.V.Bhagavan Rao | 31.03.2013
58 | ..do.. | PENTAPADU | Meenavalluru | 09.12.2010 | 10.5 | 9.35 | Sri.Y.Lakshmana Rao | 31.03.2013
59 | ..do.. | PENUGONDA | Mulaparru |  | 10 | 9.45 | Sri.S.Ramakrishna Reddy | 31.03.2013
60 | ..do.. | UNDRAJAVARAM | Chivatam |  | 11.5 | 10.51 | Sri.S.Ramakrishna Reddy | 31.03.2013
61 | ..do.. | UNDRAJAVARAM | Satyawada |  | 11.5 | 10.54 | Sri G.Venkateswararao | 31.03.2013
62 | ..do.. | PEDAPADU | Pathamupparu | 16.01.2013 | 14 | --- |  |  | Site not available
|  |  | Sub-total |  | 149.15 | 123.72
DISTRICT : KRISHNA
63 | KRI | Nuzvid | Seetharamapuram | 09.12.10 | 11.38 | 9.88 | Ch.Ratnakara Rao | 30.09.2013
64 | -do- | Mopideevi | K.Kothapalem |  | 11.68 | 11 | Sri B.Madhu babu, | 18-01-2014
65 | -do- | Sagguru | Kommuru |  | 11.35 | 10.17 | Ch.Ratnakara Rao | 31.03.2014
66 | -do- | Challapalli | Nadukuduru |  | 11.69 | 11.09 | Sri B.Madhu babu | 27-12-2013
67 | -do- | Koduru | Vullipalem |  | 11.81 | 4.1 | Sri K.Sambasiva Rao |  | Finishings are in progress | 31.01.2016
68 | -do- | Ghantasala | Ghantasala |  | 11.74 |  |  |  | PHC constructed. Hence not required
69 | -do- | Thotlavalluru | Bhadrirajupalem |  | 11.71 | 10.23 | S.V.Koteswararao | 30-1-2014
70 | -do- | Makkapeta | Makkapeta | 09.12.10 | 14 | 0 | --- |  | Existing building available, repairs required
71 | -do- | Gantasala | Daliparru (Gudlavalluru-II) |  | 14 | 4.18 | V.Balaji |  | Roof level | 31.03.2016
72 | -do- | Challapalli | Ramanagaram (Kowthavaram) |  | 14 | 12.95 | B.Madhu babu | 30.06.2015
73 | -do- | Gudlavalleru | Vinnakota |  | 14 | 13.42 | Sri T.Srimann | 13-5-2013
74 | -do- | Gudiwada | Billapadu |  | 11.81 | 11.11 | Sri A.Subba Rao | 20-1-2014
75 | -do- | Mylavaram | Mulapadu(Pulluru) |  | 14 | 0.17 | --- |  | Foundations is in progress. | 31.03.2016
76 | -do- | Gantasala | Vemulapalli |  | 11.72 | 10.68 | Sri B.Madhu babu | 20-01-2014
77 | -do- | Musunuru | Gopavaram | 16.01.2013 | 14 | 8.39 | Ch.Ratnakara Rao, Nuzvid | 21-12-2013
78 | -do- | Bantumilli | Arthamuru | 16.01.2013 | 14 | 11.91 | M/s Elixir Met Form Pvt.ltd, Hyd | 31.01.2014
79 | -do- | Bantumilli | Pedatummidi | 16.01.2013 | 14 |  |  |  | PHC constructed. Hence not required
80 | -do- | Kruthivennu | Nellipudi | 16.01.2013 | 14 | 11.91 | M/s Elixir Met Form Pvt.ltd, Hyd | 31.01.2014
81 | -do- | Vuyyuru | Mudunuru | 16.01.2013 | 14 | 12.53 | M/s Elixir Met Form Pvt.ltd, Hyd | 31.01.2014
82 | -do- | Gudiwada | Jammidintakuru | 16.01.2013 | 14 | 12.53 | M/s Elixir Met Form Pvt.ltd, Hyd | 31.01.2014
83 | -do- | Mudinepalli | Venduru | 16.01.2013 | 14 | 12.53 | M/s Elixir Met Form Pvt.ltd, Hyd | 31.01.2014
84 | -do- | Jaggayyapeta | Budavada | 16.01.2013 | 14 | 12.22 | M/s Elixir Met Form Pvt.ltd, Hyd | 31.01.2014
85 | -do- | Pamidimukkala | Meduru | 16.01.2013 | 14 | 12.47 | M/s Elixir Met Form Pvt.ltd, Hyd | 31.01.2014
86 | -do- | Movva | Pedasanagallu | 16.01.2013 | 14 | 12.465 | M/s Elixir Met Form Pvt.ltd, Hyd | 31.01.2014
|  |  | Sub-total |  | 314.89 | 215.935
DISTRICT : GUNTUR
87 | GNT | Bapatla(M) | Hyderpeta | 09.12.2010 | 9 | 8.2 | Sri K.Murali Krishna | 2012-09-07
88 | -do- | Ponnuru(M) | Munipalle |  | 9 | 8.75 | Sri R.Radha Krishna Murthy. | 2012-10-04
89 | -do- | Amaravathi(M) | Narukullapadu |  | 9 | 8.58 | Sri K.Srinivasu, | 2012-03-12
90 | -do- | Bhattiprolu(M) | Ilavaram |  | 9 | 8.78 | Sri N.Bala Kotaiah | 2012-12-09
91 | -do- | Dachepalli. | Mutyalampadu |  | 9 | 8.72 | Sri M.Yeleswara Reddy | 2012-12-09
92 | -do- | Cherukupalli(M) | Arepalli |  | 9 | 8.19 | Sri K.Murali Krishna | 31-7-13
93 | -do- | Cherukupalli(M) | Nadimpalli |  | 9 | 8.57 | Sri K.Murali Krishna | 20-2-13
94 | -do- | Krosuru(M) | Bayyavaram |  | 9 | 8.46 | Sri M.Yeleswara Reddy | 31/01/2014
95 | -do- | Krosuru(M) | Utukuru |  | 9 | 8.52 | Sri K.Srinivasu, | 20-6-12
96 | -do- | Machavaram(M) | Chennayapalem |  | 9 | 8.63 | Sri R.Radha Krishna Murthy. | 2012-01-09
97 | -do- | Rajepalem(M) | Uppalapadu (R) |  | 9 | 8.67 | Sri M.Yeleswara Reddy | 30-9-12
98 | -do- | Mangalagiri(M) | Chinakakani |  | 9 | 8.1 | Sri R.Radha Krishna Murthy. | 2012-12-07
99 | -do- | Tadepalli(M) | Kunchanapalli |  | 9 | 8.84 | Sri R.Radha Krishna Murthy. | 2012-12-07
100 | -do- | Savalyapuram(M) | Velpur (Uppalapadu (I)) | 09.12.2010 | 14 | 12.7 | Sri M.Yeleswara Reddy | 31.07.2014
101 | -do- | Savalyapuram(M) | Karumanchi |  | 9 | 8.4 | Sri O.Srinivasa Rao. | 31/01/2014
102 | -do- | Prathipadu(M) | Gottipadu | 09.12.2010 | 9 | 8.41 | Sri K.Murali Krishna | 31/01/2014
103 | -do- | Macherla(M) | Kothapalli |  | 9 | 8.66 | Sri A.Chennakesava Reddy. | 2012-08-12
104 | -do- | Macherla(M) | Kotturu |  | 9 | 8.09 | Sri A.Chennakesava Reddy. | 25-4-13
105 | -do- | Durgi(M) | Polepalli |  | 9 | 8.65 | Sri A.Chennakesava Reddy. | 31-7-2013
106 | -do- | Veldurthi(M) | Gangalakunta |  | 14 | 12.81 | Sri K.Sardar Naik, Contractor, | 22.12.2014
107 | -do- | Veldurthi(M) | Kandilakunta |  | 14 | 8.64 | Sri P.Lakshma Reddy, | 15.02.2014
|  |  | Sub-total |  | 204 | 187.37
DISTRICT : PRAKASAM
108 | PKSM | Yerragondapalem | Mallapalem | 09.12.2010 | 14 | 4.49 | Y.Chandrasekhar |  | Finishings in progress | 31.01.2016
109 | -do- | Pullalacheruvu | Manepalli |  | 9 | 8.64 | Sri.P.VenkataReddy, | 20.6.2013
110 | -do- | Yerragondapalem | Naidupalem |  | 14 | - | G.Krishnaiah |  | Site to be handed over |  | sp
111 | -do- | Pullalacheruvu | Maguturu |  | 14 | - | Y.Chandrasekhar |  | Earth Work excavation is in progress | 31.03.2016
112 | -do- | Donakonda | Donakonda |  | 14 | - | G.Krishnaiah |  | Site to be handed over |  | sp
113 | -do- | Giddalur | Narwaboinapalli |  | 14 | 4.93 | Y.Chandrasekhar |  | Superstructure in progress | 29.02.2016
114 | -do- | Yerragondapalem | Aynamukkala |  | 14 | 4.6 | Y.Chandrasekhar |  | Finishings in progress | 31.01.2016
115 | -do- | Thripuranthakam | Mittapalem |  | 14 | 3.79 | G.Venkateswarlu | 30.06.2015
116 | -do- | Dornala | Nallakunta |  | 14 | 4.66 | Y.Chandrasekhar |  | Superstructure in progress | 31.01.2016
117 | -do- | Besthavaripeta | R Kothapalli |  | 14 | - | - |  | Site to be handed over |  | sp
118 | -do- | Kanigiri | Nanadanamaralla |  | 9 | 8.59 | M/s.Sri Sashi | 14.12.2011
119 | -do- | C.S.Puram | Kothapalli |  | 14 | 4.28 | Y.Chandrasekhar |  | Finishings in progress | 31.01.2016
120 | -do- | Chirala | Devangapuri |  | 9 | 8.63 | Sri V.Sundaraiah | 14.12.2011
121 | -do- | Yerragondapalem | Ganjivaripali |  | 14 |  | - |  | Work is in progress | 30.06.2016
122 | -do- | Pullalacheruvu | Pedakolukula | 09.12.2010 | 14 | - | G.Krishnaiah |  | Agreement concluded. Site allotted but building portion D.Marked |  | sp
123 | -do- | Komarolu | Nallaguntla |  | 9 | 8.59 | Sri V.Krishnamohan reddy | 6.12.2011
124 | -do- | Thripuranthakam | Kanakalapalli |  | 14 |  | - |  | Agreement concluded. Work to be started |  | w2s
125 | -do- | Komarole | Komarole |  | 9.75 | 9.33 | Sri.V.Krishnamohan reddy | 30.09.2013
126 | -do- | Singarayakonda | Mannetikota |  | 14 |  | - |  | Plinth beam to be laid | 29.02.2016
127 | -do- | Yerragondapalem | Gurrapusala |  | 14 | - | G.Krishnaiah |  | Agreement concluded. Site allotted but building portion D.Marked |  | sp
|  |  | Sub-total |  | 255.75 | 70.53
DISTRICT : NELLORE
128 | NLR | Anantha sagaram | Kamireddypadu | 09.12.2010 | 9 | 8.35 | K.V.K. Reddy | 15-10-2012
129 | -do- | Anantha sagaram | Vengampalli |  | 9 | 8.46 | K.V.K. Reddy | 25-09-2012
130 | -do- | V.giri | Nagavolu |  | 9 | 8.28 | A. Niranjan Reddy | 16-08-2014
131 | -do- | V.giri | Kalavalapudi |  | 9 | 8.56 | A. Niranjan Reddy | 23-03-2013
132 | -do- | Udayagiri | Durgampalli |  | 9 | 8.45 | L. Rama Siva Reddy | 31-03-2013
133 | -do- | Udayagiri | Kurru |  | 9 | 8.55 | B. Ramesh Babu | 25-06-2014
134 | -do- | Vinjamur | Garimanapeta |  | 14 | 8.54 | L. Lakshmi Reddy | 15-09-2014
135 | -do- | Kondpuram | Saipeta |  | 14 | 8.65 | K. Ramesh | 15-11-2014
136 | -do- | Atmakur | Karatampadu | 09.12.2010 | 9 | 8.51 | J. Pullaiah | 24-11-2012
137 | -do- | Marripadu | Brahmanapalli |  | 9 | 8.47 | Ch. Venkates-warlu Reddy | 20-03-2013
138 | -do- | Marripadu | Chenchuluru |  | 9 | 8.65 | J. Pullaiah | 28-03-2012
139 | -do- | Rapur | Venadu |  | 14 | 0 | J. Pullaiah | 31.08.2015
140 | -do- | Tada | Bhimunivanipalem |  | 14 | 8.11 | Ch. Satish | 09-08-2014
141 | -do- | Sullurpet | Vatembedu |  | 14 | 7.94 | Ch. Satish | 09-08-2014
142 | -do- | Udayagiri | Gundupally |  | 9 | 8.43 | K. Rama chandra Reddy | 12-06-2012
143 | -do- | Kavali | Annareddypalem |  | 9 | 8.68 | B. Ramesh Babu | 05-07-2012
144 | -do- | Rapur | Penubarthi |  | 9 | 8.28 | P. Mahaboob Basha | 30-10-2012
145 | -do- | Tada | Irakam (Island) | 16.01.2013 | 14 | 12.37 | J. Pullaiah | 12-08-2014
146 | -do- | Rapur | Tegacherla |  | 14 |  |  | 31.08.2015
147 | -do- | Rapur | Gundavolu / Obulayapalli |  | 14 |  |  |  | Site allotted in R&R colony by I & CAD dept in which aminities such as roads, electricity, water supply to be provided. The work could ntot be grounded as demarkation yet to be done and there is no approach road to the colony to convey materials.
|  |  | Sub-total |  | 220 | 147.28
DISTRICT : CHITTOOR
148 | CTR | Irala | Govindareddypalli | 09.12.2010 | 9 | 8.99 | Sri. Jaya Chandra Naidu | 05-11-12
149 | -do- | Kalikiri | T.Sandravaripalli |  | 9 | 9 | Sri. P. Sudhakar | 30-12-12
150 | -do- | Kalikiri | Pollavolu |  | 9 | 9 | Sri. M. Chandra Sekhar Reddy | 08-06-12
151 | -do- | Kalikiri | M.K.Palli |  | 9 | 9 | Sri. M. Chandra Sekhar Reddy | 11-09-11
152 | -do- | Nagari | Desuruagraharam |  | 9 | 8.54 | Sri. M. Bhaskar Reddy | 10-05-12
153 | -do- | Somala | Cherukuvaripalli |  | 9 | 9 | Sri. T. Surendra Naidu | 10-09-11
154 | -do- | Nimmanapalli | Machireddygaripalli |  | 9 | 7.92 | Sri. K. Reddeppa Reddy | 28-02-14
155 | -do- | Nindraq | Paidiri |  | 9 | 8.24 | Sri. M. Bhaskar Reddy | 17-07-13
156 | -do- | P.T.M. | Mallela |  | 9 | 8.99 | Sri. C. Venkateswara Reddy | 09-12-11
157 | -do- | Peddamandyam | Siddavaram |  | 9 | 8.73 | Sri. C. Venkateswara Reddy | 31.01.2014
158 | -do- | Penumur | Thirupalli |  | 9 | 9 | Sri. V. Ramesh Babu | 09-09-11
159 | -do- | Pulicherla | E-Ramireddygari palli |  | 9 | 9 | Sri. N. Ashok Reddy | 16-05-12
160 | -do- | Renigunta | Peruru |  | 9 | 8.87 | Sri. G. Munaswamy | 18-06-12
161 | -do- | Santhipuram | Boyanapalli |  | 9.75 | 9.45 | M/s. chandu | 12-11-11
162 | -do- | Thottambedu | Pudi |  | 9 | 8.32 | Sri. K. Govinda Rajulu | 31.12.2015
163 | -do- | G.D. Nellore | Balaganganapalli |  | 9 | 9 | M/s. Seshachala | 06-12-11
164 | -do- | Bangarupalem | Tekumanda | 09.12.2010 | 9 | 8.72 | M/s. Prasad | 30.08.2014
165 | -do- | Ramakuppam | Pedduru |  | 9 | 8.87 | Sri. C. Murali Mohan | 10-11-11
166 | -do- | Vijayapuram | Sriharipuram |  | 9 | 8.73 | Sri. M. Bhaskar Reddy | 18-07-13
167 | -do- | Penumur | L.K.P.Vooru |  | 9 | 8.84 | Sri. M. Bhaskar Reddy | 11-11-11
168 | -do- | Peddapanjani | Peddavallagatturu |  | 9 | 9 | Sri. P. Sudhakar | 05-12-11
169 | -do- | Penumur | Pulikallu |  | 9 | 8.82 | Sri. M. Bhaskar Reddy | 10-12-11
170 | -do- | Ramakuppam | Saginekuppam |  | 9 | 9 | M/s. chandu Constructions. | 30-12-11
171 | -do- | KVB Puram | Kotamangapuram |  | 9 | 8.75 | Sri. Munichandra Reddy, | 30.09.2014
|  |  | Sub-total |  | 216.75 | 211.78
DISTRICT : ANANTAPUR
172 | ATP | Kambadur | Ramapuram | 09.12.2010 | 9 | 7.85 | Sri Sai Harijan | 31.01.2014
173 | -do- | Penukonda | Settipalli |  | 9 |  | Sri.R.Hanumantha Reddy. |  | RAS to be received
174 | -do- | Tadimarri | Dathithota |  | 9 | 8.21 | Sri.N.Bala Krishna. | 18-1-2013
175 | -do- | Kanekal | Garudachedu |  | 9 | 8.48 | Sri.G.Rajagopal Naidu. | 29-11-2011
176 | -do- | Peddavadugur | Appecherla |  | 9 | 7.99 | Sri.N.Ramudu, | 15-8-2012
177 | -do- | Agali | Inagalore |  | 9 |  | Sri.T.Darshan. |  | RAS to be received
178 | -do- | Rolla | Rathnagiri |  | 9 | 8.32 | Sri.T.Darshan. | 28-11-2012
179 | -do- | Amarapuram | S.Thammidepalli |  | 9 | 8.38 | Sri.B.Pulla Reddy. | 10-6-2013
180 | -do- | Bathalapalli | Dampetla |  | 9 | 8.27 | Sri.B.Muthyalappa. | 14-3-2012
181 | -do- | Puttaparthy | P.Kammavaripalli |  | 9 | 8.25 | Sri.D.Venkatadri. | 10-6-2013
182 | -do- | Amadaguru | Chinnaganipalli |  | 9 | 8.1 | Sri.B.Muthyalappa. | 26-11-2011
183 | -do- | Setturu | Kanakuru |  | 9 | 8.25 | Sri.V.Narendra Reddy | 31-3-2012
184 | -do- | Kundurpi | Apilepalli |  | 9 | 7.9 | Sri.V.Narendra Reddy | 30-4-2012
185 | -do- | Putluru | Yelukuntla |  | 14 |  |  |  | Site not handed over
186 | -do- | N.P.Kunta | Pedaballi |  | 9 | 8.39 | Sri.I.Govinda Naik. | 31-3-2013
187 | -do- | Kothacheruvu | Byrapuram |  | 9 | 7.53 | Sri.N.Bala Krishna. | 1-6-2011
188 | -do- | Roddam | M.Kothapalli | 09.12.2010 | 9 | 8.3 | Sri.M.Mohammad Basha. | 23-2-2012
189 | -do- | Gudibanda | S.Rayapuram |  | 14 |  |  |  | LOA issued. Agreement to be concluded.
190 | -do- | Bukkapatnam | Madirebylu |  | 9 | 8.28 | Sri.B.Sivaiah. | 24-3-2012
191 | -do- | Atmakur | Muttala |  | 9 |  | Sri.K.Suryanarayana Reddy |  | RAS to be received
192 | -do- | Beluguppa | Ankampalli |  | 9 | 8.28 | M/s.Nandan | 30-6-2012
193 | -do- | Madakasira | Y.Gundumala |  | 9 | 8.25 | Sri.G.Jayappa, | 29-11-2011
194 | -do- | Yadiki | Nagaruru |  | 9 |  | Sri.M.V.Bhaskar Reddy. |  | RAS to be received
|  |  | Sub-total |  | 217 | 139.03
DISTRICT : KADAPA
195 | YSR | (Kommaddi) Kokatam | (Kommaddi) Kokatam | 09.12.2010 | 14 | 13.16 | K.Jagannatha Reddy, | 31.07.2014
196 | -do- | Chinnaguravalur | Chinnaguravalur |  | 9 | 8.14 | S.Krishnarjuna Reddy, | 31.08.2013
197 | -do- | Kothacheruvu | Kothacheruvu |  | 9 | 8.14 | B.V.Subba Reddy, | 10.06.2012
198 | -do- | Balasingapalli | Balasingapalli |  | 9 | 8.22 | O.Vijaya Baskhar Reddy, | 07/2012
199 | -do- | Rajukunta | Rajukunta |  | 9 | 8.61 | A.Srinivasula, | 41091
200 | -do- | Pandillapalli | Pandillapalli |  | 9 | 8.26 | Alankanpalli | 22.05.2013
201 | -do- | Araveedu | Araveedu |  | 9 | 8.71 | K.Reddappa Reddy, | 41153
202 | -do- | Neelavaram | Neelavaram |  | 9 | 8.97 | S.Chandra Sekhar, Duvvur | 31.01.2014
203 | -do- | Rachayapeta | Rachayapeta | 09.12.2010 | 9 | 8.05 | N.Krishna Reddy, Badvel | 08/2012
204 | -do- | Chinnareddypalli | Chinnareddypalli |  | 9 | 7.88 | M.Yesurathnam | 09.07.2012
205 | -do- | Kommanuthala | Kommanuthala |  | 9 | 8.29 | D.Chandra Sekhar, | 09/2012
206 | -do- | Penikalapadu | Penikalapadu |  | 9 | 2.24 | P.Narapureddy | 31.03.2015 | Plinth beam laid work stopped due to court stayorder. Final bill paid
207 | -do- | Lekkalavaripalli | Lekkalavaripalli |  | 14 | 13.32 | P.Srinivasulu | 30.11.2014
208 | -do- | Edullapalli | Edullapalli |  | 9 | 8.62 | M.Yesurathnam | 12/2012
209 | -do- | Tangutoor | Tangutoor |  | 9 | 7.46 | N.Kulai Reddy, Mydukur | 09/2012
210 | -do- | (Nallguttapalli) Alladupalli | (Nallguttapalli) Alladupalli |  | 14 | 13.25 | B. Raja Sekhar Reddy, | 30.06.2014
211 | -do- | Machireddigaripalli | Machireddigaripalli | 09.12.2010 | 9 | 8.51 | K.V.Ramana Reddy, | 04.04.2013
212 | -do- | V.Koduru | V.Koduru |  | 9 | 7.49 | P.Nagamuni Chennur | 41244
213 | -do- | Gotur | Gotur |  | 9 | 7.8 | Havila Infrastructure, | 12/2012
214 | -do- | Balireddypally | Balireddypally |  | 14 | 13.02 | C.Venkata Subba Reddy, | 30.04.2015
215 | -do- | Botlacheruvu | Botlacheruvu |  | 9 | 8.7 | N.Sahadeva Reddy | 01.08.2013
216 | -do- | Laxmipet | Laxmipet |  | 9 | 8.56 | S.Krishnarjuna Reddy, | 09/2012
217 | -do- | Sambepalli | Peddabediki |  | 14 | 0 | J.V.Krishna Yadav, |  | Site Dispute
218 | -do- | Pullampeta | Annasamudram |  | 14 | 0 | J.V.Krishna Yadav, |  | Site to be identified
|  |  | Sub-total |  | 246 | 195.4
DISTRICT : KURNOOL
219 | KNL | Allagadda | P.Chinthakunta | 09.12.2010 | 9 | 8.67 | B.Manohar Rao | 20.12.2012
220 | -do- | Allagadda | R.Krishnapuram |  | 10.15 | 5.26 | S.B.Venkata Reddy | 31.12.2014
221 | -do- | Rudravaram | Muthalur |  | 9 | 8.81 | M.Sanjeeva Rayudu | 14.02.2012
222 | -do- | Rudravaram | Bethamcherla-IV |  | 14 | 0 |  |  | Earth Work excavation is in progress | 31.03.2016
223 | -do- | D. Venipenta | D.Vempenta |  | 10.5 | 7.87 | S.B.Venkata Reddy | 31.10.2012
224 | -do- | Nandyal | Chabolu |  | 10.22 | 8.47 | M.Gurrappa | 30.10.2013
225 | -do- | Jupadubunglow | Bennur |  | 9.56 | 8.97 | A.Syed Hussain | 30.07.2013
226 | -do- | Owk | Mettupalli |  | 10.5 | 8.31 | S.B.Venkata Reddy | 30.09.2012
227 | -do- | Pamulapadu | Mittakandala |  | 9.5 | 8.41 | A.Syed Hussain | 20.02.2013
228 | -do- | Sanjamala | Kanala |  | 14 | 5.5 | J.V. Narayana Reddy |  | Finishings are in progress | 31.03.2016
229 | -do- | Koilakuntla | Bheemunipadu |  | 9.36 | 8.96 | B.Manohara Rao | 24.12.2012
230 | -do- | Sirivella | Kotapadu |  | 9.34 | 8.66 | J.V.Narayana Reddy | 06.12.2011
231 | -do- | Sirivella | Mahadevapuram |  | 9 | 8.66 | J.V.Narayana Reddy | 06.12.2011
232 | -do- | Daivamdinne | K.Thimmapuram |  | 9.66 | 8.05 | V.Krishna | 05.02.2012
233 | -do- | Krishnagiri | Lakkasamudram |  | 9.66 | 8.94 | S.Gopal Reddy | 05.02.2013
234 | -do- | Orvakal | Meedivemula |  | 9 | 8.34 | G.K.Venganna | 27.03.2012
235 | -do- | Kothapalli | Sivapuram |  | 14 | 8.41 |  |  | Finishings are in progress | 31.03.2016
236 | -do- | Halaharvi | Chinthakunta | 09.12.2010 | 9.66 | 8.79 | P.Dasaratha Rami Reddy | 30.06.2013
237 | -do- | Dhone | Kocheruvu |  | 9.66 | 8.53 | V.Hanumadas | 30.10.2012
238 | -do- | Mahanandi | Mahanandi (M), Gangavaram |  | 9 | 8.66 | J.V.Narayana Reddy | 07.02.2012
239 | -do- | Rudravaram | Yellavattula |  | 9.68 | 8.66 | S.Venkatrami Reddy | 02.03.2012
|  |  | Sub-total |  | 214.45 | 164.93
|  |  | GRAND TOTAL |  | 2523.49 | 1817.139
|  | Add establishment charges@ 7% |  |  |  | 127.1997
|  | TOTAL : |  |  |  | 1944.3387

## Sheet3
Sl. No | Name of District | Block/Mandal | Name of Centre | AS / RAS (Rs. In lakhs) | Final Bill Paid /Not paid | Gros Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | Building Handed Over /Not Handed Over | Remarks
Handed Over
1 | 2 | 3 | 4 | 5 | 7 | 8 | 9 | 10 | 11
366 SCs
1 | SKLM | Siripuram | Chinakosta | 9.5 | Not Paid | 5.69 | 3.81 | No | Work terminated. New agency fixed for Balance work in favour of Sri V. Mohana Rao and balance work completed. Final bii under prepretion.
2 | VZNG | Gantyada | Lakkidam (Thadipudi) | 14 | Not Paid | 8.73 | 5.27 | No
3 | EG | Ramachandrapuram | Draksharamam | 9 | Paid | 8.47 |  | No | Occupied but not handed over.
4 | EG | Kapileswarapuram | Nalluru | 11 | Paid | 8.33 |  | No | Occupied but not handed over.
5 | EG | Kajuluru | Tanukuwada | 11 | Paid | 8.37 |  | No
6 | EG | Korukonda | Sri Rangapatnam-1 | 9 | Not paid. | 6.13 | 2.87 | No
7 | EG | Tuni | K.O.Mallavaram | 11 | Paid | 8.63 |  | No | Occupied but not handed over.
8 | EG | Kakinada rural | Suryaraopeta | 12 | Paid | 8.66 |  | No
9 | EG | Prathipadu | Peddipalem-1 | 11 | Paid | 8.41 |  | No | Occupied but not handed over.
10 | EG | Rangampeta | Singampalli | 11 | Paid | 6.98 |  | No
11 | EG | Gollaprolu | Dugrada-1 | 9 | Paid | 8.5 |  | No
12 | WG | BHIMAVARAM | Dongapindi | 11.4 | Not paid | 9.31 | 2.09 | No
13 | KRI | Nuzvid | Seetharamapuram | 11.38 | Paid | 9.88 |  | No
14 | KRI | Sagguru | Kommuru | 11.35 | Paid | 10.17 |  | No
15 | PKSM | Thripuranthakam | Mittapalem | 14 | Not paid | 3.79 | 10.21 | No | -
16 | PKSM | Kanigiri | Nanadanamaralla | 9 | Paid | 8.59 |  | No
17 | PKSM | Chirala | Devangapuri | 9 | Paid | 8.63 |  | No
18 | NLR | Rapur | Venadu | 14 | Not paid | 0 | 14 | No
19 | NLR | Rapur | Tegacherla | 14 | Not paid |  | 14 | No
20 | KDP | Tangutoor | Tangutoor | 9 | Not Paid | 7.46 | 1.54 | No
21 | KNL | Allagadda | R.Krishnapuram | 10.15 | Not Paid | 5.26 | 4.89 | No
366 SCs