## cov.p
Dt:19.01.2016
Construction of (151) Sub-Centre Building for the year 2011-12 under NRHM

## abs (hidden)
ABSTRACT
CONSTRUCTION OF NON-TRIBAL (151) SUB-CENTRE BUILDINGS FOR THE YEAR 2011-12 UNDER NRHM
Sl. No. | District | Administrative Sacntion amount (Rs. In lakhs) | No. of works | Status of works | [5 empty] | Expenditure (Rs. in lakhs) | Remarks | Remarks
|  |  |  | Site problem | Work not taken up | Tender stage | Work to be started | Work is in progress | Work completed
1 | Srikakulam | 36 | 4 |  |  |  |  | 2 | 2 | #REF!
2 | Vizianagaram | 72 | 8 | 5 |  |  | 2 | 1 |  | #REF!
3 | Visakhapatnam | 9 | 1 | 1 | [5 empty] | #REF!
4 | West Godavari | 81 | 9 |  |  | 2 | 7 |  |  | #REF!
5 | Krishna | 81 | 9 | 2 | 1 | 5 |  | 1 |  | #REF!
6 | Guntur | 99 | 11 | 3 |  | 1 |  | 7 |  | #REF!
7 | Prakasam | 54 | 6 | 6 | [5 empty] | #REF!
8 | Nellore | 54 | 6 | 3 |  |  |  | 3 |  | #REF!
9 | Chittoor | 90 | 10 | 5 | 1 |  |  | 4 |  | #REF!
10 | Ananthapur | 90 | 10 | 10 | [5 empty] | #REF!
11 | Kadapa | 81 | 9 | 3 |  |  |  | 6 |  | #REF!
12 | Kurnool | 108 | 12 | 9 |  |  |  | 3 |  | #REF!
13 | Mahaboobnagar | 36 | 4 |  | 1 |  |  | 2 | 1 | #REF! |  | Repeated (Boyalagudem)
14 | Ranga Reddy | 63 | 7 | 1 |  | 6 |  |  |  | #REF!
15 | Nalgonda | 108 | 12 |  |  |  | 12 |  |  | #REF!
16 | Medak | 117 | 13 |  |  |  | 6 | 7 |  | #REF!
17 | Nizamabad | 90 | 10 |  |  |  | 2 | 8 |  | #REF!
18 | Khammam | 9 | 1 |  |  | 1 |  |  |  | #REF!
19 | Karimnagar | 81 | 9 | 3 |  | 3 | 2 | 1 |  | #REF!
| Total | 1359 | 151 | 51 | 3 | 18 | 31 | 45 | 3 | #REF!

## abs monthwise
ABSTRACT
CONSTRUCTION OF NON-TRIBAL (151) SUB-CENTRE BUILDINGS FOR THE YEAR 2011-12 UNDER NRHM
Sl. No. | District | AS / RAS amount (Rs. In lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up (6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other dept | Site problem | RAS awaited or etc | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | SKLM | 38 | 34.77 |  | 4 |  |  |  |  | 4 | 4 |  |  | 4 |  | 4 |  | 0
2 | VZM | 100 | 86.22 | 4.62 | 8 |  |  |  |  | 8 | 8 |  |  | 7 | 1 | 7 | 1 | 1
3 | VSP | 14 | 0 | 14 | 1 |  |  |  |  | 1 |  | 1 |  |  | 1 |  | 1 | 0
4 | WG | 86 | 58.29 | 0.33 | 9 | 1 |  | 1 | 2 | 7 | 7 |  |  | 6 | 1 | 7 |  | 0
5 | KRI | 120.97 | 69.03 | 14 | 9 |  |  | 1 | 1 | 8 | 5 | 2 | 1 | 5 | 3 | 3 | 5 | 2
6 | GNT | 104 | 95.11 |  | 11 |  |  |  |  | 11 | 11 |  |  | 11 |  | 11 |  | 0
7 | PKSM | 84 | 16.67 | 39.33 | 6 |  | 3 |  | 3 | 3 | 2 |  | 1 |  | 3 | 1 | 2 | 1
8 | NLR | 69 | 48.81 | 7.29 | 6 |  |  |  |  | 6 | 6 |  |  | 5 | 1 | 5 | 1 | 1
9 | CTR | 115 | 55.67 | 3.22 | 10 |  | 3 |  | 3 | 7 | 6 |  | 1 | 5 | 2 | 5 | 2 | 1
10 | ATP | 140 | 66.65 | 74.47 | 10 |  |  |  | 0 | 10 | 6 |  | 4 | 3 | 7 | 5 | 5 | 1
11 | KDP | 106 | 58.55 | 29.46 | 9 |  | 1 |  | 1 | 8 | 5 | 1 | 2 | 5 | 3 | 5 | 3 | 0
12 | KNL | 132.12 | 75.38 | 46.35 | 12 | 0 | 0 |  |  | 12 | 9 |  | 3 | 8 | 4 | 8 | 4 | 1
| Total | 1109.09 | 665.15 | 233.07 | 95 | 1 | 7 | 2 | 10 | 85 | 69 | 4 | 12 | 59 | 26 | 61 | 24 | 8
1095.09
(Pullapathur) Mandapalli
(Thuvapalli) Mallepalli
(B.Kothapalli) Etur
(Padmatikona) Kongalaveedu
5.7

## 151
CONSTRUCTION OF NON-TRIBAL (151) SUB-CENTRE BUILDINGS FOR THE YEAR 2011-12 UNDER NRHM
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
SRIKAKULAM
1 | SKLM | Burja | Annampeta | .06.09.2011 | 9.5 | 8.87 | Sri P.V.S. Suryanarayana | 30.08.2013
2 | -do- | Rajam | Maredubaka |  | 9.5 | 8.83 | M/s.Sri Sitharama Constructions, | 30.6.2013
3 | -do- | Kaviti | Gorlapadu |  | 9.5 | 8.29 | Sri M.Laxmanarao | 30.6.2013
4 | -do- | Srikakulam | Ragolu |  | 9.5 | 8.78 | Sri P.V.S. Suryanarayana | 30.08.2013
|  |  | Sub-total |  | 38 | 34.77
VIZIANAGARAM
5 | VZM | Garividi | Bondapalli (G) | .06.09.2011 | 12 | 11.12 | Sri K.Chandra Naidu | 30.11.12
6 | -do- | Gurla | Gurla |  | 9 | 9 | V.Suryanarayana, | 31.01.2014
7 | -do- | Gajapathinagaram | Ginnam |  | 9 | 8.97 | T.Govinda Reddy, | 15.03.13
8 | -do- | Vepada | Chinagongada |  | 14 | 10.96 | M/s SCLC Co-Operative Society Ltd, | 31.07.2015
9 | -do- | Vepada | Gudivada |  | 14 | 11.1 | M/s SCLC Co-Operative Society Ltd, | 31.07.2015
10 | -do- | Salur | Sarika |  | 14 | 12.26 | Sri K.Rama krishna, salur | 30.11.2015
11 | -do- | G.L.Puram | Deruvada | 16.01.2013 | 14 | 22.81 | M/s Elixir Met Form Pvt Ltd | 15.10.13
12 | -do- | Kurupam | Voosakonda |  | 14 |  | M/s Elixir Met Form Pvt Ltd | 31.07.13
|  |  | Sub-total |  | 100 | 86.22
VISAKHAPATNAM
13 | VSP | Ravikamatam | Chinapachila | .06.09.2011 | 14 |  |  | …. | Tenders to be invited
|  |  | Sub-total |  | 14 | 0
WEST GODAVARI
14 | WG | Penugonda | Nadipudi | .06.09.2011 | 9 | 8.15 | G.Venkatesewara Rao | 30.06.2013
15 | -do- | Poduru | Poduru - 2 |  | 9 | 8.08 | G.Venkata Rao | 30.06.2013
16 | -do- | Yelamanchili | Y.V.Lanka |  | 9 | 8.32 | G.Venkata Rao | 30.06.2013
17 | -do- | Bhimavaram | Nagidipalem |  | 9 |  |  |  | Re tenders invited. Site available and RAS awaited
18 | -do- | Nidamarru | Adavikolanu |  | 9 | 8.02 | Y.Lakshmana Rao | 30.06.2013
19 | -do- | Unguturu | A.Gokavaram |  | 9 | 8.37 | Y.Lakshmana Rao | 30.06.2013
20 | -do- | Undi | Chilukuru |  | 9 | 8.68 | Y.Lakshmana Rao | 19.11.2014
21 | -do- |  | Kothapulasamarru |  | 9 | 8.67 | S.V.Bhagavan Rao | 30.06.2013
22 | -do- | J.R.Gudem | Taduvai | 16.01.2013 | 14 |  | - |  | Converted into PHC. Hence sub-center eliminated.
|  |  | Sub-total |  | 86 | 58.29
KRISHNA
23 | KRI | Jaggayyapeta | Bandipalem | .06.09.2011 | 11.3 | 0 |  |  | RAS to be required
24 | -do- | Gudlavalleru | Puritipadu |  | 14 | 8.55 |  |  | Plasterings are in progress | 31.03.2016
25 | -do- | Gudlavalleru | Vadlamannadu |  | 11.67 | 10.77 | Sri A.Subba Rao | 20-1-2014
26 | -do- | Agiripalli | Agniparru (Chinthalavalli) |  | 14 | 0 |  |  | Site available. Tenders to be called for
27 | -do- | Bantumilli | Mallampalli (Mallaparajugudem) |  | 14 | 12.72 |  | 30.06.2015
28 | -do- | VJA.(R). | Gudavalli | 16.01.2013 | 14 | 12.33 | M/s Elixir | 31.03.2014
29 | -do- | Thotalvalluru | Pamulanka |  | 14 | 12.33 | M/s Elixir | 31.01.2014
30 | -do- | Thotalvalluru | Yakamuru |  | 14 | 12.33 | M/s Elixir | 31.01.2014
31 | -do- | Musunuru | Chinnamupudi |  | 14 | 0 |  |  | Site available. Tenders to be called for
|  |  | Sub-total |  | 120.97 | 69.03
GUNTUR
32 | GNT | Atchempet(M) | Madipadu | .06.09.2011 | 14 | 12.06 | Sri M.Yeleswara Reddy. | 31.12.2014
33 | -do- | Chilakaluripet(M) | Veluru |  | 9 | 8.57 | Sri G.Srinivasa Rao, | 2012-02-11
34 | -do- | Nuzendla(M) | Mulakaluru |  | 9 | 8.16 | Sri K.V.Murali Haranath. | 2012-11-12
35 | -do- | Narasaraopet(M) | Dondapadu |  | 9 | 8.61 | Sri M.Yeleswara Reddy | 23-1-13
36 | -do- | Nakarikallu(M) | Chejerla |  | 9 | 8.56 | Sri M.Yeleswara Reddy | 15-11-12
37 | -do- | Karlapalem | Yazali |  | 9 | 6.96 | Sri P.Koteswara Rao, | 28.02.2014
38 | -do- | Cherukupalli(M) | Gudavalli |  | 9 | 8.41 | Sri K.Murali Krishna | 30-9-13
39 | -do- | Ponnuru(M) | Chintalapudi |  | 9 | 8.52 | Sri S.Lingeswara Rao | 2012-08-10
40 | -do- | Kakumanu(M) | Bodipalem |  | 9 | 8.54 | Sri J.Rajesh. | 30-7-13
41 | -do- | Amaravathi(M) | Mandepudi |  | 9 | 8.52 | M/s.Sri Srinivasa & Co., | 2012-02-11
42 | -do- | Karempudi(M) | Oppicherla |  | 9 | 8.2 | Sri A.Chenna Kesava Reddy | 31.01.2014
|  |  | Sub-total |  | 104 | 95.11
PRAKASAM
43 | PKSM | Ulavapadu | Ramaiahpatnam | .06.09.2011 | 14 |  | - | - | Agt. Concluded but not grounded. Alternative site to be identified as earlier site identified is in port limits
44 | -do- | C.S.Puram | DG Peta |  | 14 | - | - | - | Agt. Concluded but not grounded. Alternative site to be identified as earlier site identified is in port limits
45 | -do- | P.C.Palli | Marriguntupalli |  | 14 | - | - | - | Agt. Concluded but not grounded. Alternative site to be identified as earlier site identified is in port limits
46 | -do- | Kurichedu | Kalluru |  | 14 |  | - | - | Foundation work is in progress | 02.05.2016
47 | -do- | Tarlupadu | Kalujuvvalapadu |  | 14 | 10.14 | S.Harinath Reddy, | 31.07.2015
48 |  | Kanigiri | Pathapadu | 16.01.2013 | 14 | 6.53 | S.Harinath Reddy, | 31.07.2015
|  |  | Sub-total |  | 84 | 16.67
NELLORE
49 | NLR | Anantha sagaram | Pedamattikambampadu | .06.09.2011 | 9 | 8.34 | V. Bhaskar Reddy | 07-08-2013
50 | -do- | Chittamur | Raviguntapalem |  | 14 | 6.71 | Ch. Satish | 30.08.2014
51 | -do- | Dakkili | Siripuram |  | 9 | 8.58 | A. Niranjan Reddy | 29.09.2012
52 | -do- | S.R.Puram | Dekurapalli |  | 9 | 8.19 | K.V. Krishna Reddy | 12-11-2014
53 | -do- | Chillakur | Thikkavaram |  | 14 | 8.48 | V. Mallikarjuna | 16-10-2013
54 | -do- | Chillakur | Vudathavuripalem |  | 14 | 8.51 | V. Mallikarjuna | 19-10-2013
|  |  | Sub-total |  | 69 | 48.81
CHITTOOR
55 | CTR | Chinnagottigallu | Thippireddygari Palli | .06.09.2011 | 9 | 9 | Sri. K. Maheswara Reddy | 11-07-12
56 | -do- | Vayalapadu | Punugupalli (Pathegada ) |  | 14 |  |  |  | Site dispute
57 | -do- | Nindra | Therani |  | 9 | 8.89 | Sri. D. Venkatadri Naidu | 01-06-12
58 | -do- | Vedurukuppam | Allamadugu |  | 9 | 9 | Sri. D. Venkatadri Naidu | 24-05-12
59 | -do- | Piler | Bandlavanka (M.V.palli) |  | 14 | 10.78 | Sri. M. Bharath Kumar | 31.03.2015
60 | -do- | Kurabalakota | Pitchalavavaripalli |  | 9 | 9 | Sri. D. Ganesh Kumar | 16-10-12
61 | -do- | PTM | Maddiaiahgaripalli |  | 9 | 9 | Sri. D. Ganesh Kumar | 20-19-12
62 | -do- | Kalakada | Kadiravanicheruvu ( K.Doddipalli) |  | 14 |  |  |  | Site dispute
63 | -do- | Ramasamudram | Nariganipalli | 16.01.2013 | 14 |  |  |  | Site dispute
64 | -do- | Gudupalli | Gundlanayanapalli (Pogurupalli / Instead of Beagilipalli) |  | 14 |  | M/s. Elixir Met |  | Earth Work is in progress | 31.03.2016
|  |  | Sub-total |  | 115 | 55.67
ANANTAPUR
65 | ATP | Gutturu (M) | V.G.Palem | .06.09.2011 | 14 |  | Sri.Mutyalappa | -- | Brick work completed & Plastering is in progress | 31.03.2016
66 | -do- | Amadaguru | Jowkulakothapalli |  | 14 | 5.92 | -- | 30.11.2015
67 | -do- | Bommanahal | Bollanagudem |  | 14 | 6.01 | -- | -- | Finishings are in progress | 31.01.2016
68 | -do- | Bramhasamudram | Polepalli |  | 14 | 5.61 | -- | 30.09.2015
69 | -do- | Kanekal | Poolactierla |  | 14 | 6.3 |  |  | Brick Work & plasterings are in progress | 31.01.2016
70 | -do- | N.P.Kunta | Erududona |  | 14 |  | -- |  | Brick Work & plasterings are in progress | 31.01.2016
71 | -do- | Agali (M) and | Aludi | 16.01.2013 | 14 | 26.2 | Sri.K.Lakshmi Reddy. | 30.6.2014
72 | -do- | Kanaganipalli (M) | Kurlapalli |  | 14 |  | Sri.K.Lakshmi Reddy. | 30.06.2014
73 | -do- | D.Hirehal | Pulakurthi |  | 14 | 12.22 | M/s.Elixlr Met | 31.03.2014
74 | -do- | Gummagatta | Bupasamudram |  | 14 | 4.39 | Sri.G.Rajendra Reddy | 30.06.2015
|  |  | Sub-total |  | 140 | 66.65
KADAPA
75 | YSR | Rajampet | Mandapalli (Pullapathur) | 06.09.2011 | 14 |  |  |  | Tenders to be invited
76 | -do- | Bodeddulapalli | Bodeddulapalli |  | 14 | -- | N.Malleswara Reddy |  | Work stopped due to court stay order
77 | -do- | Boreddigaripalli | Boreddigaripalli |  | 9 | 8.49 | M.Narasimha Reddy | 23.04.2013
78 | -do- | PC.Palli | PC.Palli |  | 9 | 8.45 | M.V.Ramanjaneya | 03.05.2013
79 | -do- | Muthukur | Muthukur |  | 9 | 2.04 | N.Malleswara Reddy |  | Roof slab to be laid | 31.03.2016
80 | -do- | B.Mattam | Mallepalli (Thuvapalli) |  | 14 | 5.5 | M.V.Ramanjaneya |  | Finishings are in progress | 31.01.2016
81 | -do- | Khajipet | Etur (B.Kothapalli) |  | 14 | 12.94 | T.Amareswara Reddy | 31.01.2015
82 | -do- | Madithadu | Madithadu |  | 9 | 8.38 | Y.Dharma Raju | 04.04.2013
83 | -do- | Kongalaveedu | Kongalaveedu (Padmatikona) |  | 14 | 12.75 | P.Venkata Subba Reddy | 31.10.2014
|  |  | Sub-total |  | 106 | 58.55
KURNOOL
84 | KNL | Bethamcherla | R.S.Rangapuram | .06.09.2011 | 9.52 | 9.01 | S.Abdul Khadar | 30.01.2013
85 | -do- | Nandyal | Peddakottala |  | 9 | 8.35 | S.Venkatarami Reddy | 02.10.2012
86 | -do- | Halaharvi | Pedapadu /Gulyam |  | 14 | 0 | M.Srinivasa Reddy |  | Columns raised up to Plinth level. R.R.Masonary is in progress | 31.03.2016
87 | -do- | Peapully | Burugula |  | 9.35 | 8.67 | B.Seetharamanjaneyulu | 20.01.2013
88 | -do- | Kallur | Konganapadu |  | 9.65 | 9.13 | S.A.Basha | 30.09.2013
89 | -do- | Atmakur | Kurukunda |  | 10.15 | 8.34 | B.Chennaiah | 30.07.2013
90 | -do- | Kowthalam | Halvi | .06.09.2011 | 14 | 0 | M/s Sri Chakra Constructions |  | Footings to be laid | 29.05.2016
91 | -do- | Krishnagiri | Yerragudi |  | 9.45 | 5.1 | B.Seetha Ramanjaneyulu | 31.01.2014
92 | -do- | Koilakuntla | Gulladurthy |  | 10 | 8.27 | D.Hanumantha Reddy | 30.07.2013
93 | -do- | Kosigi | Kosigi (3) |  | 9 | 8.32 | K.Seetha Rami Reddy | 30.06.2013
94 | -do- | Kosigi | Kosigi (4) |  | 14 | 0 | M/s Sri Chakra Constructions |  | Foundation work is in progress | 29.05.2016
95 | -do- | Sanjamala | Perusamula | 16.01.2013 | 14 | 10.19 | M/s Elixlr Met Forms | 31.01.2014
|  |  | Sub-total |  | 132.12 | 75.38
|  |  | Grand Total |  | 1109.09 | 665.15
|  | Add establishment charges@ 7% |  |  |  | 46.5605
|  | TOTAL : |  |  |  | 711.7105

## 8
CONSTRUCTION OF NON-TRIBAL (151) SUB-CENTRE BUILDINGS FOR THE YEAR 2011-12 UNDER NRHM
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion
VIZIANAGARAM
1 | VZM | Salur | Sarika |  | 14 | 12.26 | Sri K.Rama krishna, salur | 30.11.2015
KRISHNA
25 | KRI | Gudlavalleru | Vadlamannadu |  | 11.67 | 10.77 | Sri A.Subba Rao | 20-1-2014
27 | KRI | Bantumilli | Mallampalli (Mallaparajugudem) |  | 14 | 12.72 |  | 30.06.2015
PRAKASAM
48 | PKSM | Kanigiri | Pathapadu | 16.01.2013 | 14 | 6.53 | S.Harinath Reddy, | 31.07.2015
|  |  | Sub-total |  | 14 | 6.53
NELLORE
50 | NLR | Chittamur | Raviguntapalem |  | 14 | 6.71 | Ch. Satish | 30.08.2014
CHITTOOR
59 | CTR | Piler | Bandlavanka (M.V.palli) |  | 14 | 10.78 | Sri. M. Bharath Kumar | 31.03.2015
ANANTAPUR
66 | ATP | Amadaguru | Jowkulakothapalli |  | 14 | 5.92 | -- | 30.11.2015
KURNOOL
91 | KNL | Krishnagiri | Yerragudi |  | 9.45 | 5.1 | B.Seetha Ramanjaneyulu | 31.01.2014