## Sheet2 (hidden)
ABSTRACT
Construction of Sub-centre buildings for the year 2011-12
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Tenders invited | Tenders to be invited | Site to be handed over | Others | Remarks
1 | Srikakulam | 99 | 11 | 7 | 3 | 1
2 | Vizianagaram | 162 | 18 | 8 | 5 | 5
3 | Visakhapatnam | 9 | 1 | 1 |  |  |  | Work to be grounded.
4 | East Godavari | 162 | 18 | 17 | 1 |  |  | Recall for one work.
5 | West Godavari | 126 | 14 | 13 |  |  | 1 | Sub-centre sanction not there in village Koppaka clarification from DM&HO awaited.
6 | Krishna | 216 | 24 |  | 6 | 18 |  | The estimates are above Rs.9.00 lakhs. Hence, orders waited for further action.
7 | Guntur | 189 | 21 | 7 | 7 | 6 | 1 | Rajupalem, Uppalpadu sub-centre overlapped Hence to be deleted.
8 | Prakasam | 180 | 20 | 18 |  | 2
9 | Nellore | 180 | 20 |  | 8 | 12
10 | Chittoor | 216 | 24 | 23 |  |  | 1 | Building already existing alternative proposals to be furnished.
11 | Kadapa | 216 | 24 |  | 23 |  | 1 | Double sanction one sub-centres Kadamasti.
12 | Ananthapur | 207 | 23 |  | 16 | 7
13 | Kurnool | 189 | 21 |  | 16 | 5
14 | Mahaboobnagar | 135 | 15 | 11 |  | 4
15 | Ranga Reddy | 162 | 18 |  |  | 18
16 | Medak | 243 | 27 | 27
17 | Nizamabad | 189 | 21 | 21 |  |  |  | Tenders invited and finalized.
18 | Adilabad | 90 | 10 |  | 10
19 | Karimnagar | 45 | 5 |  |  | 4 | 1 | Building already existing alternative proposals to be furnished.
20 | Warangal | 27 | 3 | 3 |  |  |  | Work to be grounded.
21 | Khammam | 63 | 7 |  | 7
22 | Nalgonda | 189 | 21 |  | 19 | 2
| TOTAL | 3294 | 366 | 156 | 121 | 84 | 5
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## cov.p
Dt:19.01.2016
Construction of (436) Sub- Center Buildigns for the Year 2012-13

## abs monthwise
ABSTRACT
Construction of (436) Sub-centre buildings for the year 2012-13
Sl.No. | District | AS/RAS amount (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up (6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other dept | Site problem | RAS awaited or etc | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | SKLM | 350 | 179.1 | 115.01 | 25 | 5 | 1 |  | 6 | 19 | 15 |  | 4 | 5 | 14 | 4 | 15
2 | VZM | 350 | 257.05 | 35.16 | 25 |  | 4 |  | 4 | 21 | 20 |  | 1 | 4 | 17 | 14 | 7
3 | VSP | 154 | 39.9 | 46.02 | 25 | 14 | 5 |  | 19 | 6 | 4 | 1 | 1 | 1 | 5 | 1 | 5
4 | EG | 336 | 135.48 | 168.47 | 25 | 1 | 1 |  | 2 | 23 | 10 | 3 | 10 |  | 23 |  | 23
5 | WG | 182 | 44.05 | 124.81 | 25 | 12 | 1 |  | 13 | 12 | 3 | 1 | 8 |  | 12 |  | 12
6 | KRI | 210 | 105.46 | 101.37 | 15 |  | 3 |  | 3 | 12 | 7 | 2 | 3 | 4 | 8 | 1 | 11
7 | GNT | 0 | 0 |  | 15 | 15 |  |  | 15 | 0
8 | PKSM | 196 | 8.28 | 56 | 14 |  | 9 |  | 9 | 5 |  | 1 | 4 |  | 5 |  | 5
9 | NLR | 350 | 188.2709 | 134.7587 | 25 |  | 1 |  | 1 | 24 | 18 |  | 6 | 10 | 14 | 9 | 15
10 | CTR | 171 | 91.81 | 37.71 | 14 |  | 3 |  | 3 | 11 | 9 |  | 2 | 6 | 5 | 6 | 5
11 | KDP | 182 | 137.65 | 10.85 | 13 |  | 1 |  | 1 | 12 | 11 |  | 1 | 11 | 1 | 11 | 1
12 | ATP | 350 | 142.94 | 206.88 | 25 |  | 1 |  | 1 | 24 | 10 | 2 | 12 | 4 | 20 | 6 | 18
13 | KNL | 350 | 184.89 | 185.66 | 25 |  |  |  | 0 | 25 | 13 |  | 12 | 2 | 23 | 3 | 22
| TOTAL | 3181 | 1514.8809 | 1222.6987 | 271 | 47 | 30 | 0 | 77 | 194 | 120 | 10 | 64 | 47 | 147 | 55 | 139
3111
70
280
[5 empty] | 352 | [5 empty] | 264
[5 empty] | 87 | [5 empty] | 27

## abs (hidden)
ABSTRACT
Construction of (366) Sub-centre buildings for the year 2010-11
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Status of works | [5 empty] | Expenditure (Rs.in lakes) | Remarks
|  |  |  | Site problem | Work not taken up | Tender stage | Work to be started | Work is in progress | Work completed
1 | Srikakulam | 99 | 11 |  |  |  | 1 | 8 | 2 | #REF! |  | 11
2 | Vizianagaram | 162 | 18 | 1 | 4 |  |  | 10 | 3 | #REF! |  | 18
3 | Visakhapatnam | 9 | 1 | [5 empty] | 1 | #REF! |  | 1
4 | East Godavari | 162 | 18 |  |  |  | 2 | 12 | 4 | #REF! |  | 18
5 | West Godavari | 126 | 14 |  |  | 1 | 2 | 11 |  | #REF! |  | 14
6 | Krishna | 216 | 24 | 4 |  | 15 | 2 | 3 |  | #REF! | RAS requested for 16 works and 4 recently proposed for RAS. | 24
7 | Guntur | 189 | 21 | 5 | 1 | 1 |  | 9 | 5 | #REF! |  | 21
8 | Prakasam | 180 | 20 | 8 |  |  |  | 12 |  | #REF! |  | 20
9 | Nellore | 180 | 20 | 6 |  | 1 | 1 | 9 | 3 | #REF! | 1 No. Revised Administrative approval requested. | 20
10 | Chittoor | 216 | 24 |  |  |  |  | 16 | 8 | #REF! |  | 24
11 | Ananthapur | 207 | 23 | 1 |  |  | 1 | 14 | 7 | #REF! |  | 23
12 | Kadapa | 216 | 24 | 2 |  |  | 2 | 17 | 3 | #REF! |  | 24
13 | Kurnool | 189 | 21 | 5 |  |  |  | 12 | 4 | #REF! |  | 21
14 | Mahaboobnagar | 135 | 15 |  |  |  |  | 6 | 9 | #REF! |  | 15
15 | Ranga Reddy | 162 | 18 |  | 1 |  | 1 | 13 | 3 | #REF! | Sub-centre work at Motukur was entrusted to PR Dept. and they have taken up the work. | 18
16 | Nalgonda | 189 | 21 |  |  |  | 3 | 16 | 2 | #REF! | 1 No. Location change. | 21
17 | Medak | 243 | 27 | 1 |  | 1 |  | 17 | 8 | #REF! | 1 No. RA awaited. | 27
18 | Nizamabad | 189 | 21 |  |  |  |  | 7 | 14 | #REF! |  | 21
19 | Warangal | 27 | 3 | [5 empty] | 3 | #REF! |  | 3
20 | Khammam | 63 | 7 |  | 6 |  |  | 1 |  | #REF! | 6 works to ITDA. | 7
21 | Karimnagar | 45 | 5 | 1 |  |  |  | 2 | 2 | #REF! |  | 5
22 | Adilabad | 90 | 10 | 1 | 1 |  |  | 5 | 3 | #REF! | 1 No. deleted. | 10
| TOTAL | 3294 | 366 | 35 | 13 | 19 | 15 | 200 | 84 | #REF! |  | 366
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## 436
Construction of (436) Sub-centre buildings for the year 2012-13
Sl. No. | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress |  | Tentative date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11
DISTRICT : SRIKAKULAM
1 | SKLM | L.N.Peta | Chorlangi | 28-06-2012 | 14 | 10.7 | Sri K.Ganapathi Rao, | 31.07.2015 |  | Completed
2 | -do- | Seethampeta | K.Veeragattam | 28-06-2012 | 14 | 10.5 | Sri B.Satya Raju | 31.07.2015 |  | Completed
3 | -do- | L.N.Peta | Kadagandi | 28-06-2012 | 14 | 10.12 | Sri K.Ganapathi Rao, | 31.08.2015 |  | Completed
4 | -do- | Donubai | Pedda Polla | 28-06-2012 | 14 | 12.82 | Sri V.V.L.N.Naidu, | 31.07.2015 |  | Completed
5 | -do- | Seethampeta | Kodisa | 28-06-2012 | 14 | 11.24 | Sri B.Satya Raju | 30.06.2015 |  | Completed
6 | -do- | Nandigam | Nowgam | 28-06-2012 | 14 | 12.79 | M.Harikrishna | 27.06.2015 |  | Completed
7 | -do- | Hiramandalam | Labba | 28-06-2012 | 14 | 9.52 | Sri K. Vykunta Rao | 30.09.2015 |  | Completed
8 | -do- | Budambo Colony | Bellupatia | 28-06-2012 | 14 | 8.77 | Sri V.Mohana Rao | 30.09.2015
9 | -do- | Siripuram | Budarasingi | 28-06-2012 | 14 | 8.63 | Sri V.Mohana Rao | 30.11.2015
10 | -do- | M.Singupuram | Vatapagu | 28-06-2012 | 14 | 11.38 | Sri V.Mohana Rao | 30.06.2015 |  | Tender Stage
11 | -do- | Chorlangi | Gulumuru | 28-06-2012 | 14 | 7.72 | Sri K. Vykunta Rao | 30.06.2015 |  | Tender Stage
12 | SKLM | Saravakota | Nowthala | 28-06-2012 | 14 | 12.79 | Sri G.Adinarayana, | 30.06.2015 |  | Completed
13 | -do- | Saravakota | Kidimi | 28-06-2012 | 14 | 12.59 | M/s.Suresh | 30.06.2015 |  | Completed
14 | -do- | K.KavitiBitiwada | K.Kaviti | 28-06-2012 | 14 | 5.4 | Srinivasa Murthy M |  | Plasterings are in progress | Completed | 31.01.2016
15 | -do- | Veeraghattam | K.Gumadam | 28-06-2012 | 14 |  |  |  | Site is in low laying area (Site problem) | Completed
16 | -do- | Bitiwada | Hussainpuram | 28-06-2012 | 14 | 3.01 | Srinivasa Murthy M |  | Columns upto roof level under progress. | Completed | 31.01.2016
17 | -do- | Nandigam | Pedda Guruvuru | 28-06-2012 | 14 | 12.75 | Sri M.Harikrishna | 30.06.2015 |  | Completed
18 | -do- | Annavaram | Velagavada | 28-06-2012 | 14 |  |  |  | Work taken up by ITDA | Site problem
19 | -do- | Donubai | Devanapuram | 28-06-2012 | 14 |  | V.V.L.N.Naidu |  | Foundation Level | Completed | 31.03.2016
20 | -do- | Veeraghattam | S.N.Puram | 28-06-2012 | 14 |  |  |  | Work taken up by ITDA | Brick work & Plasterings
21 | -do- | Budambo Colony | Cheep | 28-06-2012 | 14 |  | - |  | Work taken up by ITDA | Site Problem
22 | -do- | Baleru | M.K.Puram | 28-06-2012 | 14 | 10.27 | Sri K. Vykunta Rao | 30.06.2015 |  | Site Problem
23 | -do- | Kanchili | Sasanam | 28-06-2012 | 14 |  | - |  | Work taken up by ITDA | Site is in low laying area (Site problem)
24 | -do- | Budambo Colony | Kondalogam | 28-06-2012 | 14 | 8.1 | Sri V.Mohana Rao |  | Brick work completed & Plasterings are in progress. Contractor noticed for slow progress. (EoT sanctioned upto 31.07.15 further EoT applied upto 30.09.15) | Marking Given but site problem | 31.01.2016
25 | -do- | Nandigam | Dimidijola | 28-06-2012 | 14 |  | - |  | Work taken up by ITDA | Tender Stage
|  |  | Sub-total |  | 350 | 179.1
DISTRICT : VIZIANAGARAM
26 | VZNG | Parvathipuram | Gochekka | 28-06-2012 | 14 | 13.05 | T.Govinda Reddy | 15.02.2015
27 | -do- | Komarada | R.L.Puram Komarada | 28-06-2012 | 14 | 13 | T.Govinda Reddy | 31.01.2015
28 | -do- | Parvathipuram | Jamadala Bandaluppi | 28-06-2012 | 14 | 13 | T.Govinda Reddy | 08.11.2014
29 | -do- | Parvathipuram | Adduruvalasa Pedabondapalli | 28-06-2012 | 14 | 11.91 | T.Govinda Reddy | 30.06.2015
30 | -do- | Pachipenta | Kothavalasa Pachipenta | 28-06-2012 | 14 | 11.6 | K.Rama Krishna | 31.03.2015
31 | -do- | Pachipenta | Panchali under G.N.Peta | 28-06-2012 | 14 | 11.91 | B.Appala naidu | 31.08.2015
32 | -do- | Pachipenta | Gyrampeta Pachipenta | 28-06-2012 | 14 | 11.21 | K.Rama Krishna | 31.03.2015
33 | -do- | G.L.Puram | Kottaguda Thadikonda | 28-06-2012 | 14 | 12.64 | B.Sankarajogi Naidu | 30.06.2015
34 | -do- | Jiyyammavalasa | Dangabadra Jiyyammavalasa | 28-06-2012 | 14 | 12.31 | B.Sankarajogi Naidu | 30.06.2015
35 | -do- | B.J.Puram Jiyyammavalasa of Jiyyammavalasa | B.J.Puram Jiyyammavalasa | 28-06-2012 | 14 | 11.76 | B.Sankarajogi Naidu | 30.06.2015
36 | -do- | G.L.Puram | Dummangi Thadikonda of G.L.Puram | 28-06-2012 | 14 | 12.79 | B.Sankarajogi Naidu | 31.08.2015
37 | -do- | Kurupam | Rastakuntubai Regidi | 28-06-2012 | 14 | 12.58 | B.Sankarajogi Naidu | 30.06.2015
38 | -do- | Salur | Kandulapadam Mamidipalli | 28-06-2012 | 14 | 12.41 | K.Rama Krishna | 30.06.2015
39 | -do- | G.L.Puram | Manda Thadikonda | 28-06-2012 | 14 | 12.58 | B.Sankarajogi Naidu | 30.06.2015
40 | -do- | Salur | Sivarampuram Baguvalasa | 28-06-2012 | 14 | 11.15 | V.Adhinarayana | 31.07.2015
41 | -do- | Jiyyammavalasa | G.T.Vada Jiyyammavalasa | 28-06-2012 | 14 | 11.88 | B.Sankarajogi Naidu | 31.07.2015
42 | -do- | Kurupam | Pedaguttili Mondemkhallu | 28-06-2012 | 14 | 12.59 | B.Sankarajogi Naidu | 30.06.2015
43 | -do- | Makkuva | Kona Makkuva | 28-06-2012 | 14 | 12.17 | K.Rama Krishna | 31.07.2015
44 | -do- | Parvathipuram | K.Mulaga Dokiseela | 28-06-2012 | 14 | 11.49 | T.Govinda Reddy |  | Finishings are in progress. |  | 31.01.2016
45 | -do- | Komarada | Thulasivalasa Madalangi | 28-06-2012 | 14 | 12.48 | T.Govinda Reddy | 31.08.2015
46 | -do- | G.L.Puram | Rella Thadikonda | 28-06-2012 | 14 | 12.54 | B.Sankarajogi Naidu | 31.07.2015
47 | -do- | Makkuva | Kaviripalli Sambar | 28-06-2012 | 14 |  |  |  | Site not availeble
48 | -do- | Makkuva | Kasipatnam Makkuva | 28-06-2012 | 14 |  | K.Rama Krishna |  | Site not available
49 | -do- | Kurupam | Tompalapadu Neelakantapuram | 28-06-2012 | 14 |  | - |  | Site takenover.Tenders called for no response even (5th Call). (Not accessble) Addressed the District Medical and Health Officer,Vizianagaram to propose alternate location
50 | -do- | Kurupam | Babbidi Duddukhallu | 28-06-2012 | 14 |  | - |  | Site takenover.Tenders called for no response even (5th Call). (Not accessble) Addressed the District Medical and Health Officer,Vizianagaram to propose alternate location
|  |  | Sub-total |  | 350 | 257.05
DISTRICT : VISAKHAPATNAM
51 | VSP | Cheedikada | Konam | 28-06-2012 | 14 | 0 |  |  | Site to be handed over
52 | -do- | Narsipatnam | Pamulavaka | 28-06-2012 | 14 | 11.17 | A.Appala Naidu | 31.01.2015
53 | -do- | Bheemili | Chippada | 28-06-2012 | 14 | 0 |  |  | Site not handed over
54 | -do- | Nakkapalli | Pedabodigallam | 28-06-2012 | 14 | 9.25 | G.Appa Rao | 30.11.2015
55 | -do- | Chodavaram | Kandipalem | 28-06-2012 | 14 | 2.6 | S.Satyanarayana |  | Brick work is in progress |  | 31.01.2016
56 | -do- | Ravikamatham | Gompa | 28-06-2012 | 14 | 0 | P.Eswara Rao |  | Site to be handed over
57 | -do- | Parawada | Tanam | 28-06-2012 | 14 | 0 | Siddi Venkateswara Horticultural |  | Site handedover on 02.09.2015. Notice issued to the Agency to start the work
58 | -do- | Gajuwaka | Akkireddy palem - 1 | 28-06-2012 | 14 | 0 | Sri S.Ch.Sanyasi Rao |  | Site to be handed over
59 | -do- | Gajuwaka | Yarada | 28-06-2012 | 14 | 8.23 | T.Veera Reddy | 31.08.2015
60 | -do- | Pedagantyada | Duvvada | 28-06-2012 | 14 | 0 | S.Ch.Sanyasi Rao |  | site to be handed over
61 | -do- | Devrapalli | Chinagangavaram | 28-06-2012 | 14 | 8.65 | G.Appala Raju | 30.09.2015
62 | -do- | Ananthagiri | Jalada | 28-06-2012 |  |  |  |  | Not taken up
63 | -do- | Ananthagiri | Zeenabad | 28-06-2012 |  |  |  |  | Not taken up
64 | -do- | Ananthagiri | Koraparthi | 28-06-2012 |  |  |  |  | Not taken up
65 | -do- | Koyyuru | Palakajeedi | 28-06-2012 |  |  |  |  | Not taken up
66 | -do- | Koyyuru | Kongasingi | 28-06-2012 |  |  |  |  | Not taken up
67 | -do- | Koyyuru | Mampa | 28-06-2012 |  |  |  |  | Not taken up
68 | -do- | Koyyuru | Kommaika | 28-06-2012 |  |  |  |  | Not taken up
69 | -do- | G.Madugula | Nurmthi | 28-06-2012 |  |  |  |  | Not taken up
70 | -do- | G.Madugula | Gaduthuru | 28-06-2012 |  |  |  |  | Not taken up
71 | -do- | Paderu | Kakki | 28-06-2012 |  |  |  |  | Not taken up
72 | -do- | Hukumpeta | Olda | 28-06-2012 |  |  |  |  | Not taken up
73 | -do- | Hukumpeta | Gedhalapadu | 28-06-2012 |  |  |  |  | Not taken up
74 | -do- | G.K.Veedhi | Garimanda | 28-06-2012 |  |  |  |  | Not taken up
75 | -do- | Chinthapalli | Anjali Sanivaram | 28-06-2012 |  |  |  |  | Not taken up
|  |  | Sub-total |  | 154 | 39.9
DISTRICT : EAST GODAVARI
76 | EG | Kakinada Rural | Pagadalapeta | 28-06-2012 | 14 | 10.13 | R.S. Santharam, | 31.03.2015
77 | -do- | Pithapuram | Chitrada | 28-06-2012 | 14 | 11.72 | R. Suresh, | 31.03.2015
78 | -do- | Vetlapalem | Chandrampalem | 28-06-2012 | 14 | 11.63 | V.R. Kaleswara Rao. | 31.03.2015
79 | -do- | Kirlampudi | Veeravaram | 28-06-2012 | 14 | 5.02 | B. Polarao, | 31.07.2015
80 | -do- | Prathipadu | Pothuluru | 28-06-2012 | 14 | 3.49 | M. Rambabu, |  | Roof slab laid |  | 31.01.2016
81 | -do- | Tuni | D.Polavaram | 28-06-2012 | 14 | 5.09 | B. Polarao, | 30.09.2015
82 | -do- | Rajanagaram | Chakradwarabandam | 28-06-2012 | 14 | 2.66 | J. Srinivasa Rao, |  | Roof slab laid |  | 31.01.2016
83 | -do- | Dowleswaram | Thorredu | 28-06-2012 | 14 | 3.88 | J. Srinivasa Rao, |  | Brick work is in progress. |  | 31.01.2016
84 | -do- | Biccavolu | Balabhadrapuram | 28-06-2012 | 14 | 7.1 | M. Satyanarayana Reddy, Balabadrapuram. | 30.11.2015
85 | -do- | Mandapeta | Maredubaka | 28-06-2012 | 14 | 6.15 | R.S. Santharam | 31.03.2015
86 | -do- | Kajuluru | Seela (Dugguduru) | 28-06-2012 | 14 | …. |  |  | Tenders to be invited |  |  | Ts
87 | -do- | Mummidivaram | Balusutippa | 28-06-2012 | 14 |  | …. |  | 4 times tenders called for. But no bidders are participated. |  |  | Ts
88 | -do- | Amalapuram | Batnavilli | 28-06-2012 | 14 | …. | G. Satyanarayana |  | Site handed over, not feasible for constructions, too low laying area. |  |  | Sp
89 | -do- | Mamidikuduru | Mogalikuduru | 28-06-2012 | 14 | 11.48 | V.R. Kaleswara Rao | 31.03.2015
90 | -do- | Malikipuram | Kesanapalli | 28-06-2012 | 14 | 11.79 | V.R. Kaleswara Rao | 31.03.2015
91 | -do- | Alamuru | Madiki | 28-06-2012 | 14 |  | Sri Venkateswara Agencies |  | Roof laid. |  | 31.01.2015
92 | -do- | Gandepalli | Mallepalli | 28-06-2012 | 14 | 4.16 | …. |  | Columns raised upto roof level. |  | 31.01.2015
93 | -do- | Uppalaguptam | Kurmapuram (Uppalaguptam-1) | 28-06-2012 | 14 | …. | G. Satyanarayana |  | Tenders to be invited |  |  | Ts
94 | -do- | Maredumilli | D.V.Kota | 28-06-2012 |  | …. |  |  | Work taken up by ITDA |  |  | Nt
95 | -do- | Devipatnam | D.N.Palem | 28-06-2012 | 14 | 5.99 | K. Srinivas |  | Finishings are in progress. |  | 31.01.2015
96 | -do- | Y. Ramavaram | P.Vulumpadu | 28-06-2012 | 14 | 5.67 | K. Srinivas |  | Brick work completed, plasterings are in progress. |  | 31.01.2015
97 | -do- | R. Chodavaram | Kota | 28-06-2012 | 14 | 8.26 | K. Srinivas |  | Finishings are in progress. |  | 31.01.2015
98 | -do- | Rajavommangi | Vatangi | 28-06-2012 | 14 | 8.64 | K. Srinivas |  | Flooring Water Supply & Internal electrification is in progress |  | 31.01.2015
99 | -do- | Rajavommangi | Maredubaka | 28-06-2012 | 14 | 6.15 | K. Srinivas | 30.11.2015
100 | -do- | Rajavommangi | Chikilinta | 28-06-2012 | 14 | 6.47 | K. Srinivas. |  | Flooring Water Supply & Internal electrification is in progress |  | 31.01.2015
|  |  | Sub-total |  | 336 | 135.48
DISTRICT : WEST GODAVARI
101 | WG |  | Deva | 28-06-2012 | 14 | 5.87 | Y.Lakshmana Rao |  | Roof slab laid. |  | 31.01.2015
102 | -do- |  | D.R.Palem | 28-06-2012 | 14 | 5.79 | Sri.Y.Lakshmana Rao |  | Brick work & plastering is in progress |  | 29.02.2016
103 | -do- |  | Kavvagunta | 28-06-2012 | 14 | 10.52 | M/s Shanmukha consultency | 30.11.2015
104 | -do- |  | ilaparru | 28-06-2012 | 14 |  | Sri.Y.Lakshmana Rao |  | footings work in progress. |  | 31.03.2016
105 | -do- |  | Rayalam | 28-06-2012 | 14 | --- |  |  | The concerned Hon'ble MLA desired to design the sub-centre with 3 floors. Finalization of designs under preparation at H.O. |  |  | ts
106 | -do- |  | Juvvalapalem | 28-06-2012 | 14 |  | Sri.Y.Lakshmana Rao |  | Earth work in progress. |  | 31.03.2016
107 | -do- |  | Venkatarayapalem | 28-06-2012 | 14 | 8.69 | Sri.Y.Lakshmana Rao | 30.11.2015
108 | -do- |  | Dirusumarru | 28-06-2012 | 14 |  | Sri S.Satya Srinivas |  | Foundations work in progress. |  | 29.02.2016
109 | -do- |  | Kapavaram | 28-06-2012 | 14 | 2.5 | Sri G.Venkata Rao |  | Earth work in progress. |  | 29.02.2016
110 | -do- |  | Chittavaram | 28-06-2012 | 14 | 2.5 | Sri G.Venkata Rao |  | Earth work in progress. |  | 31.03.2016
111 | -do- |  | Prathikollalanka | 28-06-2012 | 14 | --- |  |  | Site not available
112 | -do- |  | Venkatapuram | 28-06-2012 | 14 | 8.18 | T. Mallayya | 30.11.2015
113 | -do- |  | Penumantra HQ | 28-06-2012 | 14 |  | Sri.Y.Lakshmana Rao |  | Earth work in progress. |  | 31.03.2016
114 | -do- |  | Veppalapadu | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
115 | -do- |  | Jainvarigudem | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
116 | -do- |  | Gurugumilli | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
117 | -do- |  | Aliveru | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
118 | -do- |  | Tatiyakulagudem | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
119 | -do- |  | P.Rajavaram | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
120 | -do- |  | Routhugudem | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
121 | -do- |  | Rachannagudem | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
122 | -do- |  | Puchikapadu | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
123 | -do- |  | Repalliwada | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
124 | -do- |  | Pragadavaram | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
125 | -do- |  | Buddalavarigudem | 28-06-2012 |  |  |  |  | Works are allotted to I.T.D.A. Department.
|  |  | Sub-total |  | 182 | 44.05
DISTRICT : KRISHNA
126 | KRISHNA |  | Kammavari palem | 28-06-2012 | 14 | 0.17 | Sri M.Srini vas Rao |  | The available site is insufficient
127 | -do- |  | Chivetikallu | 28-06-2012 | 14 | 0.17 | Sri M.Srini vas Rao |  | Agt. Concluded but not grounded. Identified site has to be handed over
128 | -do- |  | Venuturumilli | 28-06-2012 | 14 | 4.88 | P.Sobhanbabu |  | Roof laid. |  | 15.05.2016
129 | -do- |  | Kudapa | 28-06-2012 | 14 | 12.75 | M/s BKM constructions | 30.11.2015
130 | -do- |  | Obulapuram | 28-06-2012 | 14 | 0 | Sri K.Ashok reddy |  | Agt. Concluded but not grounded. Identified site has to be handed over
131 | -do- |  | Tarakaturu | 28-06-2012 | 14 | 10.87 | G.Subrah manyeswara Rao | 30.11.2015
132 | -do- |  | Mallachittur | 28-06-2012 | 14 | 0 | -- |  | Roof level |  | 31.01.2016
133 | -do- |  | Puchagadda | 28-06-2012 | 14 | 13.24 | Sri B.Madhu babu, | 30.06.2015
134 | -do- |  | Vakkalagadda | 28-06-2012 | 14 | 13.18 | Sri P.Sobhan babu | 30.06.2015
135 | -do- |  | Adapavaripalem | 28-06-2012 | 14 | 13.25 | Si B.Madhu babu, Hyd | 30.6.2015
136 | -do- |  | Thotlavalluru (North) | 28-06-2012 | 14 | 13.05 | M/s Hari zana Labour society | 30.06.2015
137 | -do- |  | Lingala/ (Thotlavalluru (South)) | 28-06-2012 | 14 | 0 | V.Nagendar |  | LOA issued
138 | -do- |  | Kanumolu | 28-06-2012 | 14 | 0 | P.Sobhanbabu |  | Agreement concluded.work to be started
139 | -do- |  | Velivolu | 28-06-2012 | 14 | 11.25 | P.Sobhan babu |  | Finishing stage |  | 31.01.2015
140 | -do- |  | Tatakuntla | 28-06-2012 | 14 | 12.65 | M/s BKM constructions | 30.11.2015
|  |  | Sub-total |  | 210 | 105.46
DISTRICT : GUNTUR
141 | GNT | Macherla | Koppunur | 28-06-2012 |  |  |  |  | Works entrusted to Panchayat Raj Department by District Collector, Guntur.
142 | -do- | Macherla | Chinthalatanda | 28-06-2012
143 | -do- | Macherla | Rayavaram | 28-06-2012
144 | -do- | Macherla | Jammalamadaka | 28-06-2012
145 | -do- | Veldurthi | Sirigiripadu | 28-06-2012
146 | -do- | Veldurthi | Mittamidapalle | 28-06-2012
147 | -do- | Veldurthi | Gottipalla | 28-06-2012
148 | -do- | Veldurthi | Veldurthi | 28-06-2012
149 | -do- | Veldurthi | Bodilaveedu | 28-06-2012
150 | -do- | Veldurthi | Gundlapadu | 28-06-2012
151 | -do- | Durgi | Durgi | 28-06-2012
152 | -do- | Durgi | Dharmavarm | 28-06-2012
153 | -do- | Durgi | Adigoppula-II | 28-06-2012
154 | -do- | Durgi | Kolagutla | 28-06-2012
155 | -do- | Durgi | Athmakuru | 28-06-2012
|  |  | Sub-total |  | 0 | 0
DISTRICT : PRAKASAM
156 | PKSM | Jarugumalli | Narasingolu | 28-06-2012 | 14 |  | K.V.Subba Rao |  | Earth work is in progress |  | 23.02.2016
157 | -do- | Addanki | Kalavakuru | 28-06-2012 | 14 |  |  |  | Agt. Concluded but not grounded. Alternative site to be identified as earlier site identified is not feasible for construction of building. |  |  | sp
158 | -do- | N.G.Padu | Uppugunduru-II | 28-06-2012 | 14 | 5 | V.Sundaraiah |  | Brick masonry in progress |  | 22.03.2016
159 | -do- | Tarlupadu | Tummalacheruvu | 28-06-2012 | 14 |  | S.P.Gorantlaiah |  | footings work in progress. |  | 09.03.2016
160 | -do- | Karamchedu | Kunkalamarru | 28-06-2012 | 14 |  |  |  | Site not handed over |  |  | sp
161 | -do- | B.Peta | Basinepalli | 28-06-2012 | 14 |  |  |  | do |  |  | sp
162 | -do- | Gudluru | Chimidithapadu | 28-06-2012 | 14 |  |  |  | do |  |  | sp
163 | -do- | L.Samudram | Pedapavani | 28-06-2012 | 14 | 3.28 | Ch.Srinivasa Reddy |  | Columns raised upto roof level |  | 17.02.2016
164 | -do- | Vetapalem | Nainapalli | 28-06-2012 | 14 |  |  |  | Site not handed over |  |  | sp
165 | -do- | Thallur | Boddikurapadu | 28-06-2012 | 14 |  |  |  | do |  |  | sp
166 | -do- | C.S.Puram | D.G.Peta | 28-06-2012 | 14 |  |  |  | do |  |  | sp
167 | -do- | Pamur | Kambaladinne | 28-06-2012 | 14 |  |  |  | do |  |  | sp
168 | -do- | Tripuranthakam | Medapi | 28-06-2012 | 14 |  |  |  | Agreement concluded work to be started. |  |  | Ts
169 | -do- | Ongole | Ulichi | 28-06-2012 | 14 |  |  |  | Site not handed over |  |  | sp
|  |  | Sub-total |  | 196 | 8.28
DISTRICT : NELLORE
170 | NLR | Dakkili | Devulapalli | 28-06-2012 | 14 | 11.7931 | P.R. Krishna Reddy | 31.03.2015
171 | -do- | Sullurpeta | Gopala Reddypalem | 28-06-2012 | 14 | 12.4613 | K.R.V. Raghava Reddy | 11-04-2015
172 | -do- | Chejarla | Kollapa Naidupalli | 28-06-2012 | 14 | 3.5047 | V. Mallikarjuna |  | Roof slab laid |  | 29.03.2016
173 | -do- | Sydapuram | Kommipadu | 28-06-2012 | 14 | 12.1459 | V. Mallikarjuna | 04-03-2015
174 | -do- | Chejarla | Mamuduru | 28-06-2012 | 14 | 6.4022 | K. Subba Rao | 31.07.2015
175 | -do- | Dakkili | Mopuru | 28-06-2012 | 14 | 12.7704 | V. Mallikarjuna | 04-03-2015
176 | -do- | Chejarla | Thurpu Kambampadu | 28-06-2012 | 14 | -- | OBMS Reddy |  | Site identified & Work started |  | 31.05.2016 | sp
177 | -do- | Sydapuram | Utukuru | 28-06-2012 | 14 | 12.8943 | V. Mallikarjuna | 08-04-2015
178 | -do- | SR Puram | Ayyavaripalli | 28-06-2012 | 14 | 5.9003 | K. Krishna Reddy | 31-07.2015
179 | -do- | Atmakur | Battepadu | 28-06-2012 | 14 | 11.9769 | D. Ayyappa Reddy | 31-03-2015
180 | -do- | Marripadu | Budawada | 28-06-2012 | 14 | 8.1023 | B. Ravindra Reddy | 31.08.2015
181 | -do- | Marripadu | DC Palli | 28-06-2012 | 14 | 2.5754 | Ch. Venkateswarlu Reddy |  | Brick Work & Plastering is in progress. |  | 31.01.2016
182 | -do- | Kondapuram | Gottigundala | 28-06-2012 | 14 | 10.63 | M/s A.R. Constructions | 31-07-2015
183 | -do- | AS Peta | Hasanapuram | 28-06-2012 | 14 | 7.2446 | K. Subba Rao | 30.09.2015
184 | -do- | Zaladanki | Jammalapalem | 28-06-2012 | 14 |  | M/s JRR Nirman & Co. |  | Site identified but could not be grounded due to local disputes in site handing over |  |  | sp
185 | -do- | Ananthasagaram | Lingamgunta | 28-06-2012 | 14 |  | B.V. Krishna Reddy |  | Foundation level |  | 31.03.2016
186 | -do- | AS Peta | Mahimaluru | 28-06-2012 | 14 |  | B.V. Krishna Reddy |  | Plinth beam level |  | 31.03.2016
187 | -do- | Marripadu | Nandavaram | 28-06-2012 | 14 | 8.46 | K. Ravi Sankar Reddy | 31-07-2015
188 | -do- | Duttalur | Rachavaripalli | 28-06-2012 | 14 | 11.3826 | K. Krishna Reddy | 30-06-2015
189 | -do- | Ananthasagaram | Revuru | 28-06-2012 | 14 | 11.9481 | B.V. Krishna Reddy | 31-07-2015
190 | -do- | Varikuntapadu | Rompidodla | 28-06-2012 | 14 | 4.7773 | B. Ramesh Babu |  | Water supply & Electrical works are in progress |  | 31.12.2015
191 | -do- | Ananthasagaram | Somasila | 28-06-2012 | 14 | 5.5828 | Y. Srinivasulu Reddy | 31-07-2015
192 | -do- | Vinjamuru | Tamidipadu | 28-06-2012 | 14 | 9.207 | B. Ramesh Babu | 31.03.2015
193 | -do- | Kaligir | Tellapadu | 28-06-2012 | 14 | 11.7186 | B. Ravindra Reddy | 15-12-2014
194 | -do- | Sangam | Vasili | 28-06-2012 | 14 | 6.7931 | K. Subba Rao | 30.09.2015
|  |  | Sub-total |  | 350 | 188.2709
DISTRICT : CHITTOOR
195 | CTR | Thamabalapalli | Renumakulapalli | 28-06-2012 | 9 | 9 | K. Reddeppa Reddy | 30.09.2014
196 | -do- | Thamabalapalli | Thamabalapalli | 28-06-2012 | 14 | 12.21 | N. Venkateswara Reddy | 30.04.2015
197 | -do- | Thamabalapalli | Kukkarajupalli | 28-06-2012 | 14 | 13.46 | K. Reddeppa Reddy | 30.04.2015
198 | -do- | P.T.M | Kammacheruvu | 28-06-2012 | 14 |  |  |  | Site dispute
199 | -do- | Thamabalapalli | Kannemadugu | 28-06-2012 | 14 | 13.34 | N. Venkateswara Reddy | 30.04.2015
200 | -do- | Peddamandyam | Bandirevu | 28-06-2012 | 14 | 12.89 | K. Reddeppa Reddy | 30.04.2015
201 | -do- | Gudupalli | Sanganapalli | 28-06-2012 | 14 | 4.62 | Sri. B.V. Prakash Reddy |  | Roof slab laid, brick work completed, plastering in progress |  | 31.03.2015
202 | -do- | Kuppam | Peddabangurunatham | 28-06-2012 | 14 | 6.43 | Sri. B.V. Prakash Reddy, |  | Finishing work are in progress |  | 31.01.2016
203 | -do- | Somala | Valligattala | 28-06-2012 | 9 | 9 | N. Tirumala Prakasam | 30.09.2014
204 | -do- | K.V.Palli | Marella | 28-06-2012 | 14 |  |  |  | work to be started after finalization of site
205 | -do- | Kalakada | Enugondapalem | 28-06-2012 | 9 | 3.78 | M. Mallikarjuna Reddy | 30.09.2015
206 | -do- | Kalakada | Modiyamvaripalli | 28-06-2012 | 9 | 3.32 | M/s. Sairam Constructions | 30.09.2015
207 | -do- | Vayalpadu | Vittalam | 28-06-2012 | 9 | 3.76 | M. Mallikarjuna Reddy | 30.09.2015
208 | -do- | Kalikiri | Pathegada | 28-06-2012 | 14 |  | K. Sreenivasa Kumar |  | work to be started after finalization of site
|  |  | Sub-total |  | 171 | 91.81
DISTRICT : KADAPA
209 | YSR | Khajipet | Thudamaladinne | 28-06-2012 | 14 | 12.94 | T.Amareswara Reddy, | 31.12.2014
210 | -do- | Khajipet | Rangapuam | 28-06-2012 | 14 | 13.01 | S.Chandra Sekhar | 31.12.2014
211 | -do- | Mydukuru | Settivaripalli | 28-06-2012 | 14 | 13.02 | N.Nagi Reddy, | 31.12.2014
212 | -do- | Badvel | Thiruvengalapuram | 28-06-2012 | 14 | 11.5 |  | 31.12.2014
213 | -do- | Chapadu | Annavaram | 28-06-2012 | 14 | 13.05 | P.V.Sudarshan Reddy, | 31.12.2014
214 | -do- | Chapadu | Badripuram | 28-06-2012 | 14 | 13.08 | B.Raja Sekhar Reddy | 31.12.2014
215 | -do- | Yerraguntla | Sirrajupalli | 28-06-2012 | 14 | 6.02 | G.Ramasubba Reddy | 31.12.2014
216 | -do- | Chitvel | Devamachupalli | 28-06-2012 | 14 | 3.15 | Sri M.Pandu Ranga Reddy |  | Roof slab to be laid |  | 31.01.2016
217 | -do- | Sambepalli | Rowthukunta | 28-06-2012 | 14 |  |  |  | Site problem
218 | -do- | Nandalur | Gundlur | 28-06-2012 | 14 | 12.87 | M.Pandu Ranga Reddy | 31.12.2014
219 | -do- | Duvvur | Gudipadu | 28-06-2012 | 14 | 13.49 | B.Raja Sekhar Reddy | 31.12.2014
220 | -do- | Gopavaram | Valleravaripalli | 28-06-2012 | 14 | 12.57 | G.Ramasubba Reddy | 31.12.2014
221 | -do- | Peddamudiyam | Peddapasupula | 28-06-2012 | 14 | 12.95 | B.Narasimha Reddy | 31.01.2015
|  |  | Sub-total |  | 182 | 137.65
DISTRICT : ANANTAPUR
222 | ATP | Singanamala | Korivipalli | 28-06-2012 | 14 |  | A.Eswar Reddy, |  | Site not available
223 | -do- | Guntakal | Venkatampalli | 28-06-2012 | 14 | 12.3 | K.P.Ranga Reddy | 30.06.2015
224 | -do- | Guntakal | Nakkanadoddi | 28-06-2012 | 14 | 12.43 | D.Ramachandra, | 30.06.2015
225 | -do- | Vajrakarur | Ganjikunta | 28-06-2012 | 14 | 6.52 | D.Ramachandra, |  | Brick Work & Plasterig is in progress. |  | 31.01.2015
226 | -do- | Kambadur | Kadiridevarapalli | 28-06-2012 | 14 | 12.4 | D.Venkatadri | 31.03.2015
227 | -do- | Kundurpi | Bandameeda palli | 28-06-2012 | 14 | 10.81 | D.Venkatadri | 30.09.2015
228 | -do- | Dharmavaram | Muthuvakunta | 28-06-2012 | 14 | 7.72 | Venkatadri | 30.09.2015
229 | -do- | Madakasira | P.Byadigera | 28-06-2012 | 14 |  |  |  | Tender Stage LOA issued.
230 | -do- | Madakasira | Kodipalli | 28-06-2012 | 14 | 7.12 | Suryanarayana | 31.05.2015
231 | -do- | Madakasira | Nidragatta | 28-06-2012 | 14 |  | Sri.K.Raja Prasad Reddy |  | Foundation work in progress. |  | 31.03.2016
232 | -do- | Amarapuram | Maddanakunta | 28-06-2012 | 14 | 5.44 | Ranganath |  | Brick Work & Plastering Plastering in progress |  | 31.03.2016
233 | -do- | Amarapuram | Halukuru | 28-06-2012 | 14 | 5.12 | Ranganath |  | Roof Level Super Structuer completed, Slab work is in progress. |  | 31.03.2016
234 | -do- | Gudibanda | Kummaranagepalli | 28-06-2012 | 14 |  | Ranganath |  | Plinth Beam completed. |  | 26.02.2016
235 | -do- | Gudibanda | Maddanakunta | 28-06-2012 | 14 |  | Ranganath |  | RR Masonry work is in progress. |  | 31.03.2016
236 | -do- | Gudibanda | Muthukur | 28-06-2012 | 14 |  | Sri.K.Raja Prasad Reddy |  | Tender Stage LOA issued. |  |  | Ts
237 | -do- | Rolla | Gudduguriki | 28-06-2012 | 14 | 5.76 | K.Raja Prasad Reddy |  | Brick Work & Plastering is in progress |  | 31.03.2016
238 | -do- | Rolla | Hottebetta | 28-06-2012 | 14 | 5.5 | K.Raja Prasad Reddy |  | Slab, Super Structure completed and further work in progress |  | 31.03.2016
239 | -do- | Talupula | Vepamanpeta | 28-06-2012 | 14 | 7.86 | Ramakrishn Reddy | 30.09.2015
240 | -do- | Talupula | Kurli | 28-06-2012 | 14 | 5.54 | P.Ramakrishna Reddy |  | Finishings are in progress |  | 31.01.2016
241 | -do- | Gandlapenta | Kamathampalli | 28-06-2012 | 14 | 8.05 | K.Ramaiah, | 30.09.2015
242 | -do- | N.P.Kunta | T.N.Palli | 28-06-2012 | 14 | 12.26 | K.Ramaiah, | 30.06.2015
243 | -do- | N.P.Kunta | Daniyancheruvu | 28-06-2012 | 14 | 7.76 | Ramakrishn Reddy | 30.09.2015
244 | -do- | Tanakal | G.N.Thanda | 28-06-2012 | 14 | 4.38 | T.Ramanaiah, |  | Finishings are in progress |  | 31.01.2016
245 | -do- | Tanakal | C.G.Project | 28-06-2012 | 14 | 5.65 | T.Ramanaiah, |  | Finishings are in progress |  | 31.01.2016
246 | -do- | O.D.Cheruvu | Eddulavaripalli | 28-06-2012 | 14 | 5.86 | Ramakrishn Reddy |  | Finishings are in progress |  | 31.01.2016
|  |  | Sub-total |  | 350 | 142.94
DISTRICT : KURNOOL
247 | KNL | Adoni | Kuppagal | 28-06-2012 | 14 | 9.64 | N.Rajendra Prasad, | 31.01.2015
248 | -do- | Adoni | Arekal | 28-06-2012 | 14 | 12.64 | M.Nazeer Basha, | 31.01.2015
249 | -do- | Adoni | Kadithota | 28-06-2012 | 14 | 9.87 | N.Rajendra Prasad | 30.03.2015
250 | -do- | Adoni | Thagaradona | 28-06-2012 | 14 | 5.7 | N.Chandra Kanth Prasad, |  | Finishings are in progress |  | 31.01.2016
251 | -do- | Adoni | Basaladoddi | 28-06-2012 | 14 | 7.02 | C.Giridhar Reddy, |  | Finishings are in progress |  | 31.01.2016
252 | -do- | Kowthalam | Nadichagi | 28-06-2012 | 14 | 11.29 | M.Nazeer Basha, | 01.08.2014
253 | -do- | Kowthalam | Gotuladoddi | 28-06-2012 | 14 | 7.02 | V.Venkateswar Reddy, |  | Brick work & plastering is in progress |  | 31.01.2016
254 | -do- | Kowthalam | Kumbalanur | 28-06-2012 | 14 | 7.04 | S.Veeresh, |  | Finishings are in progress |  | 31.01.2016
255 | -do- | Kowthalam | Urukunda | 28-06-2012 | 14 | 11.48 | V.Venkateswar Reddy, | 30.03.2015
256 | -do- | Kowthalam | Chudi | 28-06-2012 | 14 | 7 | S.Veeresh, |  | Finishings are in progress |  | 31.01.2016
257 | -do- | Kowthalam | Yerigeri | 28-06-2012 | 14 | 11.32 | V.Venkateswar Reddy, | 30.06.2015
258 | -do- | kosigi | Kosigi-1 | 28-06-2012 | 14 | 11.85 | B.Aleem Miah, | 01.08.2014
259 | -do- | kosigi | Kosigi-11 | 28-06-2012 | 14 | 11.83 | B.Aleem Miah, | 01.08.2014
260 | -do- | kosigi | D.Belgal | 28-06-2012 | 14 | 0 | B.Aleem Miah, |  | Columns raised up to Plinth level. R.R.Masonary completed up to basement level |  | 30.04.2016
261 | -do- | kosigi | Kandukur | 28-06-2012 | 14 | 4.68 | V.Venkateswar Reddy, |  | Brick masonry work is in progress |  | 31.01.2016
262 | -do- | kosigi | Sajjalagudem | 28-06-2012 | 14 | 0 | V.Venkateswar Reddy, |  | Earth work completed |  | 30.03.2016
263 | -do- | kosigi | Duddi | 28-06-2012 | 14 | 11.54 | V.Venkateswar Reddy, | 30.11.2015
264 | -do- | kosigi | Vandagal | 28-06-2012 | 14 | 11.95 | M.Nazeer Basha, | 30.03.2015
265 | -do- | Pedda kadubur | Rangapuram | 28-06-2012 | 14 | 11.26 | N.Chandra Kanth Prasad, | 15.11.2014
266 | -do- | Pathikonda | Hosur (Kallukunta) | 28-06-2012 | 14 | 0 | V.Venkateswar Reddy, |  | Roof laid. |  | 26.05.2016
267 | -do- | Pedda kadubur | Chinna Thumbalam | 28-06-2012 | 14 | 11.2 | N.Rajendra Prasad, | 31.01.2015
268 | -do- | Pedda kadubur | H.Muravani | 28-06-2012 | 14 | 0 | V.Venkateswar Reddy, |  | Columns raised up to basement level. R.R.Masonary is in progress |  | 30.04.2016
269 | -do- | Pedda kadubur | Doddi Mekala | 28-06-2012 | 14 | 0 | V.Venkateswar Reddy, |  | Plinth beam is in progress |  | 30.04.2016
270 | -do- | Molagavelli | Joharapuram | 28-06-2012 | 14 | 10.56 | P.Dasaratha Rami Reddy, | 30.04.2015
271 | -do- | Gajjahalli | Hebbatam (Vandavagili) | 28-06-2012 | 14 | 0 | K.Sreedhar Reddy, |  | Earth work completed |  | 12.05.2016
|  |  | Sub-total |  | 350 | 184.89
|  |  | GRAND TOTAL |  | 3181 | 1514.8809