## COVP
Dt:19.01.2016
Construction of (94) Primary Health Centres for the year 2012-13

## abs
ABSTRACT
Construction of (94) Primary Health Centres for the year 2012-13
S.NO | District | AS/RAS (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up (6-10) | Stage of takenuo works |  |  | Final bill |  | Building
[6 empty] | Taken up by other department | Site problem | Tender stage (RAS awaited or etc) | Total (7+8+9) |  | Completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13 | 14 | 15 | 16 | 17
1 | SKLM | 342.5 | 57.69 |  | 5 | 0 | 0 | 4 | 4 | 1 | 1 |  |  | 1 | - |  | 1
2 | VZM | 68.5 | 63.14 |  | 1 | 0 | 0 | 0 | 0 | 1 | 1 |  |  | 1 | 0 | 1 | 0
3 | VSP | 548 | 127.63 |  | 8 | 6 | 0 | 0 | 6 | 2 | 2 |  |  | 2 |  | 2
4 | EG | 685 | 558.53 | 88.65 | 10 | 0 | 0 | 0 | 0 | 10 | 9 |  | 1 | 6 | 4 | 4 | 6
5 | WG | 274 | 168.7 | 99.58 | 4 |  |  |  |  | 4 | 3 |  | 1 | 1 | 3 | 2 | 2
6 | KRI | 411 | 216.62 | 40.42 | 6 |  |  | 2 | 2 | 4 | 4 |  |  | 2 | 2 | 3 | 1
7 | GNT | 548 | 389.35 | 124.52 | 8 |  |  | 1 | 1 | 7 | 6 |  | 1 | 5 | 2 | 3 | 4
6 | PKSM | 274 | 136.92 | 68.58 | 4 |  | 1 |  | 1 | 3 | 3 |  |  | 1 | 2 | 1 | 2
7 | NLR | 548 | 383.0267 | 131.8605 | 8 |  |  |  |  | 8 | 8 |  |  | 2 | 6 | 4 | 4
8 | CTR | 274 | 184.86 |  | 4 |  | 1 |  | 1 | 3 | 3 |  |  | 3 |  | 3
7 | KDP | 205.5 | 133.4 | 59.47 | 3 |  |  |  |  | 3 | 3 |  |  | 1 | 2 | 2 | 1
8 | KNL | 479.5 | 398.33 | 41.34 | 7 | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 4 | 3 | 6 | 1
| Grand Total | 4658 | 2818.1968 | 654.4205 | 68 | 6 | 2 | 7 | 15 | 53 | 50 |  | 3 | 29 | 24 | 31 | 22
94
454
[7 empty] | 204 |  | 94
218

## details
Construction of (94) Primary Health Centres for the year 2012-13
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
SRIKAKULAM
1 | SKLM | Narasannapeta (M) | Urlam | 31.08.2012 | 68.5 | 57.69 | M/s.Sai nath Enterprises | 31.12.2014
2 | -do- | Lavaru | Venakatapuram |  | 68.5 |  |  |  | Revised proposals were submitted to the PIP for Rs.124 Lakhs for each work. RAS is awaited.
3 | -do- | Kaviti | Manikyapuram |  | 68.5 |  |  |  | -do-
4 | -do- | Kaviti | Rajapuram |  | 68.5 |  |  |  | -do-
5 | -do- | Laveru | Laveru (LMD Colony) |  | 68.5 |  |  |  | -do-
|  |  | Sub-total |  | 342.5 | 57.69
VIZIANAGARM
6 | VZM | Ramabhadrapuram | Arakithota | 31.08.2012 | 68.5 | 63.14 | Sri K.Chandra Naidu, | 31.05.2014
|  |  | Sub-total |  | 68.5 | 63.14
VISAKHAPATANAM
7 | VSP |  | Sunkarametta | 31.08.2012 | 68.5 |  |  |  | transfer the work Tribal Welfare Dept.
8 | -do- |  | U.Cheedipalem |  | 68.5
9 | -do- |  | Sileru |  | 68.5
10 | -do- |  | Korukonda |  | 68.5
11 | -do- |  | Pedavalasa |  | 68.5
12 | -do- | Anakapalli | Tagarampudi |  | 68.5 | 64.08 | Sri Bh.Ramakrishana | 30.11.2014 |  |  | 411
13 | -do- | Chinagadhili | Maduruwada |  | 68.5 | 63.55 | _do_ | 30.11.2014
14 | -do- |  | R.V.Nagar |  | 68.5 |  |  |  | transfer the work Tribal Welfare Dept.
|  |  | Sub-total |  | 548 | 127.63
EAST GODAVARI
15 | EG | Zeddangi | Zeddangi | 31.08.2012 | 68.5 | 63.41 | Sri.DV Subbaraju | 17.08.2014
16 | -do- | Rajavommangi | Rajavommangi |  | 68.5 | 63.12 | _do_ | 02.11.2014
17 | -do- | Maredumilli | Maredumilli |  | 68.5 | 7.5 | Sri Venkateswara Agency | 31.03.2015 | Columns raised upto roof level. Work stopped by the Contrator. Final notice issued to Contractor.
18 | -do- | Veeravaram | Veeravaram |  | 68.5 | 63.33 | RS Santha Ram | 09.11.2014
19 | -do- | Virava | Virava |  | 68.5 | 59.93 | G Satya Sudeer | 30.09.2014
20 | -do- | Lakkavaram | Lakkavaram |  | 68.5 | 60.88 | Sri Satya Narayana | 31.08.2014
21 | -do- | Nagaram | Nagaram |  | 68.5 | 60.76 | Villa Rama Kaleswara Rao | 31.08.2014
22 | -do- | Nagulapalli | Nagulapalli |  | 68.5 | 57.04 | Sri Surya Rama Constructions | 31.01.2015
23 | -do- | Mallam | Mallam |  | 68.5 | 61.58 | RS Santha Ram | 11.10.2014
24 | -do- | U.Kothapalli | U.Kothapalli |  | 68.5 | 60.98 | Y Prakash Rao | 31.08.2014
|  |  | Sub-total |  | 685 | 558.53
WEST GODAVARI
25 | WG | Poalavaram | L.N.D.Peta | 31.08.2012 | 68.5 | 18.12 | G. Srinivasa Reddy |  | Slab work in progress. | 31.03.2016
26 | -do- | Jeelugumilli | Jeelugumilli |  | 68.5 | 42.11 | M/s.R.Gangaiah | 31.07.2015
27 | -do- | Eluru Rural | Gudiwadalanka |  | 68.5 | 62.78 | CH.Ratnakara Rao, Nuzvid | 30.06.2014
28 | -do- | Kamavarapukota | Kamavarapukota |  | 68.5 | 45.69 | M/s.Sachin build Tech , Vizag | 27.11.2015
|  |  | Sub-total |  | 274 | 168.7
KRISHNA
29 | KRI | Challapalli | Puritigadda | 31.08.2012 | 68.5 | 55.76 | Md.Haleem khan, Khammam | 31.03.2015
30 | -do- | Pamidimukkala | Kaplieswarapuram |  | 68.5 | 59.21 | M/s Sri construc- tions, VJA | 31.07.2014
31 | -do- | Unguturu | Indupalli |  | 68.5 | 0.23 | M/s Sri construc- tions, VJA |  | Revised proposals were submitted to the PIP for Rs.124 Lakhs for each work. RAS is awaited.
32 | -do- | Pammarru | Pammarru |  | 68.5 | 60.6 | Sri P.Madhu babu, Hyd | 31.07.2014
33 | -do- | Kaikaluru | Kolletikota | 31.08.2012 | 68.5 | -- | -- |  | Revised proposals were submitted to the PIP for Rs.124 Lakhs for each work. RAS is awaited.
34 | -do- | Kaikaluru | Seethanapalli |  | 68.5 | 40.82 | BKM constructions | 31.11.2015
|  |  | Sub-total |  | 411 | 216.62
GUNTUR
35 | GNT | Durgi | Durgi | 31.08.2012 | 68.5 | 62.75 | Sri K.Srinivasu, | 31.05.2014
36 | -do- | Repalli(M) | Mollagunata |  | 68.5 | 31.37 | Sri B. Rama Krishna. |  | Finishings in progress | 31.12.2015
37 | -do- | Dachepalli | Dachepalli |  | 68.5 | 59.54 | Sri B.Venkata Reddy. | 31.05.2014
38 | -do- | Piduguralla | Piduguralla |  | 68.5 | 0.13 | Sri R.Radha Krishna Murthy. |  | As the identified site is very low lying. Revised Estimate for Rs. 134.50 lakhs submitted for obtaining Revised Administrative sanction.
39 | -do- | Pedakakani(M) | Venigandla |  | 68.5 | 58.6 | Sri J.Srinviasa Rao | 03.03.2014
40 | -do- | Piduguralla(M) | Karlapadu |  | 68.5 | 49.48 | Sri B.Venkata Reddy. | 20.04.2015
41 | -do- | Rompicherla | Rompicherla |  | 68.5 | 63.59 | Sri B.Venkata Reddy. | 31.12.2014
42 | -do- | Bollapalli | Vellaturu (Alternate place Daroor Camp in Karim nagar Dist) |  | 68.5 | 63.89 | Sri B.Venkata Reddy | 31.07.2015
|  |  | Sub-total |  | 548 | 389.35
PRAKASAM
43 | PKSM | Ballikurava | Guntupalli | 31.08.2012 | 68.5 | 27.93 | D.Bhaskara Rao | 30.09.2015
44 | -do- | N.G.Padu | Pothavaram |  | 68.5 |  | V Sundaraiah |  | Site to be handed over. Revised proposals were submitted to the PIP for Rs.124 Lakhs for each work. RAS is awaited.
45 | -do- | N.G.Padu | Thimmasamudram |  | 68.5 | 52.4 | V Sundaraiah | 31.07.2015
46 | -do- | Martur | Dronadula |  | 68.5 | 56.59 | V Sundaraiah | 31.08.2014
|  |  | Sub-total |  | 274 | 136.92
NELLORE
47 | NLR | Dagadarthi | Thurimerla | 31.08.2012 | 68.5 | 45.35 | K. Ramesh, Kavali | 31.08.2014
48 | -do- | Chittamur | Gunapatipalem |  | 68.5 | 48.7792 | Venugopal Reddy | 20-10-2014
49 | -do- | Vakadu | Chinthota |  | 68.5 | 46.1205 | M/s AR Constructions | 31.07.2015
50 | -do- | Vidavalur | Vidavalur |  | 68.5 | 41.1744 | J.V.Rama Rao | 28-03-2014
51 | -do- | S.R.Puram | S.R.Puram |  | 68.5 | 51.4788 | Ch. Venkates-warlu Reddy | 31.03.2015
52 | -do- | Marripadu | Marripadu |  | 68.5 | 34.2193 | Ch. Venkates-warlu Reddy | 28-03-2014
53 | -do- | Bogolu | Kovurpalli |  | 68.5 | 52.4085 | M. Srinivasulu Reddy | 28-03-2014
54 | -do- | Chillakur | vallipedu |  | 68.5 | 63.4961 | N.Venu Gopal Reddy | 31.08.2015
|  |  | Sub-total |  | 548 | 383.0267
CHITTOR
55 | CTR | Tirupati Rural | Mangalam | 31.08.2012 | 68.5 | 59.54 | M/s Sumasri constructions | 30.09.2014
56 | -do- | Gurramkonda | Gurramkonda |  | 68.5 | 61 | Sri. G. Chakrapani Reddy | 31.01.2015
57 | -do- | Gudipala | Bommasamudram |  | 68.5 | 64.32 | Sri. Sindhu Constructions | 31.03.2015
58 | -do- | Nagalapuram | Nagalapuram (Kuppam Baduru) |  | 68.5 |  |  |  | Revised proposals were submitted to the PIP for Rs.124 Lakhs for each work. RAS is awaited.
|  |  | Sub-total |  | 274 | 184.86
KADAPA
59 | YSR |  | P.Kothapalli | 31.08.2012 | 68.5 | 55.87 | Sri A.V.Mohan Reddy | 30.06.2014
60 | -do- |  | Palagurrallapalli |  | 68.5 | 50.9 | M/s. VSSR Constructions | 30.11.2014
61 | -do- |  | Narsapuram (In place of KC Canal’ in Karimnagar district) |  | 68.5 | 26.63 | Sri A.V. Mohan Reddy | 27.11.2015
|  |  | Sub-total |  | 205.5 | 133.4
KURNOOL
62 | KNL | Srisailam | Srisailam | 31.08.2012 | 68.5 | 56.25 | V.Hanuman Das | 31.03.2015
63 | -do- | Velugodu | Mothkur (Velutodu Tribal) |  | 68.5 | 57.33 | Rambhupal Reddy | 01.03.2015
64 | -do- | Atmakur | Bairluty |  | 68.5 | 56.1 | B.Aleem Miah | 31.07.2014
65 | -do- |  | Gajulapally (Molagavelli) |  | 68.5 | 55.92 | N Gopal reddy | 31.07.2014
66 | -do- | Rudvaram | Yerraguntla |  | 68.5 | 62.4 | G Raj gopal reddy | 01.08.2014
67 | -do- | Owk | Uppalapalem |  | 68.5 | 50.58 | D.Dastagiri | 31.03.2015
68 | -do- | Pagidala | Parthakota |  | 68.5 | 59.75 | Ranga swamy | 31.07.2014
|  |  | Sub-total |  | 479.5 | 398.33
|  |  | Grand total |  | 4658 | 2818.1968
|  | Add establishment charges@ 7% |  |  |  | 197.2738
|  | TOTAL : |  |  |  | 3015.4705
`