## 20 beds abs (hidden)
ABSTRACT
Construction of 20 Bed Special Care Newborn Units (SCNUs) for the year 2011-12 (Phase-1)
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Status of works |  |  |  | Expenditure (Rs.in lakes) | Remarks
|  |  |  | Site problem | Work to be started | Work is in progress | Work Completed
1 | Srikakulam | 38 | 1 |  | 1 |  |  | 0
2 | Vizianagaram | 38 | 1 |  |  |  | 1 | 37.9
3 | Visakhapatnam | 38 | 1 |  |  |  | 1 | 33
4 | East Godavari | 76 | 2 |  |  |  | 2 | 34.98
5 | West Godavari | 38 | 1 |  |  | 1 |  | 35.47
6 | Krishna | 38 | 1 |  |  | 1 |  | 25.22
7 | Guntur | 38 | 1 |  |  |  | 1 | 35.25
8 | Prakasam | 38 | 1 |  |  | 1 |  | 36.92 | Not handed over RIMS authorities.
9 | Nellore | 38 | 1 |  |  |  | 1 | 33.32
10 | Chittoor | 38 | 1 |  |  | 1 |  | 35.24 | Requesting for new building, since space is not available in the existing building. RAS requested either for Rs.46.50 or 96.00 vide this office Lr.No.1407/APMSIDC/HQ/NRHM/2010-11 /Kadapa/ 3769, dt.03.09.11.
11 | Ananthapur | 38 | 1 |  |  | 1 |  | 25.47
12 | Kadapa | 38 | 1 |  |  |  | 1 | 29.62
13 | Kurnool | 38 | 1 |  |  | 1 |  | 35.43
14 | Mahaboobnagar | 38 | 1 |  |  |  | 1 | #REF!
15 | Ranga Reddy | 76 | 2 |  |  |  | 2 | #REF!
16 | Nalgonda | 38 | 1 |  |  |  | 1 | #REF!
17 | Medak | 38 | 1 |  | 1 |  |  | #REF!
18 | Nizamabad | 38 | 1 |  |  | 1 |  | #REF!
19 | Warangal | 76 | 2 |  |  |  | 2 | #REF!
20 | Khammam | 38 | 1 |  |  |  | 1 | #REF!
21 | Karimnagar | 38 | 1 |  |  |  | 1 | #REF!
22 | Adilabad | 38 | 1 |  |  |  | 1 | #REF!
| TOTAL | 950 | 25 | 0 | 2 | 7 | 16 | #REF!
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## cop.p1
Dt:19.01.2016
Construction of 20 & 12 Bed Special Care New Born Units (SCNUs) - Phase-1 & 2 for the year 2011-12 under NRHM

## abs 20bed m.wise
MONTH WISE ABSTRACT
Construction of 20 Bed Special Care Newborn Units (SCNUs) for the year 2011-12 (Phase-1)
Sl.No. | District | AS / RAS amount (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up 6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other department/Scheme | Site problem | RAS awaited | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | SKLM | 38 | 0 |  | 1 | 1 |  |  | 1 | 0
2 | VZM | 38 | 37.9 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
3 | VSP | 38 | 33 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
4 | EG | 76 | 69.78 |  | 2 |  |  |  | 0 | 2 | 2 |  |  | 2 |  | 2
5 | WG | 49 | 35.47 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
6 | KRI | 38 | 25.22 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
7 | GNT | 38 | 35.25 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
8 | PKSM | 38 | 36.92 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
9 | NLR | 38 | 33.32 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
10 | CTR | 38 | 35.24 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
11 | ATP | 38 | 25.47 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
12 | KDP | 38 | 29.62 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
13 | KNL | 38 | 35.43 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
| TOTAL | 543 | 432.62 |  | 14 | 1 | 0 | 0 | 1 | 13 | 13 | 0 | 0 | 13 | 0 | 13 | 0

## (20) detail
Construction of 20 Bed Special Care Newborn Units (SCNUs)-Phase-1
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs.in lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
DISTRICT : SRIKAKULAM
1 | SKLM |  | RIMS, Srikakulam | 02.05.2011 | 38 |  | M/s. Satya Sai Construction Visakhapatnam |  | Functioning in old hospital in RIMS campus. Included in Balance work of RIMS
DISTRICT : VIZIANAGARAM
2 | VZNG | VZNG | Maternity Hospital | 02.05.2011 | 38 | 37.9 | Sri K.Chandra Naidu, | 7.10.11
DISTRICT : VISAKHAPATNAM
3 | VSP | VSP | Victoria Maternity Hospital | -do- | 38 | 33 | Sri B.Muralikrishna | 08.03.12
DISTRICT : EAST GODAVARI
4 | EG | Rajahmundry | District HQ Hospital, Rajahmundry | -do- | 38 | 34.8 | Sri V.R. Kaleswara Rao | 15.11.2011
5 | EG | Kakinada | Rangaraya Medical College, Kakinada. | -do- | 38 | 34.98 | Sri Y. Prakasa Rao | 31.12.2011
|  |  | Sub-total |  | 76 | 69.78
DISTRICT : WEST GODAVARI
6 | WG | Eluru | District HQ Hospital, Eluru | 02.05.2011 | 49 | 35.47 | Sri.Ganta Satya Sudhir | 30.10.2012
DISTRICT : KRISHNA
7 | KRI | Krishna | District HQ Hospital, Machilipatnam | -do- | 38 | 25.22 | Sri K.Srinivas Rao, | 31.10.2013
DISTRICT : GUNTUR
8 | GNT | Guntur | Government General Hospital | -do- | 38 | 35.25 | Sri T.Govinda Reddy. | 2012-07-11
DISTRICT : PRAKASAM
9 | PKSM | Ongole | RIMS, Ongole | -do- | 38 | 36.92 | P.Venkatareddy | 8.10.2012
DISTRICT : NELLORE
10 | NLR | Nellore | MCH Hospital | -do- | 38 | 33.32 | I. Tirupalu | 26.11.2012
DISTRICT : CHITTOOR
11 | CTR | Chittoor | District Hospital | 02.05.2011 | 38 | 35.24 | M/s. Sumasree Constructions | 30-12-12
DISTRICT : ANANTAPUR
12 | ATP | Anantapur | Srikrishna Devaraya Medical College | -do- | 38 | 25.47 | Sri.A.Ramappa. | 31-5-2013
DISTRICT : KADAPA
13 | YSR | Kadapa | DH Proddutur | 01.06.2011 | 38 | 29.62 | Balachennaredy, | 04.01.2013
DISTRICT : KURNOOL
14 | KNL | Kurnool | Government General Hospital | 02.05.2011 | 38 | 35.43 | M/s HEMS Constructions | 29.08.2012
|  |  | GRAND TOTAL |  | 543 | 432.62
|  | Add establishment charges@ 7% |  |  |  | 30.2834
|  | TOTAL : |  |  |  | 462.9034

## 12 beds abs (hidden)
ABSTRACT
Construction of 12 Bed Special Care Newborn Units (SCNUs) for the year 2011-12 (Phase-1)
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Status of works |  |  |  |  | Expenditure (Rs.in lakes) | Remarks
|  |  |  | Site problem | Tender process | Work is in progress | Work completed | Not taken up
1 | Vizianagaram | 30 | 1 |  |  |  | 1 |  | 29.54
2 | Visakhapatnam | 60 | 2 |  |  |  | 2 |  | 53.747
3 | East Godavari | 30 | 1 |  |  | 1 |  |  | 28
4 | Kurnool | 30 | 1 |  |  | 1 |  |  | 27.5
5 | Warangal | 30 | 1 |  |  |  | 1 |  | #REF!
6 | Khammam | 30 | 1 |  |  |  | 1 |  | #REF!
7 | Adilabad | 30 | 1 |  |  | 1 |  |  | #REF!
| TOTAL | 240 | 8 | 0 | 0 | 3 | 5 | 0 | #REF!
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## abs 12bed m.wise
Construction of 12 Bed Special Care Newborn Units (SCNUs) (ITDA) - Phase-1
Sl.No. | District | AS / RAS amount (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up 6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other department/Scheme | Site problem | RAS awaited | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | VZM | 30 | 29.54 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
2 | VSP | 60 | 53.747 |  | 2 |  |  |  |  | 2 | 2 |  |  | 2 |  | 2
3 | EG | 30 | 28 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
4 | KNL | 30 | 27.5 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
| TOTAL | 150 | 138.787 |  | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 5 | 0 | 5 | 0

## (12) details
PROGRESS REPORT FOR THE MONTH OF JULY - 2011 (FOR THE REVIEW AT HEAD OFFICE ON 03.08.2011)
Construction of 12 Bed Special Care Newborn Units (SCNUs) (ITDA) - Phase-1
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 8
DISTRICT : VIZIANAGARAM
1 | VZM | Parvathipuram | AH, Parvathipuram | 2.05.11 | 30 | 29.54 | Sri K.Chandra Naidu | 24.12.11
DISTRICT : VISAKHAPATNAM
2 | VSP | Chintapally | CHC, Chintapally | -do- | 30 | 25.887 | Sri T.Eswara Rao | 25.11.11
3 | -do- | Paderu | AH, Paderu | -do- | 30 | 27.86 | Sri K.Chandra Naidu | 09.12.11
|  |  | Sub-total |  | 60 | 53.747
DISTRICT : EAST GODAVARI
4 | EG | Ramachodavaram | AH, Ramachodavaram | -do- | 30 | 28 | Sri R.S. Santharam | 30.06.2012
DISTRICT : KURNOOL
5 | KNL | Srisailam | AH, Srisailam | -do- | 30 | 27.5 | D.Venkata Narayana | 12.03.2012
|  |  | Grand Total |  | 150 | 138.787
|  | Add establishment charges@ 7% |  |  |  | 9.7151
|  | TOTAL : |  |  |  | 148.5021
138.787
#REF!

## abs 20bedp2 m.wise
MONTH WISE ABSTRACT
Construction of 20 Bed Special Care Newborn Units (SCNUs) for the year 2011-12 (Phase-2)
Sl.No. | District | AS / RAS amount (Rs. In lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up 6-10) | Status of takenup works |  |  | Final bill |  | Building |  | Expenditure (Rs.in lakes) | Expected month of completion | Remarks
[6 empty] | Taken up by other department/Scheme | Site problem | RAS awaited | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | VSP | 38 | 35.64 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
2 | KRI | 38 | 35.01 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
3 | GNT | 38 | 32.2 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
4 | CTR | 76 | 49.8 |  | 2 |  |  |  |  | 2 | 2 |  |  | 2 |  | 2
5 | KDP | 38 | 35.43 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
6 | KNL | 38 | 35.23 |  | 1 |  |  |  |  | 1 | 1 |  |  | 1 |  | 1
| TOTAL | 266 | 223.31 | 0 | 7 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 7 | 0 | 7 | 0 | 0 | 0

## 20 bedded P-2
Construction of 20 Bed Special Care Newborn Units (SCNUs) - Phase-2
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
DISTRICT : VISAKHAPATNAM
1 | VSP | VSP | Andhra Medical College & KGH. | 31.10.2011 | 38 | 35.64 | Sri K.Satyanarayana Murthy | 04.12.12
DISTRICT : KRISHNA
2 | KRI |  | Siddhartha Medical College, Vijayawada. | -do- | 38 | 35.01 | Sri D.Venkateswara Raju | 28-12-2013
DISTRICT : GUNTUR
3 | GNT |  | DH, Tenali | -do- | 38 | 32.2 | M/s.Silas Constructions | 30-1-13
DISTRICT : CHITTOOR
4 | CTR |  | SVRR, Tirupathi | -do- | 38 | 25.1 | M/s. I. Muni Mohan Reddy & Co., | 16-07-12
5 | CTR |  | GMH, Tirupathi |  | 38 | 24.7 | M/s. I. Muni Mohan Reddy & Co., | 16-07-12
|  |  | Sub-total |  | 76 | 49.8
DISTRICT : KADAPA
6 | YSR |  | RIMS, Kadapa | -do- | 38 | 35.43 | N.Adinarayana Reddy, | 02.04.2013
DISTRICT : KURNOOL
7 | KNL |  | District HQ Hospital, Nandyal | 31.10.2011 | 38 | 35.23 | M.Pulla Reddy | 22.10.2012
|  |  | Grand total |  | 266 | 223.31
|  | Add establishment charges@ 7% |  |  |  | 15.6317
|  | TOTAL : |  |  |  | 238.9417

## cop.p2 (hidden)
Date: .08.2012
Construction of 20 Bedded Special Care New Born Units (SCNUs) - Phase- 2 for the year 2011-12 under NRHM

## 20 beds abs p-2 (hidden)
ABSTRACT
Construction of 20 Bed Special Care Newborn Units (SCNUs) for the year 2011-12 (Phase-2)
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Status of works | [6 empty] | Expenditure (Rs.in lakes) | Work to be completed |  |  | Remarks
|  |  |  | Site problem | Site problem | Not taken up | Tender process | Work to be started | Work is in progress | Work Completed |  | 31.05.2012 | 30.06.2012 | 31.07.2012
1 | Visakhapatnam | 38 | 1 |  |  |  |  | 1
2 | Krishna | 38 | 1 |  |  |  | 1 | [6 empty] | 1
3 | Guntur | 38 | 1 | [5 empty] | 1 |  |  |  |  | 1
4 | Chittoor | 76 | 2 | [5 empty] | 2 |  |  | 2
5 | Kadapa | 38 | 1 | [5 empty] | 1 |  |  | 1
6 | Kurnool | 38 | 1 |  |  |  |  | 1 |  |  |  |  | 1
7 | Hyderabad | 114 | 3 |  |  |  | 2 | 1 |  |  |  |  | 3
8 | Warangal | 38 | 1 | [5 empty] | 1 |  |  | 1
| TOTAL | 418 | 11 | 0 | 0 | 0 | 3 | 3 | 5 | 0 | 0

## Sheet1 (hidden)
PROGRESS REPORT FOR THE MONTH OF JULY - 2011 (FOR THE REVIEW AT HEAD OFFICE ON 03.08.2011)
Construction of 20 Bed Special Care Newborn Units (SCNUs)- Phase-2
Ref. to AS : G.O.Ms.No.322, dt.31.10.2011 of HM&FW (D2) Dept.
Estimate Cost of each work : Rs.38.00
Sl. No. | Location of the work | Name of the Agency | Administrative sanction amount (Rs.in lakhs) | Agreement amount (Rs.in lakhs) | Agreement No & Date | Over all expenditure (Rs. lakhs) | Stage of work | Stage of work during this month | Likely date of completion | Name of Location | Ref. to Administrative Approval | Amount of Administrative Approval | Ref. to Technical Sanction | Amount of Technical Sanction | Agreed Date of Completion | Probable Date of Completion | Cumulative Expenditure (Rs.in lakhs) | District | Stage of work |  | Expenditure to the end of Previous Year | Budget Allocation during Year (Rs.in lakhs) | Expenditure (Rs.in lakhs) |  |  | Expected date of completion
[20 empty] | Cumulative |  |  | To end of Previous Month | During Month | Total
1 | [9 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 5 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 5
1 | [9 empty] | 2: Andhra Medical College & KGH.; 3: G.O.Ms.No.322 HM&FW(D2) Dept. dt.31.10.2011.; 4: 38; 3: Visakhapatnam; 4: Tenders stage; Total 5: 31.04.2012
2 | [9 empty] | 2: Siddhartha Medical College, Vijayawada.; 3: -do-; 4: 38; 3: Krishna; 4: Tenders stage; Total 5: 31.04.2012
3 | [9 empty] | 2: DH, Tenali; 3: -do-; 4: 38; 3: Guntur; 4: Tenders stage; Total 5: 31.04.2012
4 | [9 empty] | 2: SVRR, Tirupathi; 3: -do-; 4: 38; 3: Chittoor; 4: Tenders stage; Total 5: 31.04.2012
5 | [9 empty] | 2: GMH, Tirupathi; 3: -do-; 4: 38; 3: Chittoor; 4: Tenders stage; Total 5: 31.04.2012
6 | [9 empty] | 2: RIMS, Kadapa; 3: -do-; 4: 38; 3: Kadapa; 4: Tenders stage; Total 5: 31.04.2012
7 | [9 empty] | 2: District HQ Hospital, Nandyal; 3: -do-; 4: 38; 3: Kurnool; 4: Tenders stage; Total 5: 31.04.2012
8 | [9 empty] | 2: Modern Maternity Hospital, Pitlaburz.; 3: G.O.Ms.No.322 HM&FW(D2) Dept. dt.31.10.2011.; 4: 38; 3: Hyderabad; 4: Site to be identified; Total 5: --
9 | [9 empty] | 2: Niloufer Hospital; 3: -do-; 4: 38; 3: Hyderabad; 4: Tenders stage; Total 5: 31.04.2012
10 | [9 empty] | 2: Maternity Hospital, Koti.; 3: -do-; 4: 38; 3: Hyderabad; 4: Tenders stage; Total 5: 31.04.2012
11 | [9 empty] | 2: MGM Hospital; 3: -do-; 4: 38; 3: Warangal; 4: Tenders stage; Total 5: 31.04.2012
Note on A2: KRP: G.O.Ms.No.121, dt.02.05.11 of HM&FW (D2) Dept., for Rs.912.00 lakhs