## cop.p1
Dt:19.01.2016
Construction of New Born Stabilization Units (NBSUs) - Phase - 1& 2 for the year 2011-12 under NRHM
5

## absP1
MONTH WISE ABSTRACT
Construction of New Born Stabilization Units (NBSUs)-Phase-1
Sl.No. | District | AS / RAS amount (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up 6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other department/Scheme | Site problem | RAS awaited | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 12 | 14 | 15 | 16 | 17 | 18
1 | SKLM | 15 | 13.32 |  | 3 |  |  |  |  | 3 | 3 |  |  | 3 |  | 3
2 | VZM | 10 | 7.82 |  | 2 |  |  |  |  | 2 | 2 |  |  | 2 |  | 2
3 | VSP | 30 | 19.883 |  | 6 |  |  |  |  | 6 | 6 |  |  | 6 |  | 6
4 | EG | 25 | 18.84 |  | 5 |  |  |  |  | 5 | 5 |  |  | 5 |  | 5
5 | WG | 20 | 15.87 |  | 4 |  |  |  |  | 4 | 4 |  |  | 4 |  | 4
6 | KRI | 15 | 13.61 |  | 3 |  |  |  |  | 3 | 3 |  |  | 3 |  | 3
7 | GNT | 25 | 23.22 |  | 5 |  |  |  |  | 5 | 5 |  |  | 5 |  | 5
8 | PKSM | 20 | 17.16 |  | 4 |  |  |  |  | 4 | 4 |  |  | 4 |  | 4
9 | NLR | 15 | 13.7633 |  | 3 |  |  |  |  | 3 | 3 |  |  | 3 |  | 3
10 | CTR | 35 | 32.41 |  | 7 |  |  |  |  | 7 | 7 |  |  | 7 |  | 7
11 | ATP | 50 | 35.63 |  | 10 |  |  |  |  | 10 | 10 |  |  | 10 |  | 10
12 | KDP | 55 | 36.82 |  | 11 |  |  |  |  | 11 | 11 |  |  | 11 |  | 11
13 | KNL | 15 | 11.77 |  | 3 |  |  |  |  | 3 | 3 |  |  | 3 |  | 3
| GRAND TOTAL | 330 | 260.1163 |  | 66 |  |  |  |  | 66 | 66 |  |  | 66 |  | 66

## details P1
Construction of New Born Stabilization Units (NBSUs) - Phase - 1
Sl. No | Name of District | Block /Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
DISTRICT : SRIKAKULAM
1 | SKLM | Tekkali | AH, Tekkali | 02.05.11 | 5 | 4.76 | Sri K.Mohana Rao | 30.6.2013
2 | -do- | Palakonda | AH, Palakonda |  | 5 | 3.92 | Sri K.Mohana Rao | 2.1.2012 |  |  | 260.1163
3 | -do- |  | AH, Narsannapeta |  | 5 | 4.64 | Sri K.Mohana Rao | 20.9.2012 |  |  | #REF!
|  |  | Sub-total |  | 15 | 13.32
DISTRICT : VIZIANAGARAM
4 | VZNG | S.Kota | AH, S.Kota | 02.05.11 | 5 | 3.06 | Sri B.Vijayavardhan | 29.09.11
5 | -do- | Gajapathinagaram | AH, Gajpathinagaram |  | 5 | 4.76 | G.Appala Naidu | 01.10.11
|  |  | Sub-total |  | 10 | 7.82
DISTRICT : VISAKHAPATNAM
6 | VSP | Gajuwaka | AH, Agnampadu | 02.05.11 | 5 | 4.054 | M/s Surya Associates | 24.09.11
7 | -do- | Nakkapalli | CHC, Nakapalli |  | 5 | 2.707 | Sri P.N.V.Ramana | 05.10.11
8 | -do- | Kotauratla | CHC, Kotavurutala |  | 5 | 3.581 | Sri P.N.V.Ramana | 28.09.11
9 | -do- | Anakapalli | AH, Anakapalli |  | 5 | 3.313 | Sri T.Govinda Reddy | 04.10.11
10 | -do- | K.Kotapadu | CHC, K.Kotapadu |  | 5 | 2.378 | Sri Ch.Govinda | 27.09.11
11 | -do- | Aruku | AH, Aruku |  | 5 | 3.85 | Sri P.Rambabu | 16.10.11
|  |  | Sub-total |  | 30 | 19.883
DISTRICT : EAST GODAVARI
12 | EG | Tuni | AH, Tuni | 02.05.11 | 5 | 4.67 | Sri R.S. Santharam | 31.12.2011
13 | -do- | Amalapuram | AH, Amalapuram |  | 5 | 2.52 | Sri V.R. Kaleswara Rao | 31.10.2011
14 | -do- | Ramachandrapuram | AH, Ramachandrapuram |  | 5 | 3.3 | Sri V. Srinivasa Rao | 31.12.2011
15 | -do- | Peddapuram | CHC, Peddapuram |  | 5 | 4.58 | Sri V. Srinivasa Rao | 31.12.2011
16 | -do- | Prathipadu | CHC, Prathipadu |  | 5 | 3.77 | Sri R.S. Santharam | 31.12.2011
|  |  | Sub-total |  | 25 | 18.84
DISTRICT : WEST GODAVARI
17 | WG | Tadepalligudem | AH, Tadepalligudem | 02.05.11 | 5 | 4.66 | M/S Sai Ram Constructions | 9.11.2011
18 | -do- | Tanuku | AH, Thanuku |  | 5 | 4.58 | Sri.V.R.Kalesewara Rao | 4.11.2011
19 | -do- | Palakollu | AH, Palakollu |  | 5 | 3.95 | Sri.Y.Lakshmana Rao | 26.11.2011
20 | -do- | Bhimavaram | AH, Bhimavaram |  | 5 | 2.68 | Sri G.Venkata Rao | 2.12.2011
|  |  | Sub-total |  | 20 | 15.87
DISTRICT : KRISHNA
21 | KRISHNA | Gudivada | AH, Gudivada | 02.05.11 | 5 | 4.45 | M/s Vishnu constructions | 17-04-2012
22 | -do- | Nuziveedu | AH, Nuziveedu |  | 5 | 4.54 | Sri Ch.Suresh kumar, Nuzvid | 07-09-2013.
23 | -do- | Avanigadda | CHC, Avanigadda |  | 5 | 4.62 | Sri P.V.S.N.Purnachandra Rao | 04-09-2012.
|  |  | Sub-total |  | 15 | 13.61
DISTRICT : GUNTUR
24 | GNT | Narsaraopet | AH, Narsaraopet | 02.05.11 | 5 | 4.67 | Sri R.Bhaskara Rao | 10.11.2011
25 | -do- | Sattanapalli | AH, Sattanapalli |  | 5 | 4.63 | Sri R.Bhaskara Rao | 1.10.2011
26 | -do- | Macherla | AH, Macherla |  | 5 | 4.63 | Sri R.Bhaskara Rao | 28.2-2012
27 | -do- | Vinukonda | AH, Vinukonda |  | 5 | 4.67 | Sri K.Rama Rao | 20.03.2012
28 | -do- | Repalli | CHC, Repalli |  | 5 | 4.62 | Sri N.Bala Kotaiah. | 04.01.2012 |  |  |  | 5
|  |  | Sub-total |  | 25 | 23.22
DISTRICT : PRAKASAM
29 | PKSM | Chirala | AH,Chirala | 02.05.11 | 5 | 4.36 | Sri V.Sundaraiah | 9.10.2011
30 | -do- | Markapur | AH, Markapur |  | 5 | 4.64 | Sri.V.S.RamiReddy | 25.9.2011
31 | -do- | Kandukur | AH, Kandukur |  | 5 | 4.46 | Sri.P.VenkataRedd | 26.9.2011
32 | -do- | Kanigiri | AH, Kanigiri |  | 5 | 3.7 | Sri.P.VenkataReddy | 25.9.2011
|  |  | Sub-total |  | 20 | 17.16
DISTRICT : NELLORE
33 | NLR | Gudur | AH, Gudur | 02.05.11 | 5 | 4.6819 | I. Tirupalu | 29.01.2012
34 | -do- | Kavali | AH, Kavali |  | 5 | 4.4085 | I. Tirupalu | 10.05.2012
35 | -do- | Udayagiri | CHC, Udayagiri |  | 5 | 4.6729 | M. Venkataiah | 07.04.2012
|  |  | Sub-total |  | 15 | 13.7633
DISTRICT : CHITTOOR
36 | CTR | Madanapally | AH, Madanapally | 02.05.11 | 5 | 4.68 | Sri. P. Sudhakar | 28-05-13
37 | -do- | Kuppam | AH, Kuppam |  | 5 | 4.4 | Sri. S. Subramanyam Reddy | 02-08-12
38 | -do- | Palmalaner | AH, Palmalaner |  | 5 | 4.62 | Sri. Madukar Reddy. | 15-04-12
39 | -do- | Pileru | AH, Pileru |  | 5 | 4.69 | Sri. M. Chandra Sekhar Reddy | 28-06-12
40 | -do- | Srikalahasti | AH, Srikalahasti |  | 5 | 4.67 | Sri. D. Venkatadri Naidu | 26-09-11
41 | -do- | V Kota | AH, V Kota |  | 5 | 4.67 | Sri. S. Subramanyam Reddy | 30-05-12
42 | -do- | Puttur | AH, Puttur |  | 5 | 4.68 | M/s. Sri Venkateswara Constns. | 15-09-11
|  |  | Sub-total |  | 35 | 32.41
DISTRICT : ANANTAPUR
43 | ATP | Hindupur | DH, Hindupur | 02.05.11 | 5 | 4.43 | Sri.P.Muthyalappa | 10-6-2013
44 | -do- | Gooty | AH, Gooty |  | 5 | 2.59 | Sri.S.Amzad Hussain | 10-6-2013
45 | -do- | Kalyandurg | AH, Kalyandurg |  | 5 | 2.66 | Sri.N.Bala Krishna | 10-6-2013
46 | -do- | Guntakal | AH, Guntakal |  | 5 | 3.23 | Sri.S.Amzad Hussain | 10-6-2013
47 | -do- | Kadiri | AH, Kadiri |  | 5 | 2.34 | Sri.N.Bala Krishna | 10-6-2013
48 | -do- | Dharmavaram | AH, Dharmavaram |  | 5 | 4.64 | Sri.B.Muthyalappa | 10-6-2013
49 | -do- | Uravakonda | AH, Uravakonda |  | 5 | 3.62 | Sri.N.Bala Krishna | 10-6-2013
50 | -do- | Madakasira | AH, Madakasira |  | 5 | 4.2 | Sri.B.Pulla Reddy | 10-6-2013
51 | -do- | Tadipatri | AH, Tadipatri |  | 5 | 4.04 | Sri.S.Amzad Hussain | 10-6-2013
52 | -do- | Penukonda | CHC, Penukonda |  | 5 | 3.88 | Sri.P.Muthyalappa | 10-6-2013
|  |  | Sub-total |  | 50 | 35.63
DISTRICT : KADAPA
53 | KDP | Pulivendula. | AH, Pulivendula | 02.05.11 | 5 | 3.97 | V.chinnasubbarayudu | 26.09.2012
54 | -do- | jammalamadugu | AH, Jammalamadugu |  | 5 | 4.12 | N.Adinarayana Reddy | 20.04.2012
55 | -do- | Badvel | CHC, Badvel |  | 5 | 2.52 | N.Adinarayana Reddy | 28.11.2011
56 | -do- | Porumamilla | CHC, Porumamilla |  | 5 | 2.01 | G.Ravichandra Reddy | 28.11.2012
57 | -do- | Mydukur | CHC, Maidukur |  | 5 | 1.16 | Sri Venkateswara | 05.06.2012
58 | -do- | Rayachoti | CHC, Rayachoti |  | 5 | 3.79 | S.Abdul Shukur | 05.06.2013
59 | -do- | Rly.kodur | CHC, Railway Kodur |  | 5 | 3.4 | P.Nagamuni | 10.11.2012
60 | -do- | Sidhoutam | CHC, Siddouttam |  | 5 | 3.51 | B.Chandra Obul Reddy | '08/2012
61 | -do- | Lakkireddy palli | CHC, Lakkireddypalli |  | 5 | 4.33 | S.Abdul Shukur | 09/2012
62 | -do- | vempalli | CHC, Vempalli |  | 5 | 3.65 | Narasimha Reddy | 08/2012
63 | -do- | Rajampeta | CHC, Rajampeta |  | 5 | 4.36 | Sapthagiri VLCCS | 08/2012
|  |  | Sub-total |  | 55 | 36.82
DISTRICT : KURNOOL
64 | KNL | Adoni | MCH, Adoni | 02.05.11 | 5 | 2.85 | B.M.D.Ismail | 30.08.2012
65 | -do- | Banganapally | CHC, Banganapally |  | 5 | 4.29 | J.Shiva Shankar Reddy | 18.09.2011
66 | -do- | Koilakuntla | CHC, Koilakuntla |  | 5 | 4.63 | B.Manohar Rao | 13.04.2012
|  |  | Sub-total |  | 15 | 11.77
|  |  | Grand total |  | 330 | 260.1163
|  | Add establishment charges@ 7% |  |  |  | 18.2081
|  | TOTAL : |  |  |  | 278.3245

## absP2
MONTH WISE ABSTRACT
Construction of New Born Stabilization Units (NBSUs)-Phase-2
Sl.No. | District | AS / RAS amount (Rs.in lakhs) | Gross Expenditure (Rs. In lakhs) | Balance amount required (Rs. In lakhs) | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up 6-10) | Status of takenup works |  |  | Final bill |  | Building
[6 empty] | Taken up by other department/Scheme | Site problem | RAS awaited | Total (7+8+9) |  | Work completed | Work to be started | Work is in progress | Paid | Not paid | Handed over | Not Handed Over
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | SKLM | 15 | 13.03 |  | 3 |  |  |  | 0 | 3 | 3 |  |  | 3 |  | 3
2 | VZM | 5 | 4.86 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
3 | VSP | 5 | 3.87 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
4 | EG | 10 | 9.31 |  | 2 |  |  |  | 0 | 2 | 2 |  |  | 2 |  | 2
5 | WG | 20 | 16.16 |  | 4 |  |  |  | 0 | 4 | 4 |  |  | 4 |  | 4
6 | KRI | 20 | 14.23 |  | 4 |  |  |  | 0 | 4 | 4 |  |  | 4 |  | 4
7 | GNT | 15 | 13.96 |  | 3 |  |  |  | 0 | 3 | 3 |  |  | 3 |  | 3
8 | PKSM | 15 | 4.38 | 5 | 3 | 1 |  |  | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 | 1
9 | NLR | 5 | 4.58 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
10 | CTR | 25 | 21.13 |  | 5 |  |  |  | 0 | 5 | 5 |  |  | 5 |  | 5
11 | ATP | 5 | 0 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
12 | KNL | 5 | 4.67 |  | 1 |  |  |  | 0 | 1 | 1 |  |  | 1 |  | 1
| GRAND TOTAL | 145 | 110.18 | 5 | 29 | 1 | 0 | 0 | 1 | 28 | 27 | 1 | 0 | 27 | 1 | 27 | 1

## details P2
Construction of New Born Stabilization Units (NBSUs) - Phase - 2
Sl. No | Name of District | Block/Mandal | Name of Centre | Date/Month of Work sanctioned | Financial Progress |  | Name of Execution agency | Physical Progress
[5 empty] | AS / RAS amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) |  | If complete - Date/Month of Work Completion | If not completed -Stage of Progress | Tentative date of completion
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
DISTRICT : SRIKAKULAM
1 | SKLM |  | AH Palasa | 31.10.2011 | 5 | 4.6 | Sri B.Trinadharao | 3.9.2012 |  |  | 105.6
2 | -do- | Pathapatnam | CHC Pathapatnam |  | 5 | 4.08 | Sri M.Ramarao Korasavada (V) Pathapatnam (M) Srikakulam (Dist) | 18.4.2013 |  |  | #REF!
3 | -do- | Sompeta | CHC Sompeta |  | 5 | 4.35 | Sri P.Applaswami | 20.4.2013
|  |  | Sub-total |  | 15 | 13.03 |  |  |  |  | 105.6
DISTRICT : VIZIANAGARAM | [10 empty] | #REF!
4 | VZM | Bhogapuram | CHC Bhogapuram | 31.10.2011 | 5 | 4.86 | K.V.Ramana | 06.06.12
DISTRICT : VISAKHAPATNAM
5 | VSP | Narsipatnam | AH Narsipatnam | .31.10.2011 | 5 | 3.87 | Sri A.Appala Naidu, | 15.05.12 |  |  | 110.18
DISTRICT : EAST GODAVARI | [10 empty] | #REF!
6 | EG | Kothapet | AH Kothapet | 31.10.2011 | 5 | 4.65 | Sri V.R. Kaleswara Rao, Amalapuram. | 07.04.2012
7 | -do- | Razolu | CHC Razolu |  | 5 | 4.66 | Sri V.R. Kaleswara Rao | 07.04.2012
|  |  | Sub-total |  | 10 | 9.31
DISTRICT : WEST GODAVARI
8 | WG | Narasapuram | AH Narsapur | 31.10.2011 | 5 | 4.65 | Sri G.Venkata Rao | 13.08.2012
9 | -do- | Kovuru | CHC Kovuru |  | 5 | 3.7 | Sri.Y.Lakshmana Rao | 30.06.2013
10 | -do- | Chintalpudi | CHC Chintalpudi |  | 5 | 4.46 | Sri.Y.Lakshmana Rao | 29.11.2012
11 | -do- | Jangareddigudem | AH Jangareddigudem |  | 5 | 3.35 | Sri.P.Satyanarayana, TP.Gudem | 30.06.2013
|  |  | Sub-total |  | 20 | 16.16
DISTRICT : KRISHNA
12 | KRI | Mylavaram | CHC Mylavaram | 31.10.2011 | 5 | 2.89 | Sri N.Govinda Rao | 12.03.2013
13 | -do- | Vuyyuru | CHC Vuyyuru |  | 5 | 2.51 | Sri J.Sudhakar rao | 24.10.2012
14 | -do- | Tiruvuru | CHC Tiruvuru |  | 5 | 4.23 | Sri D.V.Raju | 31.10.2012
15 | -do- | Nandigama | AH Nandigama |  | 5 | 4.6 | Sri M.Srinivasa Rao, Nandigama | 15.11.2012
|  |  | Sub-total |  | 20 | 14.23
DISTRICT : GUNTUR
16 | GNT | Chilakaluripeta | CHC Chilakaluripeta | 31.10.2011 | 5 | 4.68 | Sri G.Srinivasa Rao | 17.11.2011
17 | -do- | Amaravathi | CHC Amaravathi |  | 5 | 4.67 | Sri R.Radha Krishna Murthy | 19.10.2012
18 | -do- | Bapatla | AH Bapatla |  | 5 | 4.61 | Sri B.Madhu Babu | 5.01.2013
|  |  | Sub-total |  | 15 | 13.96
DISTRICT : PRAKASAM
19 | PKSM | Giddalur | AH Giddalur | 31.10.2011 | 5 | - | - | - | Existing structures are in dilapidated condition, Hence accommadation of CHNC in the same campus not advisable. Hence treated as deleted.
20 | -do- | Ongole | MCH Ongole |  | 5 | 4.38 | Sri Chavali Suresh Babu | 10.1.2013
21 | -do- | Kumbum | CHC Kumbum |  | 5 | - | - | - | Agreement to be concluded
|  |  | Sub-total |  | 15 | 4.38
DISTRICT : NELLORE
22 | NLR | Nellore | DH Nellore | 31.10.2011 | 5 | 4.58 |  | 08.07.2012
DISTRICT : CHITTOOR
23 | CTR | Kalikiri | CHC Kalikiri | 31.10.2011 | 5 | 4.67 | Sri. M. Mallikarjuna Reddy | 20-09-12
24 | -do- | Satyavedu | CHC Satyavedu |  | 5 | 4.51 | Sri. B. Nagaraju | 30-07-13
25 | -do- | Punganur | CHC Punganur |  | 5 | 4.69 | Sri. M. Chandra Sekhar Reddy | 15-10-12
26 | -do- | Vayalapadu | CHC Vayalpadu |  | 5 | 3.99 | Sri. M. Mallikarjuna Reddy | 20-08-12
27 | -do- | Nagari | AH Nagari |  | 5 | 3.27 | Sri. B. Nagaraju | 30-07-13
|  |  | Sub-total |  | 25 | 21.13
DISTRICT : ANANTAPUR
28 | ATP |  | CHC Rayadurg | 31.10.2011 | 5 |  |  |  | Work Completed.
DISTRICT : KURNOOL
29 | KNL | Yemmiganur | CHC Yemmiganur | 31.10.2011 | 5 | 4.67 | M.Sreenivasa Reddy | 12.05.2012
|  |  | Grand total |  | 145 | 110.18
|  | Add establishment charges@ 7% |  |  |  | 7.7126
|  | TOTAL : |  |  |  | 117.8926

## abs monthwise (hidden)
ABSTRACT
Construction of New Born Stabilization Units (NBSUs)-Phase-1
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Status of works |  |  |  |  | Work to be completed. |  |  | Expenditure (Rs.in lakes) | Remarks
|  |  |  | Site problem | Tender stage | Work to be started | Work is in progress | Work completed | 30.04.2012 | 31.05.2012 | 30.06.2012
1 | Srikakulam | 15 | 3 |  |  |  | 2 | 1 | 1 | 1 |  | 13.32
2 | Vizianagaram | 10 | 2 |  |  |  |  | 2 |  |  |  | 7.82
3 | Visakhapatnam | 30 | 6 |  |  |  |  | 6 |  |  |  | 19.883
4 | East Godavari | 25 | 5 |  |  |  |  | 5 |  |  |  | 18.84
5 | West Godavari | 20 | 4 | 1 |  |  |  | 3 |  |  |  | 15.87
6 | Krishna | 15 | 3 |  |  |  | 3 |  |  | 2 | 1 | 13.61
7 | Guntur | 25 | 5 |  |  |  |  | 5 |  |  |  | 23.22
8 | Prakasam | 20 | 4 |  |  |  |  | 4 |  |  |  | 17.16
9 | Nellore | 15 | 3 |  |  |  |  | 3 |  |  |  | 13.7633
10 | Chittoor | 35 | 7 |  |  |  | 1 | 6 |  | 1 |  | 32.41
11 | Ananthapur | 50 | 10 |  |  |  |  | 10 |  |  |  | 35.63
12 | Kadapa | 55 | 11 |  |  |  | 1 | 10 |  | 1 |  | 36.82
13 | Kurnool | 15 | 3 |  |  |  | 1 | 2 |  | 1 |  | 11.77
14 | Mahaboobnagar | 30 | 6 |  |  |  | 1 | 5 |  | 1 |  | #REF!
15 | Hyderabad | 40 | 8 |  |  |  | 1 | 7 |  |  | 1 | #REF!
16 | Ranga Reddy | 10 | 2 |  |  |  |  | 2 |  |  |  | #REF!
17 | Nalgonda | 30 | 6 |  |  |  |  | 6 |  |  |  | #REF!
18 | Medak | 25 | 5 | 1 |  |  | 2 | 2 |  |  | 2 | #REF!
19 | Nizamabad | 15 | 3 |  |  |  |  | 3 |  |  |  | #REF!
20 | Warangal | 20 | 4 |  |  |  |  | 4 |  |  |  | #REF!
21 | Khammam | 45 | 9 |  |  |  | 1 | 8 |  | 1 |  | #REF!
22 | Karimnagar | 25 | 5 |  |  |  |  | 5 |  |  |  | #REF!
23 | Adilabad | 35 | 7 |  |  |  | 5 | 2 |  | 2 | 3 | #REF!
| GRAND TOTAL | 605 | 121 | 2 | 0 | 0 | 18 | 101 | 1 | 10 | 7 | #REF!
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## cop.p2 (hidden)
Date : 03.08.2012
Construction of New Born Stabilization Units (NBSUs) - Phase - 2 for the year 2011-12 under NRHM
5

## absp2 monthwise (hidden)
ABSTRACT
Construction of New Born Stabilization Units (NBSUs)-Phase-2
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Status of works | [5 empty] | Work to be completed |  |  |  | Expenditure (Rs.in lakes) | Remarks
|  |  |  | Site problem | Work not taken up | Work completed | Tender stage | Work to be started | Work is in progress | 30.04.2012 | 31.05.2012 | 30.06.2012 | 31.07.2012
1 | Srikakulam | 15 | 3 | [5 empty] | 3 |  | 3
2 | Vizianagaram | 5 | 1 | [5 empty] | 1 |  | 1
3 | Visakhapatnam | 5 | 1 | [5 empty] | 1 |  | 1
4 | East Godavari | 10 | 2 |  |  | 2
5 | West Godavari | 20 | 4 |  |  |  | 4 |  |  |  | 4
6 | Krishna | 20 | 4 | 1 |  | 1 | 2 |  |  |  |  | 2
7 | Guntur | 15 | 3 |  |  |  | 1 |  | 2 | 1 | 1 | 1
8 | Prakasam | 15 | 3 | 2 |  |  | 1 |  |  |  |  | 1
9 | Nellore | 5 | 1 | [5 empty] | 1 |  | 1
10 | Chittoor | 25 | 5 | [5 empty] | 5 |  |  | 5
11 | Ananthapur | 5 | 1 |  |  |  | 1 | [5 empty] | 1
12 | Kurnool | 5 | 1 |  |  |  |  | 1 |  |  | 1
13 | Mahaboobnagar | 5 | 1 | [5 empty] | 1 | 1
14 | Nalgonda | 10 | 2 |  |  |  | 2 |  |  |  |  | 2
15 | Medak | 5 | 1 |  |  |  | 1 | [5 empty] | 1
16 | Nizamabad | 10 | 2 |  |  |  | 2 | [5 empty] | 2
| GRAND TOTAL | 175 | 35 | 3 |  | 3 | 14 | 1 | 14 | 2 | 12 | 11 | 4 | 0
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00