## CV P
PRIMARY HEALTH CENTERS

## ABS
PRIMARY HEALTH CENTERS
Sl. No. | Name of the Work | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up | Status of takenup works |  |  | Building |  | Building completed to be handed over
|  |  | Taken up by other dept/Scheme | Site problem | RAS awaited or etc | Total |  | Work completed | Tender stage | Work is in progress | Handed over | Not Handed Over
1 | 55 PHCs | 36 | 0 | 1 | 0 | 1 | 35 | 34 |  | 1 | 31 | 4 | 3
2 | 100 PHCs | 82 | 1 | 0 | 4 | 5 | 77 | 77 |  |  | 70 | 7 | 7
3 | 94 PHCs | 68 | 6 | 2 | 7 | 15 | 53 | 50 |  | 3 | 31 | 22 | 19
| TOTAL | 186 | 7 | 3 | 11 | 21 | 165 | 161 | 0 | 4 | 132 | 33 | 29

## Cancellation
PROSED FOR CANCELLATION
SITE PROBLEMS & NOT STARTED WORKS
Sl. No | Name of District | Name of Centre | Sanction amount (Rs. In lakhs)
55 PHCs - 2010-11
1 | CTR | S.Gollapalli | 68.5
100 PHCs - 2011-12
2 | WG | Borrampalem | 68.5
3 | WG | Chintapalli (New) | 68.5
4 | GNT | Vatticherukuru | 68.5
5 | ATP | Raketla | 68.5
94 PHCs - 2012-13
6 | SKLM | Venakatapuram | 68.5
7 | SKLM | Manikyapuram | 68.5
8 | SKLM | Rajapuram | 68.5
9 | SKLM | Laveru (LMD Colony) | 68.5
10 | KRI | Indupalli | 68.5
11 | KRI | Kolletikota | 68.5
12 | GNT | Piduguralla | 68.5
13 | PKSM | Pothavaram | 68.5
14 | CTR | Nagalapuram | 68.5
SITE PROBLEMS
Sl. No |  | Name of Location | Admin. Sanction (Rs.in lakhs)
55 PHCs - 2010-11
1 | 55 PHCsCTE | S.Gollapalli | 68.5
94 PHCs - 2012-13
1 | PKSM | Pothavaram | 68.5
2 | CTR | Nagalapuram | 68.5

## Completed to be handed over
Building completed and to be handed over by user department
Sl. No | Name of District | Name of Centre | Sanction Amount (Rs. In lakhs)
55 PHCs - 2010-11
1 | CTR | Vijayapuram (Talapunenivaripalli) | 68.5
2 | ATP | Garudachedu | 40
3 | KDP | Talla palli | 40
100 PHCs - 2011-12
4 | SKLM | Srikurmam (In place of Pendurthi in VSP Dist) | 68.5
5 | EG | Bendamurulanka | 40
6 | -do- | Lutukuru (In place of Malkajagiri in RR Dist) | 68.5
7 | KRI | Chinnapuram | 46.6
8 | -do- | Yelamarru | 48.85
9 | GNT | Inturu | 49.5
10 | NLR | Bangarupet | 68.5
94 PHCs - 2012-13
11 | SKLM | Urlam | 68.5
12 | EG | Virava | 68.5
13 | -do- | Lakkavaram | 68.5
14 | -do- | Nagaram | 68.5
15 | -do- | Nagulapalli | 68.5
16 | -do- | Mallam | 68.5
17 | WG | Kamavarapukota | 68.5
18 | KRI | Seethanapalli | 68.5
19 | GNT | Karlapadu | 68.5
20 | -do- | Rompicherla | 68.5
21 | -do- | Vellaturu (Alternate place Daroor Camp in Karim nagar Dist) | 68.5
22 | PKSM | Guntupalli | 68.5
23 | -do- | Thimmasamudram | 68.5
24 | NLR | Gunapatipalem | 68.5
25 | -do- | Vidavalur | 68.5
26 | -do- | Marripadu | 68.5
27 | -do- | Kovurpalli | 68.5
28 | KDP | Narsapuram (In place of KC Canal’ in Karimnagar district) | 68.5
29 | KNL | Uppalapalem | 68.5

## Progress of works
PROGRESS OF WORK
Sl. No | Name of District | Name of Centre | Sanction amount (Rs. In lakhs) | Expenditure (Rs. In lakhs) | Stage of work
55 PHCs - 2010-11
1 | ATP | Avuladatla | 40 | 32.64 | Work completed to the extent of Administrative Sanction amount
94 PHCs - 2012-13
2 | EG | Maredumilli | 68.5 | 7.5 | Columns raised upto roof level. Work stopped by the Contrator. Final notice issued to Contractor.
3 | WG | L.N.D.Peta | 68.5 | 18.12 | Slab work in progress.
4 | GNT | Mollagunata | 68.5 | 31.37 | Finishings in progress

## RAS-ONGOING
REVISED ADMINISTRATIVE SANCTION
Sl. No | Name of District | Name of Centre | Sanction amoount | RAS required (Rs. In lakhs) | Status of Work
55 PHCs - 2010-11
1 | ATP | Avuladatla | 40 | 47.08 | Work completed to the extent of Administrative Sanction amount
2 | KDP | Tallapalli | 40 | 47 | Work completed
100 PHCs - 2011-12
3 | NLR | Bangarupet | 40 | 47 | Work completed to the extent of Administrative Sanction amount
94 PHCs - 2012-13
4 | GNT | Mollagunta | 68.5 | 93.5 | work is in Finishing stage, as the site is very low laying area and very low SBC of 50KN/sqm, foundations cost increased.