## Sheet2 (hidden)
ABSTRACT
Construction of Sub-centre buildings for the year 2011-12
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Tenders invited | Tenders to be invited | Site to be handed over | Others | Remarks
1 | Srikakulam | 99 | 11 | 7 | 3 | 1
2 | Vizianagaram | 162 | 18 | 8 | 5 | 5
3 | Visakhapatnam | 9 | 1 | 1 |  |  |  | Work to be grounded.
4 | East Godavari | 162 | 18 | 17 | 1 |  |  | Recall for one work.
5 | West Godavari | 126 | 14 | 13 |  |  | 1 | Sub-centre sanction not there in village Koppaka clarification from DM&HO awaited.
6 | Krishna | 216 | 24 |  | 6 | 18 |  | The estimates are above Rs.9.00 lakhs. Hence, orders waited for further action.
7 | Guntur | 189 | 21 | 7 | 7 | 6 | 1 | Rajupalem, Uppalpadu sub-centre overlapped Hence to be deleted.
8 | Prakasam | 180 | 20 | 18 |  | 2
9 | Nellore | 180 | 20 |  | 8 | 12
10 | Chittoor | 216 | 24 | 23 |  |  | 1 | Building already existing alternative proposals to be furnished.
11 | Kadapa | 216 | 24 |  | 23 |  | 1 | Double sanction one sub-centres Kadamasti.
12 | Ananthapur | 207 | 23 |  | 16 | 7
13 | Kurnool | 189 | 21 |  | 16 | 5
14 | Mahaboobnagar | 135 | 15 | 11 |  | 4
15 | Ranga Reddy | 162 | 18 |  |  | 18
16 | Medak | 243 | 27 | 27
17 | Nizamabad | 189 | 21 | 21 |  |  |  | Tenders invited and finalized.
18 | Adilabad | 90 | 10 |  | 10
19 | Karimnagar | 45 | 5 |  |  | 4 | 1 | Building already existing alternative proposals to be furnished.
20 | Warangal | 27 | 3 | 3 |  |  |  | Work to be grounded.
21 | Khammam | 63 | 7 |  | 7
22 | Nalgonda | 189 | 21 |  | 19 | 2
| TOTAL | 3294 | 366 | 156 | 121 | 84 | 5
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## abs (hidden)
ABSTRACT
Construction of (366) Sub-centre buildings for the year 2010-11
Sl.No. | District | Administrative sanction amount (Rs.in lakhs) | No. of works | Status of works | [5 empty] | Expenditure (Rs.in lakes) | Remarks
|  |  |  | Site problem | Work not taken up | Tender stage | Work to be started | Work is in progress | Work completed
1 | Srikakulam | 99 | 11 |  |  |  | 1 | 8 | 2 | #REF! |  | 11
2 | Vizianagaram | 162 | 18 | 1 | 4 |  |  | 10 | 3 | #REF! |  | 18
3 | Visakhapatnam | 9 | 1 | [5 empty] | 1 | #REF! |  | 1
4 | East Godavari | 162 | 18 |  |  |  | 2 | 12 | 4 | #REF! |  | 18
5 | West Godavari | 126 | 14 |  |  | 1 | 2 | 11 |  | #REF! |  | 14
6 | Krishna | 216 | 24 | 4 |  | 15 | 2 | 3 |  | #REF! | RAS requested for 16 works and 4 recently proposed for RAS. | 24
7 | Guntur | 189 | 21 | 5 | 1 | 1 |  | 9 | 5 | #REF! |  | 21
8 | Prakasam | 180 | 20 | 8 |  |  |  | 12 |  | #REF! |  | 20
9 | Nellore | 180 | 20 | 6 |  | 1 | 1 | 9 | 3 | #REF! | 1 No. Revised Administrative approval requested. | 20
10 | Chittoor | 216 | 24 |  |  |  |  | 16 | 8 | #REF! |  | 24
11 | Ananthapur | 207 | 23 | 1 |  |  | 1 | 14 | 7 | #REF! |  | 23
12 | Kadapa | 216 | 24 | 2 |  |  | 2 | 17 | 3 | #REF! |  | 24
13 | Kurnool | 189 | 21 | 5 |  |  |  | 12 | 4 | #REF! |  | 21
14 | Mahaboobnagar | 135 | 15 |  |  |  |  | 6 | 9 | #REF! |  | 15
15 | Ranga Reddy | 162 | 18 |  | 1 |  | 1 | 13 | 3 | #REF! | Sub-centre work at Motukur was entrusted to PR Dept. and they have taken up the work. | 18
16 | Nalgonda | 189 | 21 |  |  |  | 3 | 16 | 2 | #REF! | 1 No. Location change. | 21
17 | Medak | 243 | 27 | 1 |  | 1 |  | 17 | 8 | #REF! | 1 No. RA awaited. | 27
18 | Nizamabad | 189 | 21 |  |  |  |  | 7 | 14 | #REF! |  | 21
19 | Warangal | 27 | 3 | [5 empty] | 3 | #REF! |  | 3
20 | Khammam | 63 | 7 |  | 6 |  |  | 1 |  | #REF! | 6 works to ITDA. | 7
21 | Karimnagar | 45 | 5 | 1 |  |  |  | 2 | 2 | #REF! |  | 5
22 | Adilabad | 90 | 10 | 1 | 1 |  |  | 5 | 3 | #REF! | 1 No. deleted. | 10
| TOTAL | 3294 | 366 | 35 | 13 | 19 | 15 | 200 | 84 | #REF! |  | 366
Note on A2: KRP: G.O.MS.No.345, HM&FW (D2) Dept Dt.09.12.10 Rs.9.00

## CV P
SUB CENTERS

## ABST
SUB CENTERS
Sl. No. | Name of the Scheme | No. of works Sanctioned | No.of Works Not taken |  |  |  | No.of Works taken up | Status of takenup works |  |  | Building |  | Building completed to be handed over
|  |  | Taken up by other dept/Scheme | Site problem | RAS awaited | Total |  | Work completed | Tender stage | Work is in progress | Handed over | Not Handed Over
1 | 271 - SCs | 164 | 3 | 0 |  | 3 | 161 | 159 |  | 2 | 159 | 2 | 0
2 | 366 - SCs | 239 | 4 | 11 | 6 | 21 | 218 | 200 | 2 | 16 | 179 | 39 | 21
3 | 151 - SCs | 95 | 1 | 7 | 2 | 10 | 85 | 69 | 4 | 12 | 61 | 24 | 8
4 | 436 - SCs | 271 | 47 | 30 |  | 77 | 194 | 120 | 10 | 64 | 55 | 139 | 65
| TOTAL | 769 | 55 | 48 | 8 | 111 | 658 | 548 | 16 | 94 | 454 | 204 | 94
94

## Progress of works
PROGRESS OF WORKS
Sl. No | Name of District | Name of Centre | AS / RAS (Rs. In lakhs) | Expenditure (Rs. In lakhs) | Stage of work
271 SUB CENTERS - 2009-10
1 | PKSM | Pamidipadu | 9 | 0.89 | At basement level. Work cancelled. RE submitted for Rs.12.20 Lakhs RAS awaited
2 | PKSM | Dharmavaram | 9 | 1.54 | Columns raised upto roof level . Work cancelled. RE submitted for Rs.12.00 Lakhs RAS awaited
366 SUB CENTERS - 2010-11
3 | EG | Divili | 9 | 1.68 | Roof slab laid. Work stopped long back, issued notice to the Contractor.
4 | -do- | Goneda | 9 | 2.63 | Columns upto roof slab laid. Work stopped due to Hon'ble High court stay.
5 | KRI | Vullipalem | 11.81 | 4.1 | Finishings are in progress
6 | -do- | Daliparru (Gudlavalluru-II) | 14 | 4.18 | Roof level
7 | -do- | Mulapadu(Pulluru) | 14 | 0.17 | Foundations is in progress.
8 | PKSM | Mallapalem | 14 | 4.49 | Finishings in progress
9 | -do- | Maguturu | 14 | - | Earth Work excavation is in progress
10 | -do- | Narwaboinapalli | 14 | 4.93 | Superstructure in progress
11 | -do- | Aynamukkala | 14 | 4.6 | Finishings in progress
12 | -do- | Nallakunta | 14 | 4.66 | Superstructure in progress | w2s
13 | -do- | Kothapalli | 14 | 4.28 | Finishings in progress
14 | -do- | Ganjivaripali | 14 |  | Work is in progress
15 | -do- | Kanakalapalli | 14 |  | Agreement concluded. Work to be started
16 | -do- | Mannetikota | 14 |  | Plinth beam to be laid
17 | ATP | S.Rayapuram | 14 |  | LOA issued. Agreement to be concluded.
18 | KNL | Bethamcherla-IV | 14 | 0 | Earth Work excavation is in progress
19 | -do- | Kanala | 14 | 5.5 | Finishings are in progress
20 | -do- | Sivapuram | 14 | 8.41 | Finishings are in progress
151 SUB CENTERS - 2011-12
21 | VSP | Chinapachila | 14 |  | Tenders to be invited
22 | KRI | Puritipadu | 14 | 8.55 | Plasterings are in progress
23 | -do- | Agniparru (Chinthalavalli) | 14 | 0 | Site available. Tenders to be called for
24 | -do- | Chinnamupudi | 14 | 0 | Site available. Tenders to be called for
25 | PKSM | Kalluru | 14 |  | Foundation work is in progress
26 | CTR | Gundlanayanapalli (Pogurupalli / Instead of Beagilipalli) | 14 |  | Earth Work is in progress
27 | ATP | V.G.Palem | 14 |  | Brick work completed & Plastering is in progress
28 | -do- | Bollanagudem | 14 | 6.01 | Finishings are in progress
29 | -do- | Poolactierla | 14 | 6.3 | Brick Work & plasterings are in progress
30 | -do- | Erududona | 14 |  | Brick Work & plasterings are in progress
31 | KDP | Mandapalli (Pullapathur) | 14 |  | Tenders to be invited
32 | -do- | Muthukur | 9 | 2.04 | Roof slab to be laid
33 | -do- | Mallepalli (Thuvapalli) | 14 | 5.5 | Finishings are in progress
34 | KNL | Pedapadu /Gulyam | 14 | 0 | Columns raised up to Plinth level. R.R.Masonary is in progress
35 | -do- | Halvi | 14 | 0 | Footings to be laid
36 | -do- | Kosigi (4) | 14 | 0 | Foundation work is in progress
436 SUB CENTERS - 2012-13
37 | SKLM | K.Kaviti | 14 | 5.4 | Plasterings are in progress
38 | -do- | Hussainpuram | 14 | 3.01 | Columns upto roof level under progress.
39 | -do- | Devanapuram | 14 |  | Foundation Level
40 | -do- | Kondalogam | 14 | 8.1 | Brick work completed & Plasterings are in progress. Contractor noticed for slow progress. (EoT sanctioned upto 31.07.15 further EoT applied upto 30.09.15)
41 | VZM | K.Mulaga Dokiseela | 14 | 11.49 | Finishings are in progress.
42 | VSP | Kandipalem | 14 | 2.6 | Brick work is in progress
43 | -do- | Tanam | 14 | 0 | Site handedover on 02.09.2015. Notice issued to the Agency to start the work
44 | EG | Pothuluru | 14 | 3.49 | Roof slab laid
45 | -do- | Chakradwarabandam | 14 | 2.66 | Roof slab laid
46 | -do- | Thorredu | 14 | 3.88 | Brick work is in progress.
47 | -do- | Seela (Dugguduru) | 14 | …. | Tenders to be invited
48 | -do- | Balusutippa | 14 |  | 4 times tenders called for. But no bidders are participated.
49 | -do- | Madiki | 14 |  | Roof laid.
50 | -do- | Mallepalli | 14 | 4.16 | Columns raised upto roof level.
51 | -do- | Kurmapuram (Uppalaguptam-1) | 14 | …. | Tenders to be invited
52 | -do- | D.N.Palem | 14 | 5.99 | Finishings are in progress.
53 | -do- | P.Vulumpadu | 14 | 5.67 | Brick work completed, plasterings are in progress.
54 | -do- | Kota | 14 | 8.26 | Finishings are in progress.
55 | -do- | Vatangi | 14 | 8.64 | Flooring Water Supply & Internal electrification is in progress
56 | -do- | Chikilinta | 14 | 6.47 | Flooring Water Supply & Internal electrification is in progress
57 | WG | Deva | 14 | 5.87 | Roof slab laid.
58 | -do- | D.R.Palem | 14 | 5.79 | Brick work & plastering is in progress
59 | -do- | ilaparru | 14 |  | footings work in progress.
60 | -do- | Rayalam | 14 | --- | The concerned Hon'ble MLA desired to design the sub-centre with 3 floors. Finalization of designs under preparation at H.O.
61 | -do- | Juvvalapalem | 14 |  | Earth work in progress.
62 | -do- | Dirusumarru | 14 |  | Foundations work in progress.
63 | -do- | Kapavaram | 14 | 2.5 | Earth work in progress.
64 | -do- | Chittavaram | 14 | 2.5 | Earth work in progress.
65 | -do- | Penumantra HQ | 14 |  | Earth work in progress.
66 | KRI | Venuturumilli | 14 | 4.88 | Roof laid.
67 | -do- | Mallachittur | 14 | 0 | Roof level
68 | -do- | Lingala/ (Thotlavalluru (South)) | 14 | 0 | LOA issued
69 | -do- | Kanumolu | 14 | 0 | Agreement concluded.work to be started
70 | -do- | Velivolu | 14 | 11.25 | Finishing stage
71 | PKSM | Narasingolu | 14 |  | Earth work is in progress
72 | -do- | Uppugunduru-II | 14 | 5 | Brick masonry in progress
73 | -do- | Tummalacheruvu | 14 |  | footings work in progress.
74 | -do- | Pedapavani | 14 | 3.28 | Columns raised upto roof level
75 | -do- | Medapi | 14 |  | Agreement concluded work to be started.
76 | NLR | Kollapa Naidupalli | 14 | 3.5047 | Roof slab laid
77 | -do- | Thurpu Kambampadu | 14 | -- | Site identified & Work started
78 | -do- | DC Palli | 14 | 2.5754 | Brick Work & Plastering is in progress.
79 | -do- | Lingamgunta | 14 |  | Foundation level
80 | -do- | Mahimaluru | 14 |  | Plinth beam level
81 | -do- | Rompidodla | 14 | 4.7773 | Water supply & Electrical works are in progress
82 | CTR | Sanganapalli | 14 | 4.62 | Roof slab laid, brick work completed, plastering in progress
83 | -do- | Peddabangurunatham | 14 | 6.43 | Finishing work are in progress
84 | KDP | Devamachupalli | 14 | 3.15 | Roof slab to be laid
85 | ATP | Ganjikunta | 14 | 6.52 | Brick Work & Plasterig is in progress.
86 | -do- | P.Byadigera | 14 |  | Tender Stage LOA issued.
87 | -do- | Nidragatta | 14 |  | Foundation work in progress.
88 | -do- | Maddanakunta | 14 | 5.44 | Brick Work & Plastering Plastering in progress
89 | -do- | Halukuru | 14 | 5.12 | Roof Level Super Structuer completed, Slab work is in progress.
90 | -do- | Kummaranagepalli | 14 |  | Plinth Beam completed.
91 | -do- | Maddanakunta | 14 |  | RR Masonry work is in progress.
92 | -do- | Muthukur | 14 |  | Tender Stage LOA issued.
93 | -do- | Gudduguriki | 14 | 5.76 | Brick Work & Plastering is in progress
94 | -do- | Hottebetta | 14 | 5.5 | Slab, Super Structure completed and further work in progress
95 | -do- | Kurli | 14 | 5.54 | Finishings are in progress
96 | -do- | G.N.Thanda | 14 | 4.38 | Finishings are in progress
97 | -do- | C.G.Project | 14 | 5.65 | Finishings are in progress
98 | -do- | Eddulavaripalli | 14 | 5.86 | Finishings are in progress
99 | KNL | Thagaradona | 14 | 5.7 | Finishings are in progress
100 | -do- | Basaladoddi | 14 | 7.02 | Finishings are in progress
101 | -do- | Gotuladoddi | 14 | 7.02 | Brick work & plastering is in progress
102 | -do- | Kumbalanur | 14 | 7.04 | Finishings are in progress
103 | -do- | Chudi | 14 | 7 | Finishings are in progress
104 | -do- | D.Belgal | 14 | 0 | Columns raised up to Plinth level. R.R.Masonary completed up to basement level
105 | -do- | Kandukur | 14 | 4.68 | Brick masonry work is in progress
106 | -do- | Sajjalagudem | 14 | 0 | Earth work completed
107 | -do- | Hosur (Kallukunta) | 14 | 0 | Roof laid.
108 | -do- | H.Muravani | 14 | 0 | Columns raised up to basement level. R.R.Masonary is in progress
109 | -do- | Doddi Mekala | 14 | 0 | Plinth beam is in progress
110 | -do- | Hebbatam (Vandavagili) | 14 | 0 | Earth work completed

## Cancellation
PROSED FOR CANCELLATION
SITE PROBLEMS & NOT STARTED WORKS
Sl. No | District | Name of Location | Admin. Sanction (Rs.in lakhs)
366 SUB CENTERS - 2010-11
1 | VZM | P.Chenneru | 14
2 | WG | Pathamupparu | 14
3 | PKSM | Naidupalem | 14
4 | PKSM | Donakonda | 14
5 | PKSM | R Kothapalli | 14
6 | PKSM | Pedakolukula | 14
7 | PKSM | Gurrapusala | 14
8 | NLR | Gundavolu / Obulayapalli | 14
9 | KDP | Peddabediki | 14
10 | KDP | Annasamudram | 14
11 | ATP | Yelukuntla | 14
151 SUB CENTERS - 2011-12
12 | PKSM | Ramaiahpatnam | 14
13 | PKSM | DG Peta | 14
14 | PKSM | Marriguntupalli | 14
15 | CTR | Punugupalli (Pathegada ) | 14
16 | CTR | Kadiravanicheruvu ( K.Doddipalli) | 14
17 | CTR | Nariganipalli | 14
18 | KDP | Bodeddulapalli | 14
436 SUB CENTERS - 2012-13
19 | SKLM | K.Gumadam | 14
20 | VZM | Kaviripalli Sambar | 14
21 | VZM | Kasipatnam Makkuva | 14
22 | VZM | Tompalapadu Neelakantapuram | 14
23 | VZM | Babbidi Duddukhallu | 14
24 | VSP | Konam | 14
25 | VSP | Chippada | 14
26 | VSP | Gompa | 14
27 | VSP | Akkireddy palem - 1 | 14
28 | VSP | Duvvada | 14
29 | EG | Batnavilli | 14
30 | WG | Prathikollalanka | 14
31 | KRI | Kammavaripalem | 14
32 | KRI | Obulapuram | 14
33 | KRI | Chivetikallu | 14
34 | PKSM | Kalavakuru | 14
35 | PKSM | Kunkalamarru | 14
36 | PKSM | Basinepalli | 14
37 | PKSM | Chimidithapadu | 14
38 | PKSM | Nainapalli | 14
39 | PKSM | Boddikurapadu | 14
40 | PKSM | D.G.Peta | 14
41 | PKSM | Kambaladinne | 14
42 | PKSM | Ulichi | 14
43 | NLR | Jammalapalem | 14
44 | CTR | Kammacheruvu | 14
45 | CTR | Marella | 14
46 | CTR | Pathegada | 14
47 | KDP | Rowthukunta | 14
48 | ATP | Korivipalli | 14
RAS
49 | VZM | RRB Puram (Kondachilakam) | 14
50 | VZM | Mathumuru (Thangalam) | 14
51 | ATP | Settipalli | 9
52 | ATP | Inagalore | 9
53 | ATP | Muttala | 9
54 | ATP | Nagaruru | 9
55 | WG | Nagidipalem | 9
56 | KRI | Bandipalem | 11.3

## Completed to be Handed over
Building completed and to be handed over by user department
Sl. No | Name of District | Name of Centre | Sanction Amount (Rs. In lakhs)
366 SUB CENTERS - 2010-11
1 | SKLM | Chinakosta | 9.5
2 | VZNG | Lakkidam (Thadipudi) | 14
3 | EG | Draksharamam | 9
4 | EG | Nalluru | 11
5 | EG | Tanukuwada | 11
6 | EG | Sri Rangapatnam-1 | 9
7 | EG | K.O.Mallavaram | 11
8 | EG | Suryaraopeta | 12
9 | EG | Peddipalem-1 | 11
10 | EG | Singampalli | 11
11 | EG | Dugrada-1 | 9
12 | WG | Dongapindi | 11.4
13 | KRI | Seetharamapuram | 11.38
14 | KRI | Kommuru | 11.35
15 | PKSM | Mittapalem | 14
16 | PKSM | Nanadanamaralla | 9
17 | PKSM | Devangapuri | 9
18 | NLR | Venadu | 14
19 | NLR | Tegacherla | 14
20 | KDP | Tangutoor | 9
21 | KNL | R.Krishnapuram | 10.15
151 SUB CENTERS - 2011-12
22 | VZM | Sarika | 14
23 | KRI | Vadlamannadu | 11.67
24 | KRI | Mallampalli (Mallaparajugudem) | 14
25 | PKSM | Pathapadu | 14
26 | NLR | Raviguntapalem | 14
27 | CTR | Bandlavanka (M.V.palli) | 14
28 | ATP | Jowkulakothapalli | 14
29 | KNL | Yerragudi | 9.45
436 SUB CENTERS - 2012-13
30 | SKLM | Chorlangi | 14
31 | SKLM | K.Veeragattam | 14
32 | SKLM | Kadagandi | 14
33 | SKLM | Pedda Polla | 14
34 | SKLM | Kodisa | 14
35 | SKLM | Nowgam | 14
36 | SKLM | Labba | 14
37 | SKLM | Bellupatia | 14
38 | SKLM | Budarasingi | 14
39 | SKLM | Vatapagu | 14
40 | SKLM | Gulumuru | 14
41 | VZM | Kottaguda Thadikonda | 14
42 | VZM | Dummangi Thadikonda of G.L.Puram | 14
43 | VZM | Rastakuntubai Regidi | 14
44 | VZM | Manda Thadikonda | 14
45 | VZM | Pedaguttili Mondemkhallu | 14
46 | VZM | Rella Thadikonda | 14
47 | VSP | Pedabodigallam | 14
48 | VSP | Yarada | 14
49 | VSP | Chinagangavaram | 14
50 | EG | Pagadalapeta | 14
51 | EG | Chitrada | 14
52 | EG | Chandrampalem | 14
53 | EG | Veeravaram | 14
54 | EG | D.Polavaram | 14
55 | EG | Balabhadrapuram | 14
56 | EG | Maredubaka | 14
57 | EG | Mogalikuduru | 14
58 | EG | Kesanapalli | 14
59 | EG | Maredubaka | 14
60 | WG | Kavvagunta | 14
61 | WG | Venkatarayapalem | 14
62 | WG | Venkatapuram | 14
63 | KRI | Kudapa | 14
64 | KRI | Tarakaturu | 14
65 | KRI | Vakkalagadda | 14
66 | KRI | Vakkalagadda | 14
67 | KRI | Adapavaripalem | 14
68 | KRI | Thotlavalluru (North) | 14
69 | NLR | Mamuduru | 14
70 | NLR | Ayyavaripalli | 14
71 | NLR | Budawada | 14
72 | NLR | Hasanapuram | 14
73 | NLR | Nandavaram | 14
74 | NLR | Revuru | 14
75 | NLR | Somasila | 14
76 | NLR | Tamidipadu | 14
77 | NLR | Vasili | 14
78 | CTR | Enugondapalem | 9
79 | CTR | Modiyamvaripalli | 9
80 | CTR | Vittalam | 9
81 | ATP | Bandameeda palli | 14
82 | ATP | Kodipalli | 14
83 | ATP | Kamathampalli | 14
84 | ATP | Daniyancheruvu | 14
85 | KNL | Kuppagal | 14
86 | KNL | Kadithota | 14
87 | KNL | Nadichagi | 14
88 | KNL | Urukunda | 14
89 | KNL | Yerigeri | 14
90 | KNL | Kosigi-1 | 14
91 | KNL | Kosigi-11 | 14
92 | KNL | Duddi | 14
93 | KNL | Vandagal | 14
94 | KNL | Chinna Thumbalam | 14

## RAS-ONGOING
DETAILS OF REVISED ADMINISTRATIVE SANCTION FOR ONGOING WORKS UNDER NRHM
Sl. No | Name of District | AS/RAS amoount | Name of Centre | RAS required (Rs. In lakhs) | Status of Work
271 SUB CENTERS - 2009-10
1 | PKSM | 9 | Pamidipadu | 12 | Columns raised upto roof level
2 | PKSM | 9 | Dharmavaram | 12.2 | basement level completed
|  | 18 |  | 24.2